## MPR 1.3_Project under progress
(April 2025 - March 2026)
For the month (As on 1 Dec 25)
MPR Project Wing/Projects under progress
A. Under Progress - Sewage inflow to STP started- under trial operations; COD to be Declared
Sl. No. | Project | HAM/DBOT | Total Sanctioned Cost(Cr) | STP Capacity - New (MLD) | Date of start of trial operation | Reasons for delay in COD declaration
1 | I&D and STP at Unnao | HAM | 102.2 | 15 | 2023-11-07 | Trunk sewer along the original alignment has settled. Repair of the same is in progress.
2 | Pollution Abatement works for River Ganga at Hooghly Chinsurah | DBOT | 161.99 | 26.5 | Work yet to be completed | The STP is operational with partial flow. The remaining work of the I&D sewer line could not be completed earlier as open-cut excavation was not feasible. Now, under the approved variation, the balance work will be completed through trenchless pipeline laying.
3 | I&D and STP at Digha | HAM | 824 | 100 | 2025-03-01 | CoD will be declared after the completion of the trial run and successful achievement of the KPIs.
4 | I&D and STP at Khankharbagh | HAM | 578.89 | 50 | 2025-03-01 | CoD will be declared after the completion of the trial run and successful achievement of the KPIs.
5 | I&D and STP at Moradabad | HAM | 149.23 | 25 | 2025-07-01 | Trials post-construction completion not yet complete due to pending power connection from the State.
6 | I&D and STP at Jangipur | DBOT | 68.47 | 13 | 2025-06-01 | Under trial run and successful achievement of the KPIs.
7 | I & D and STP at Kota | DBOT | 258.48 | 36 | Work yet to be completed | The STP is operational from Dec-2022
8 | I&D and STP at Muzaffarnagar | HAM | 234.03 | 54.5 |  | COD declared for 22 MLD STP; Partial COD declared for 32.5 MLD STP due to pending work on IPS 2A. The IPS 2A work has been completed. Full COD declaration documentation under review at UPJN.
9 | I&D and STP at Lucknow | DBOT | 240.93 | 42.5 | 2024-09-01 | 3.5 MLD under progress (39 MLD under operational)
10 | I&D and STP at Howrah, Bally and Kamrahati & Baranagar | HAM | 595.72 | 187 |  | Partially COD declared
B. Under Progress - Effective Date to be declared
Sl. No. | Project | HAM/DBOT | Total Sanctioned Cost(Cr) | STP Capacity - New (MLD) | Date of award of LOA | Reasons for delay in Effective date declaration
1 | Interception & Diversion and STP works at Lucknow, Phase-II Part-II | HAM | 351.03 | 100 | 02-06-2025 (Concession Agreement executed on 26/08/2025) | Effective Date to be declared by 27 December 2025. Pending Conditions precedent include (i) Financial closure; (ii) BEP Approval; (iii) Construction Plan approval; (iv) Phase I design drawing Submission; (v) Escrow Agreement. Site survey, soil investigations, site clearing completed.
2 | I & D and STP at Dhanbad | HAM | 808.33 | 192 | 2025-10-15 | Due to land permission. Land for two STPs is clear for which spearate effective date may be given.

## MPR 1.4_KSDC
(April 2025 - March 2026)
For the month of November
Organisation: Knowledge-cum-Skill Development Centre (KSDC)
Sl. No. | Activity | Till October 25 | 2025-11-01 | Total
1 | Web posts | 0 | 0 | 0
2 | Training/ Workshops | 1 | 0 | 1
3 | Seminar/ Webinar | 0 | 0 | 0
4 | Exposure Visits | 0 | 0 | 0
5 | URMP Related | 0 | 0 | 0
6 | Technical Support | 0 | 0 | 0
7 | Research/ Academic | 0 | 0 | 0
8 | Publications | 0 | 0 | 0
Annexure
List (Type 2,3,4,5) November
Sl. No. | Event Topic | Type | Venue | Number of Participants | Date/Days /Duration
11.09.2025 to 13 .09.2025
List (Type 1,6) November
Sl. No. | Subject |  | Date
List (Type 7) November
Sl. No. | Subject |  | Date
1
2
3

## MPR 3.1 CPCB
(April 2025 - March 2026)
For the month of November, 2025
Technical Division / CPCB related
Sl. No. | Activity | Till Oct-25 | 2025-11-01
1 | STP Inspection Reports Received **
| Uttrakhand | Apr'25- Jul'2025 | -
| Uttar Pradesh | Apr'25- Jul'2025 | -
| Bihar | Apr'25- Jul'2025 | -
| Jharkhand | Apr'25- Jul'2025 | -
| West Bengal | Apr'25- Jul'2025 | -
2 | River water Quality Data Received *
| Uttrakhand | Apr'25- Jun'2025 | -
| Uttar Pradesh | Apr'25- Jun'2025 | -
| Bihar | Apr'25- Jun'2025 | -
| Jharkhand | Apr'25- Jun'2025 | -
| West Bengal | Apr'25- Jun'2025 | -
3 | GPI Inspection Report received *
| Target (8th Round - till 15th Jan2026) | Covered | Annexure A
| 3726 (Ganga: 1299; Yamuna2427) | 3542 | 3542 (No Change)
4 | River water Quality Data upload on GKC *
| Uttrakhand | Jan'25- Jun'2025 | -
| Uttar Pradesh | Jan'25- Jun'2025 | -
| Bihar | Jan'25- Jun'2025 | -
| Jharkhand | Jan'25- Jun'2025 | -
| West Bengal | Jan'25- Jun'2025 | -
5 | Number of Publications/Reports | 21 | 3
* Pls indicate period
** Pls indicate month
Annexure for S.No 5
S.No. | Name of Document | Date
1 | CPCB Report of 47 Yamuna Drains monitoring (May-Sept'2025) | 2025-11-21
2 | MoM of meeting held at CPCB, RD Kolkata on 18.11.2025 to Finalise Additional drains fro inclusion in the Regular monitoring Program of West Bengal | 2025-11-26
3 | Progress Report of Namami Gange Funded Projects (April-Sept,2025) | 2025-11-06
Annexure A for S.No 3
| Total GPIs | 3726
| Inspected | 3542
| Complied | 1310
| Non-Complied | 510
| Temporary Closed | 244
| Permanently Closed | 25

## MPR 3.2_Regulatory Cell
(April 2025 - March 2026)
For the month of November (As on 30th Nov 25)
Technical Division / Regulatory Cell
A | Pending Applications
1 | Pending Application at the end of Oct 25 | 14
2 | Application returned back in Nov 25 | 3
3 | Applications decided in Nov 25 | 1
4 | New Applications received in Nov 25 | 2
5 | Pending Application at the end of Nov 25 | 12
6 | Out of S.No. 5, applications pending more than 3 months ( Received before 1st Sep) | 8
5= 1-2-3+4
B | Regulatory Cell meeting
Date | Meeting Number | Cases Considered | Cases Deferred | Cases Recommended
2025-11-07 | 12 | 7 | 4 | 3
Annexure for A/S.No 6
S.No. | Subject | Applicant | Date | Status
1 | Seeking permission to draw water from Yamuna for construction of “4 laning of Aligarh-Palwal section of NH-334D”, in the state of Uttar Pradesh and Haryana on HAM mode under NH(0) Scheme | Project Director, NHAI, PIU-Aligarh | 17/02/2025. | 12th cell meeting decided to return the proposal
2 | Construction of over bridge on Yamuna River for laying 1100 mm diameter DI k-7 pipeline for surface source water supply to district Mathura under Jal Jeevan Mission (Phase-4) | UPJN (R), Mathura | 28/02/2025. | 12th cell meeting decided to return the proposal
3 | Construction of Water Sport Ramp Boat Shed Retaining Wall and Jetty on the Banks of Saryu River in Ayodhya | Project Manager U.P.S.T.D.C. | 2025-04-24 | Put to EDT on 06/11/25
4 | Construction of Proposed State of the art Bathing Ghat on the Banks of the Ganges from Panchal Ghat to old Ghatiya in Farrukhabad | Project Manager U.P.S.T.D.C. | 2025-05-02 | Put to EDT on 06/11/25
5 | Withdrawal of additional 110 Cusec water from River Gomti for capacity enhancement of Tandwa (proposed 50 Cusec), Bhainsa (proposed 30 Cusec), and Niyardeeh (proposed 30 Cusec) Pump Canals near Kerakat Rajwaha, Jaunpur, Uttar Pradesh. | Chief Engineer (Water Resource), Irrigation & Water Resource Department, Lucknow, Uttar Pradesh, | 05/05/2025 | Put to EDT on 06/11/25
6 | Hamirpur intake well | Executive Engineer Construction Division UP Jal Nigam (Urban) Hamirpur. | 31/05/2025 | 12th cell meeting decided to return the proposal
7 | Renewal for 7 years Ram anubhav kendra | Ayodhaya Development Authority | 2025-07-02 | Requested to proponent submit a Recommendations of renewed proposal through DGC and SGC via letter dated 17/10/2025
8 | Construction of a Major Bridge over the River Ghaghara | General Manager (Tech)/Project Director, NHAI, PIU-Lucknow | 2025-07-31 | No response to observations, File to be returned

## MPR 4.1_E-file status
eOffice closed files summary
(With initial total number of eFiles =7,375 on 25th Oct 2025)
Period | No. of eFiles closed
From 1st April 2020 –till 25th Oct 2025 | 104
26th Oct 2025 – till 31st Oct 2025 | 48
1st November 2025 to 30th November 2025 | 299
Total | 451
Wing/Section/ Unit wise summary from 26th Oct 2025 till 30th November 2025
i. SMD Section: 271
ii. Finance Wing: 42
iii. Communication Wing: 21
iv. Admin Wing: 13
Total: 347

## MPR 5.2_GKC
Monthly Progress Report- Gyanganga.ai (November 2025)
Generated on 1st December 2025
(1) Total documents as on 1st November 2025 - 1262
(2) Total number of documents uploaded between 1st to 30th November 2025 - 33
(3) Categories-wise details of documents uploaded between 1st to 30-st November 2025
Categories | Sub-categories | No. of documents
Publications |  | 0
Journals |  | 0
| Student Thesis Competition (STC) | 0
Articles |  | 0
Books |  | 0
Studies/Reports |  | 1
Guidelines |  | 0
Misellaneous |  | 0
Ganga River (Main Stem)Water Quality Data |  | 1
Data Set | River Atlas | 0
| Ganga River (Main Stem) Water Quality Data (CPCB) | 0
Coffes Table Books |  | 0
River Series |  | 31
Total |  | 33
(4) Details of documents uploaded between 1st to 30st November 2025:-
S.No | Category | Subject
1 | River Series | Asan: Socio-Ecological Profile
2 | River Series | Solani: Socio-Ecological Profile
3 | River Series | Garra: Socio-Ecological Profile
4 | River Series | Chandan: Socio-Ecological Profile
5 | Reports | Genetic Assessment of Aquatic Species in the Ganga River Basin Conservation Genetics Report
6 | River Series | Betwa: Socio-Ecological Profile
7 | River Series | Kali: Socio-Ecological Profile
8 | River Series | Song: Socio-Ecological Profile
9 | River Series | Chandrabhaga: Socio-Ecological Profile
10 | River Series | Tons: Socio-Ecological Profile
11 | Ganga River (Main Stem) Water Quality Data | Technical Manual for Identification of Freshwater Benthic Macroinvertebrates of India
12 | River Series | Ajay River
13 | River Series | Damodar River
14 | River Series | Mahananda River
15 | River Series | Rapti River
16 | River Series | Solani River
17 | River Series | Asan River
18 | River Series | Yamuna River
19 | River Series | Ghaghra River
20 | River Series | Kosi River
21 | River Series | Rupnarayan River
22 | River Series | Ramganga River
23 | River Series | Garra River
24 | River Series | Chandan River
25 | River Series | Suswa River
26 | River Series | Life in Song River
27 | River Series | Chambal River
28 | River Series | Gandak River
29 | River Series | Girwa River
30 | River Series | Gomti River
31 | River Series | Son River
32 | River Series | Bagmati River
33 | River Series | Sharda River
(5) Total documents as on 1st December 2025 - 1295

## MPR 5.3-Prayag status
(April 2025 - March 2026)
For the month of November (As on 1st Dec 25)
MPR Prayag/GeoPortal etc
A | OCEMS Status
1 | Installation and Data Staus
a | No. of STPs with OCEMS Installed | 263
b | No. of STPs with Flow Data received | 154
c | No. of STPs with Influent Characteristic Data received | 91
d | No. of STPs with Effluent Characteristic Data received | 116
2 | Data Reliability Status
a | No. of STPs with Satisfactory Data received | 128
b | No. of STPs with Poor Data Quality (Annex A1) | 6
c | No. of STPs with No Data Received (Annex A2) | 135
B | OCEMS based Results communicated to States till Month | Communicated till Nov-2025
C | Eflows report updated till period | Updated till first quarter 2025
D | GDPMS
| No. of Meetings held in October | 55
| No. of Meetings held in November | 16
E | Prayag GEO Portal
| No. of Active GIS Layers (Annex B) | 30
| No. of Use Cases | 7
PRAYAG-MPR November 2025 (Item 5.3, MPR)

## MPR 5.4-Jan Ganga Vertical
(April 2025 - March 2026)
For the Month of October (As on 1st Nov. 25)
MPR Communication
| Followers | Till Previous Month (September ) | Current Month (October)
1 | Twitter | 126K | 125761
| Facebook | 448K | 456K
| Instagram | 83.5K | 94.3K
2 | In Current Month
a) | Webposts (excluding B and C) | Number of Images | Videos (Minutes)
| Twitter | 245 post | 31 videos (Total minutes approx 62 min)
| Facebook | 245 post | 29 videos (Total Minutes approx 45 min)
| Instagram | 180 | 49 Videos (Total minutes approx 30 min)
b) | Rebuttals on | Nil
| Social Media | Nil
c) | Positive Stories | 11 Stories (5 in collaboration on Instagram) |  | Annex A
Social Media
3 | Youtube
4 | Print Media
a) | Rebutted | Nil
b) | Positive Stories | 8 |  | Annex A
|  | Number of Events | Participation
5 | Events Organised by NMCG |  |  | Annex B
| Cleanliness Drives on various Ghats of Yamuna- Delhi | 5 | Approx. 1000
6 | Events through Partner |  |  | Annex B
a) | DGC | Approx. 2760 | Approx. 7,64,852
b) | NGO
c) | Institutes
7 | Sponsorship
| Third Party Events |  |  | Annex B
| Annex A | S. No 2 C, 4 B
S. No. | Title | Date | Coverage
1 | RFD (Patna) | 28th Oct, 2025
2 | RFD (Patna) | 26th Ocr, 2025
3 | Sisamau Nala (Kanpur) | 24th Oct, 2025
4 | RFD (Patna) | 22nd Oct, 2025
5 | STP public review (Rishkesh) | 17th Oct, 2025
6 | Treated Water | 17th Oct, 2025
7 | Natural Farming | 16th Oct,2025
8 | Har Ghar Jal | 15th Oct, 2025
9 | Fresh Water | 15th Oct, 2025
10 | Turning Treated Used Water into a Revenue Model | 10th Oct, 2025
11 | Natural Farming | 8th Oct, 2025
12 | Ganga and Pandu river rejuvenation | 4th Oct, 2025
13 | River monitoring will be done through drone and satellite imaging | 8th Oct, 2025
14 | India’s first conservation reserve, Asan Wetland | 4th Oct, 2025
15 | Infrastructure projects in UP | 12th Oct, 2025
16 | Action Plan for Ganga tributaries | 7th Oct, 2025
17 | Action plan for Harnandi river | 25th Oct, 2025
18 | Dolphin | 18th Oct, 2025
19 | Gomati river rejuvenation | 13th-Oct-2025
| Annex B | S. No 5,6,7
S. No. | Event Name (Activity Type) | Agency | Date | Venue | Participants
1 | Cleanliness Drives on Yamuna | NMCG | 2025-10-01 | Sonia Vihar (1st Pushta Ghat), Kalindi Kunj, ITO Chhath Ghat, Geeta Colony (Yamuna Ghat) | Schools, Universities, Youth Groups, NGOs etc.
2 | Special Campaign | District Ganga Committees & SMCG | 2nd to 31st Oct. 2025 | 5 States (93 DGCs) & 2 Cities | District Administration, associated partners, academic institutes, schools, universities, youth groups, NGOs and local communities etc.
Uttarakhand (8)
Uttar Pradesh (75)
Bihar (NIL)- due to elections
Jharkhand (4 +2 cities)
West Bengal (6)

## MPR 5.5 RCA
(April 2025 - March 2026)
For the month of NOVEMBER
Organisation River Cities Alliance
Sl. No. | Activity | Till October 25 | 2025-11-01 | Total
1 | Web posts | 43 | 4 | 47
2 | Workshops (excluding 5b /URMP Workshops) | 9 | 1 | 10
3 | Seminar/ Webinar/Meetings | 15 | 2 | 17
4 | Exposure Visits | 1 | 1 | 2
5 | URMP Related (Non Ganga Basin)
| a) Meetings in States | 6 | 0 | 6
| b) Workshops in States | 2 | 0 | 2
6 | Publications
| a) Newsletter | 3 | 0 | 3
| b) Others | 9 | 1 | 10
7 | Concept Notes | 7 | 0 | 7
Annexures
List (Type 2,3,4,5) November
Sl. No. | Event Topic | Type | Venue | Date/Days /Duration | Number of Participants
1 | Training Programme on "Eco-friendly riverfront development" | 2 | Delhi | 19.11.2025 to 20.11.2025 | 66
2 | Exposure visit for RCA members to various URMP-related sites in Delhi | 4 | Delhi | 20.11.2025 to 21.11.2025 | 39
3 | Expert lecture cum workshop on "Urban rivers: Challenges and management aspects" at Miranda House, Delhi | 3 | Delhi | 14.11.2025 | 25
4 | Training session on "Urban river management: A case of Yamuna River" at Mamta Modern School, Delhi | 3 | Delhi | 28.11.2025 | 250+
List (Type 1,6) November
Sl. No. | Subject | Type | Date
1 | Inspirational Monday Series on "Wetland urban wetland eco-tourism park in Rwanda" | 1 | 03.11.2025
2 | Inspirational Monday Series on "Sengkang floating wetland, Singapore" | 1 | 10.11.2025
3 | Inspirational Monday Series on "Constructed wetland in Mexico" | 1 | 17.11.2025
4 | Inspirational Monday Series on "Climate-resilient infrastructure, Florida" | 1 | 24.11.2025
5 | Draft compendium on "Legal provisions for floodplain delineation in India" | 6b | 18.11.2025
List (Type 7) November
Sl. No. | Subject | Type | Date
1
2
3