## MPR 1.3_Project under progress
(April 2025 - March 2026)
For the month (As on 30th April 2026)
MPR Project Wing/Projects under progress
A. Under Progress - Sewage inflow to STP started- under trial operations; COD to be Declared
Sl. No. | Project | HAM/DBOT | Total Sanctioned Cost(Cr) | STP Capacity - New (MLD) | Date of start of trial operation | Reasons for delay in COD declaration
1 | I&D and STP at Unnao | HAM | 102.2 | 15 | 2023-11-07 | Trunk sewer along the original alignment has settled. Repair of the same is in progress.
2 | Pollution Abatement works for River Ganga at Hooghly Chinsurah | DBOT | 161.99 | 26.5 | Work yet to be completed | The STP is operational with partial flow. The remaining work of the I&D sewer line could not be completed earlier as open-cut excavation was not feasible. Now, under the approved variation, the balance work will be completed through trenchless pipeline laying.
3 | I&D and STP at Digha | HAM | 824 | 100 | 2025-03-01 | CoD will be declared after the completion of the trial run and successful achievement of the KPIs.
4 | I&D and STP at Kankarbagh | HAM | 578.89 | 50 | 2025-03-01 | CoD will be declared after the completion of the trial run and successful achievement of the KPIs.
5 | I&D and STP at Moradabad | HAM | 149.23 | 25 | 2025-07-01 | COD declared - 04/03/2026
6 | I&D and STP at Jangipur | DBOT | 68.47 | 13 | 2025-06-01 | Under trial run and successful achievement of the KPIs.
7 | I & D and STP at Kota | DBOT | 258.48 | 36 | Work yet to be completed | The STP is operational from Dec-2022
8 | I&D and STP at Lucknow | DBOT | 240.93 | 42.5 | 2024-09-01 | 3.5 MLD under progress (39 MLD operational)
9 | I&D and STP at Howrah, Bally and Kamrahati & Baranagar | HAM | 595.72 | 187 |  | Partially COD declared
10 | I&D with STP works at Sapera Basti, Dehradun | DBOT | 78.99 | 15 |  | Under trial operations
11 | I & D and STP works at Muni ki reti, Neelkanth, Swarg aashram | DBOT | 94.06 | 12.8 |  | Under trial operations (Muni-Ki-Reti and Swargashram) Under Construction (Neelkanth)
12 | Interception and diversion of balance discharge of 13 drains and augmentation of Salori STP | DBOT | 331.75 | 43 |  | Under trial operations
13 | I&D and STP Works at Vrindavan | DBOT | 77.7 | 13 |  | Under trial operations
14 | I&D and STP Works for Assi-BHU Area (Phase II), Varanasi, Uttar Pradesh’ under Namami Gange Programme | DBOT | 308.09 | 55 |  | Completed. O&M Statrt Date - 17/03/2026
15 | I & D and STP Project at Phusro | DBOT | 61.05 | 14 | 10 MLD - Trial started on 15th Jan 2026. 4 MLD- Trial run started on 16th Feb 2026
16 | Interception and Diversion with STP) at Chakdah Municipal Town | DBOT | 121.66 | 15 | trial run started on 14th Feb 2026.
17 | Pollution Abatement Works for River Ganga at North Barrackpore municipality | HAM | 154.27 | 38 | 30 MLD- under trial run since 15.12.2025.
B. Under Progress - Effective Date to be declared
Sl. No. | Project | HAM/DBOT | Total Sanctioned Cost(Cr) | STP Capacity - New (MLD) | Date of award of LOA | Reasons for delay in Effective date declaration
1 | Interception & Diversion and STP works at Lucknow, Phase-II Part-II | HAM | 351.03 | 100 | 02-06-2025 (Concession Agreement executed on 26/08/2025) | Effective Date to be declared by 31st May 2026. Pending Conditions precedent include (i) BEP Approval; (ii) Construction Plan approval; (iv) Phase I design drawing Submission; (v) Escrow Agreement. Site survey, soil investigations, site clearing completed. Site level variations (Actual vs RFP) reported in the review meeting held on 25/02/2026 Basin excavation and retaining wall work started
2 | I & D and STP at Dhanbad | HAM | 808.33 | 192 | Effective date for STP-1 ,2&3 has been declared as 02.03.2026. | Due to pending land NOC the effective date for remaining STPs (STP-4 &5) is yet to be declared.

## MPR 1.5 Project Engg O&M
Details of Project Engineer Engagement in various STP projects, NMCG (O&M)
Sl No. | Name of the project | STP Capacity | Name of the Bidder | Last MPR approved by NMCG | Last MPR submitted by PE | Last Payment Made by NMCG | Last Invoice submitted by PE | Project Staus | Tentative Payment (Rs. In Cr)
1 | PE Haridwar STP Project | 68 MLD | M/s. Shah Technical Consultants Pvt. Ltd. | PE contract Completed |  |  |  | O&M
2 | PE Varanasi STP Project | 50 MLD | M/s. Mahindra Consulting Engineers Ltd. (MACE) | PE contract Completed |  |  |  | O&M
3 | PE Mathura STP Project | 30 MLD | M/s. Mahindra Consulting Engineers Ltd. (MACE) | PE contract Completed |  |  |  | O&M
4 | PE Prayagraj STP project | 14 MLD 42 MLD 16 MLD | M/s. AECOM India Pvt. Ltd. In JV with URS Scott Wilson India Consortium | Nov-24 | Mar-25 | 2024-08-01 | Mar-25 | O&M (Completed) | 0.4
5 | PE Kanpur STP project | 30 MLD 15 MLD 5 MLD | M/s. Shah Technical Consultants Pvt. Ltd. | Nov-25 | Jan-26 | Mar-25 | Mar-25 | O&M
6 | PE Howrah, Bally & Baranagar | 65 MLD 40 MLD 60 MLD | M/s. HaskoningDHV Consulting Pvt. Ltd. In JV with HaskoningDHV Nederland B.V | Dec-25 | Dec-25 | Dec-25 | Dec-25 | O&M (Completed)
7 | PE Budhana Muzaffarnagar STP Project | 10 MLD 22 MLD | M/s. Egis India Consulting Engineers Pvt. Ltd. | Jun-25 | Jun-25 | 2023-03-01 | 2025-06-01 | O&M (Completed)
8 | PE Moradabad STP Project | 25 MLD |  | 2026-02-01 | Mar-26 | 2026-02-01 | 2026-02-01 | O&M
9 | PE Mirzapur Ghazipur | 8.5 MLD 8.5 MLD 21 MLD | M/s. NJS Engineers India Pvt. Ltd. | Feb-26 | Mar-26 | 2025-12-01 | Feb-26 | O&M
10 | PE Maheshtala STP | 35 MLD | M/s. WAPCOS Limted | Feb-26 | Mar-26 | Aug-25 | Aug-25 | O&M
11 | PE Bareilly | 42 MLD 20 MLD 1 MLD | M/s. HaskoningDHV Consulting Pvt. Ltd. In JV with HaskoningDHV Nederland B.V | PE contract Completed |  |  |  | O&M
12 | PE Ayodhya | 32 MLD |  | PE contract Completed |  |  |  | O&M
13 | PE Farrukhabad-Fatehgarh | 30 MLD 20 MLD 2 MLD |  | PE contract Completed |  |  |  | O&M
Total
Details of Project Engineer in various CETP Projects, NMCG
Sl No. | Name of the project | CETP Capacity | Name of the Bidder
1 | Project Engineer Services for Implementation of 20 MLD Tannery CETP & associated components at Jajmau, Kanpur, Uttar Pradesh | 20 MLD | M/s. Tamil Nadu Water Investment Company Limted (TWIC)
2 | Project Engineer Services for the upgradation of 4.5 MLD CETP for Tanneries with Soak Stream Treatment, Common Chrome Recovery System, Composite Stream Treatment on ZLD Technology at Banthar, Unnao Uttar Pradesh | 4.5 MLD | M/s. NJS Engineers India Pvt. Ltd.

## MPR 1.5 Proj engg under progres
Details of Project Engineer Engagement in various STP projects, NMCG (Under Progress)
Sl No. | Name of the project | STP Capacity | Name of the Bidder | Last MPR approved by NMCG | Last MPR submitted by PE | Last Payment Made by NMCG | Last Invoice submitted by PE | Project Staus | Tentative Payment (Rs. In Cr)
1 | PE Digha & Kankarbagh STP Project | 150 MLD 50 MLD | M/s. Mahindra Consulting Engineers Ltd. (MACE) | 2025-12-01 | 2026-03-01 | 2025-06-01 | 2025-06-01 | Under Progress
2 | PE Bhagalpur STP Project | 40 MLD 5 MLD | M/s. Egis India Consulting Engineers Pvt. Ltd. | 2026-02-01 | 2026-03-01 | 2026-02-01 | 2026-02-01 | Under Progress
3 | PE Agra STP Project | 31 MLD 35 MLD 100 MLD | M/s. NJS Engineers India Pvt. Ltd. | 2026-02-01 | 2026-03-01 | 2026-02-01 | 2026-02-01 | Under Progress
4 | PE North Barrackpore STP project | 30 MLD 8 MLD | M/s. MaRS Planning & Engineering Services Pvt. Ltd. | 2025-09-01 | 2026-03-01 | 2026-02-01 | 2026-02-01 | Under Progress
5 | PE Meerut STP Project | 220 MLD | M/s. AECOM India Pvt. Ltd. In JV with M/s. PDCOR Limited | 2026-03-01 | 2026-03-01 | 2026-02-01 | 2026-02-01 | Under Progress
6 | PE Saharanpur STP Project | 135 MLD | M/s. MSV International Tech Private Limited in consortium with M/s. MSV international Inc. & M/s. BMRV Engineering Consultant LLP | 2025-05-01 | 2026-02-01 | 2025-05-01 | 2026-02-01 | Under Progress
7 | PE Garden Reach STP Project | 65 MLD | M/s. Fichtner Consulting Engineers (India) Pvt. Ltd. | 2026-02-01 | 2026-03-01 | 2026-02-01 | 2026-02-01 | Under Progress
8 | PE Gokul Barrage STP Project | 60 MLD | M/s. NJS Engineers India Pvt. Ltd. | 2026-02-01 | 2026-03-01 | 2026-02-01 | 2026-02-01 | Under Progress
9 | PE Dhanbad STP Project | 18 MLD 21 MLD 75 MLD 60 MLD 18 MLD | M/s. MSV International Tech Private Limited in consortium with M/s. MSV international Inc. & M/s. BMRV Engineering Consultant LLP | 2026-01-26 | 2026-03-01 | 2025-04-01 | Project has divided in 5 packages, thus for alliging the payment according the package request letter received from PE on 07.05.2026. The request is under consideration. | Under Progress
10 | PE Lucknow STP Project | 100 MLD | M/s. Shah Technical Consultants Pvt. Ltd. | 2026-02-01 | 2026-02-01 | 2026-02-01 | 2026-02-01 | Under Progress
11 | Katihar | 55 MLD | [5 empty] | Under Tendering
12 | Aligarh | 113 MLD | [5 empty] | Under Tendering
13 | Siliguri | 49 MLD | [5 empty] | Under Tendering
14 | Moradabad | 80 MLD | [5 empty] | Under Tendering
15 | Durga Drain, Varanasi | 60 MLD | [5 empty] | Under Tendering
16 | Pt. DDU Nagar, Chandauli | 45 MLD | [5 empty] | Under Tendering
17 | Arrah | 47 MLD | [5 empty] | Under Tendering
Total
Details of Project Engineer in various CETP Projects, NMCG
Sl No. | Name of the project | CETP Capacity | Name of the Bidder
1 | Project Engineer Services for Implementation of 20 MLD Tannery CETP & associated components at Jajmau, Kanpur, Uttar Pradesh | 20 MLD | M/s. Tamil Nadu Water Investment Company Limted (TWIC)
2 | Project Engineer Services for the upgradation of 4.5 MLD CETP for Tanneries with Soak Stream Treatment, Common Chrome Recovery System, Composite Stream Treatment on ZLD Technology at Banthar, Unnao Uttar Pradesh | 4.5 MLD | M/s. NJS Engineers India Pvt. Ltd.

## MPR 1.4_KSDC
April 2026 - March 2027
For the month of April 2026
Knowledge-cum-Skill Development Centre (KSDC)
S.No | Activity | Till March, 2026 | April, 2026 | Total
1 | Web posts | 0 | 0 | 0
2 | Training/ Workshops | 6 | 0 | 6
3 | Seminar/ Webinar | 0 | 0 | 0
4 | Exposure Visits | 0 | 0 | 0
5 | URMP Related | 0 | 0 | 0
6 | Technical Support | 0 | 0 | 0
7 | Research/ Academic | 0 | 0 | 0
8 | Publications | 0 | 0 | 0
Annexure
List (Type 2,3,4,5) April
S.No | Event Topic | Type | Venue | Date/Days/Duration | No. of Participants
List (Type 1,6) April
| Sl. No. | Subject |  | Date
List (Type 7) April
| Sl. No. | Subject |  | Date
1
2
3

## MPR 3.1 CPCB
(April 2025 - March 2026)
For the month of April, 2026
Technical Division / CPCB related
Sl. No. | Activity | Till Mar-26 | 2026-04-01
1 | STP Inspection Reports Received **
| Uttrakhand | Aug'25 - Nov'25 | -
| Uttar Pradesh | Aug'25 - Nov'25 | -
| Bihar | Aug'25 - Nov'25 | -
| Jharkhand | Aug'25 - Nov'25 | -
| West Bengal | Aug'25 - Nov'25 | -
2 | River water Quality Data Received *
| Uttrakhand | Jul'25- Sep'2025 | Oct'25- Dec'2025
| Uttar Pradesh | Jul'25- Sep'2025 | Oct'25- Dec'2025
| Bihar | Jul'25- Sep'2025 | Oct'25- Dec'2025
| Jharkhand | Jul'25- Sep'2025 | Oct'25- Dec'2025
| West Bengal | Jul'25- Sep'2025 | Oct'25- Dec'2025
3 | GPI Inspection Report received *
| Target (8th Round - till 15th Jan2026) | Covered | Annexure A
| 3703 (Ganga: 1296; Yamuna: 2407) | 3703 | 3703
4 | River water Quality Data upload on GKC *
| Uttrakhand | Jan'25- Sep'2025 | Jan'25- Dec'2025
| Uttar Pradesh | Jan'25- Sep'2025 | Jan'25- Dec'2025
| Bihar | Jan'25- Sep'2025 | Jan'25- Dec'2025
| Jharkhand | Jan'25- Sep'2025 | Jan'25- Dec'2025
| West Bengal | Jan'25- Sep'2025 | Jan'25- Dec'2025
5 | Number of Publications/Reports | 42 | 8
* Pls indicate period
** Pls indicate month
Annexure for S.No 5
S.No. | Name of Document | Date
1 | CPCB communication on MWQM data of Nitrate of 112 Stations (2024) | 2026-04-01
2 | Progress Report of Namami Ganga Sanctioned Projects (PIAS, SER and WQM) | 2026-04-06
3 | CPCB Report of 52 Yamuna Drains monitoring (May2025-Feb'2026) | 2026-04-23
4 | CPCB email of NWMP Ganga Water Quality Data Jan-Dec2025 | 2026-04-29
5 | CPCB letter regarding Arbitration between CPCB and JV of M/s SC::AN and M/sAaxis Nano (Filing of petition in High Court) | 2026-04-29
6 | CPCB letter to UKPCB regarding Monitoring of STPs less than 5MLD on HalfYearly basis (Apr-Sept and Oct-March) and to initiate monitoring and submit Report of Apr-Sept2026 | 2026-04-30
7 | CPCB directions US 5 of E (P) Act, 1986 to M/s Shuban Tanners JajMau, Kanpur | 28.04.2026
8 | MoM of the meeting by CPCB dtd. 23.04.2026 in compliance to Hon'ble NGT order dated 29.01.2026 in matter of OA 718/2024 | 2026-04-30
Annexure A for S.No 3
| Total GPIs | 3703
| Inspected | 3703
| Complied | 2617 | << Total Action Completed Till date
| Non-Complied | 507# | << Total Action Completed Till date
| Temporary Closed | 422 | << Total Action Completed Till date
| Permanently Closed | 106 | << Total Action Completed Till date
| #Action Pending from Concerned SPCBs/PCC | 51

## MPR 3.2_Regulatory Cell
(April 2026 - March 2027)
For the month of April (As on 30th April 26)
Technical Division / Regulatory Cell
A | Pending Applications
1 | Pending Application at the end of March 26 | 13
2 | Application returned back in April 26 | 1
3 | Applications decided in April 26 | 0
4 | New Applications received in April 26 | 3
5 | Pending Application at the end of April 26 | 15
6 | Out of S.No. 5, applications pending more than 3 months ( Received before 1st Jan 2026) | 4
5= 1-2-3+4
B | Regulatory Cell meeting
Date | Meeting Number | Cases Considered | Cases Deferred/ Return | Cases Recommended
2026-04-13 | 14 | 6 | 4 | 2
Annexure for A/S.No 6
S.No. | Subject | Applicant | Date | Status
1 | Discharge of Treated Effluent from MDA operated STPs into Chap Salawa Minor under the 220 MLD STP Project, Meerut | Chief Engineer, UP Jal Nigam (Rural) | 2025-10-29 | The proposal was considered in the 14th Cell Meeting, wherein the Cell decided to seek clarification from the concerned State regarding their objections to the proposed discharge.
2 | Renewal for 7 years Ram anubhav kendra | Ayodhaya Development Authority | 2025-07-02 | Proposal discussed in 14th Cell meeting, the discussion remained inconclusive
3 | Widening and strengthening of the Ayodhya–Billharghat (A.B. Bandha) road along the bank of the River Saryu. | PWD | 17/012/2025 | Proposal considered in 14th Cell meeting, Cell sought a clarification and decided to reconsidered in next cell meeting
4 | Construction of Major bridge over River Ghaghara, a) Northern Bypass and b) Southern Bypass | Project director, NHAI, PIU, Ayodhya | 2025-12-18 | Proposal considered in 14th Cell meeting, Cell sought a clarification and decided to reconsidered in next cell meeting

## MPR 4.1_E-file status
eOffice closed files summary
(With initial total number of eFiles =7,375 on 31st January 2026)
Period | No. of eFiles closed
From 1st April 2020 –till 25th Oct 2025 | 104
26th Oct 2025 – till 31st Oct 2025 | 48
1st November 2025 to 30th November 2025 | 299
1st December 2025 to 31st December 2025 | 1
1st January 2026 to 31st January 2026 | 69
1st February 2026 to 28th February 2026 | 1
1st March 2026 to 31st March 2026 | 0
1st April 2026 to 30th April 2016 | 1
Total | 523
Wing/Section/ Unit wise summary from 26th Oct 2025 till 30th November 2025
i. SMD Section: 271
ii. Finance Wing: 42
iii. Communication Wing: 21
iv. Admin Wing: 13
Total: 347
Wing/Section/ Unit wise summary from 1st December 2025 to 31st December 2025
i. SMD Section: 1
Total: 1
Wing/Section/ Unit wise summary from 1st January 2026 till 31st January 2026
i. SMD Section: 67
ii. O/o ED (Tech): 2
Total: 69
Wing/Section/ Unit wise summary from 1st February 2026 till 28th February 2026
i. O/o ED/ Finance: 01
Wing/Section/ Unit wise summary from 1st March 2026 till 31st March 2026
i. Nill
Wing/Section/ Unit wise summary from 1st April 2026 till 30th April 2026
i. Communication Wing: 1

## MPR 5.2_GKC
Monthly Progress Report- Gyanganga.ai (April 2026)
Generated on 30th April 2026
Sl. No. | Title | Till 31st March 2026 | 2026-04-01 | Total (as on 30th April 2026)
1 | Total Number Document on GKP | 1371 | 9 | 1380
2 | Other Literature on River Ganga | 10316 | 21 | 10337
Categories-wise details of documents uploaded between 1st to 30th April 2026
Categories | Sub-categories | No. of documents
Publications |  | 0
Journals |  | 0
| Student Thesis Competition (STC) | 0
Articles |  | 0
Books |  | 2
Studies/Reports |  | 0
Guidelines |  | 0
Misellaneous |  | 0
Ganga River (Main Stem)Water Quality Data |  | 0
Data Set | River Atlas | 0
| Ganga River (Main Stem) Water Quality Data (CPCB) | 5
Coffes Table Books |  | 0
River Series |  | 0
Maps |  | 2
Total |  | 9
Details of documents uploaded between 1st to 30th April 2026
S.No | Category | Subject | Organization
1 | Water Quality Data | Ganga MWQM - FS | Central Pollution Control Board (CPCB)
2 | Water Quality Data | Ganga MWQM - FC | Central Pollution Control Board (CPCB)
3 | Water Quality Data | Ganga MWQM - PH | Central Pollution Control Board (CPCB)
4 | Water Quality Data | Ganga MWQM - DO | Central Pollution Control Board (CPCB)
5 | Water Quality Data | Ganga MWQM - BOD | Central Pollution Control Board (CPCB)
6 | Maps | Ganga Basin Cities Map | NMCG
7 | Maps | Tributaries of Ganga River | NMCG
8 | Books | Aquatic diversity and Environmental variables of River Rupnarayan | CENTRAL INLAND FISHERIES RESEARCH INSTITUTE (CIFRI)
9 | Books | Fish Nutrient Atlas of River Ganga | CENTRAL INLAND FISHERIES RESEARCH INSTITUTE (CIFRI)

## MPR 5.3-Prayag status
(April 2026 - March 2027)
For the month of April (As on 30th April 26)
MPR PRAYAG/ GeoPortal etc
A | OCEMS Status
1 | Installation and Data Status
a | No. of STPs with OCEMS Installed | 276
b | No. of STPs with Flow Data received | 194
c | No. of STPs with Influent Characteristic Data received # | 169
d | No. of STPs with Effluent Characteristic Data received | 239
2 | Data Reliability Status
a | No. of STPs with Satisfactory Data received | 230
b | No. of STPs with Poor Data Quality (Annex A1) | 6
c | No. of STPs with No Data Received (Annex A2) | 28
B | OCEMS based Results communicated to States till Month | Communicated till April 2026
C | Eflows report updated till period | Updated till Oct-Dec 2025
D | GDPMS
| No. of Meetings held in April 2026 | 21
| No. of Meetings held in March 2026 | 96
E | Prayag GEO Portal
| No. of Active GIS Layers (Annex B) | 29
| No. of Use Cases | 3
No. of STPs with Poor Data Quality (Annex A1)
| STP Name | Availability (%)
| 50 KLD STP Srikot Pauri | 0.66
| 15 MLD STP Kairana | 15.42
| 75 KLD STP Srikot Pauri | 16.7
| 1.0 MLD STP Badrinath | 19.1
| 5 MGD Kapashera | 22.36
| 22 MLD STP Uttarapara | 22.81
No. of STPs with No Data Received (Annex A2)
| Name | Capacity (MLD) | State | City
| 26.5 MLD STP at Chinsurah | 26.5 | West Bengal | Chinsurah
| 6.5 MLD STP Naihati | 6.5 | West Bengal | Naihati
| 43 MLD STP Salori | 43 | Uttar Pradesh | Prayagraj
| 18 MLD STP Kachanpara | 18 | West Bengal | Kachanpara
| 0.66 MGD Molar Band | 2.5 | Delhi | New Delhi
| 65 MLD STP Arupara Howrah | 65 | West Bengal | Arupara
| 1 MLD STP ANUPSHAHAR | 1 | Uttar Pradesh | Anupshahar
| 1.5 MLD STP Anupshahar (UPJN) | 1.5 | Uttar Pradesh | Anupshahar
| 14 MLD STP Baghpat | 14 | Uttar Pradesh | Baghpat
| 15 MLD STP Kasganj | 15 | Uttar Pradesh | Kasganj
| 21 MLD STP Pakka Bagh | 21 | Uttar Pradesh | Etawah
| 10.445 MLD STP Etawah | 10.445 | Uttar Pradesh | Etawah
| 9.5 MLD STP Nawadwip | 9.5 | West Bengal | Nawadwip
| 13.50 MLD STP Tixi Nala | 13.5 | Uttar Pradesh | Etawah
| 1.5 MLD STP Harmu | 1.5 | Jharkhand | Ranchi
| 60 MLD STP Baranagar | 60 | West Bengal | Baranagar
| 20 MLD CETP Jajmau | 20 | Uttar Pradesh | Kanpur
| 10 MLD STP at Kankinara | 10 | West Bengal | Bhatpara
| 40 MLD STP at Bally Howarh | 40 | West Bengal | Bally
| 21 MLD STP ETAWAH | 21 | Uttar Pradesh | Etawah
| 30 MLD STP JAUNPUR | 30 | Uttar Pradesh | Jaunpur
| 7 MLD STP Mirzapur | 7 | Uttar Pradesh | Mirzapur
| 1.5 MLD STP Chutia | 1.5 | Jharkhand | Ranchi
| 2.57 MLD STP Bokaro | 2.57 | Jharkhand | Bokaro
| 15 MLD STP Baniyapur UPJN | 15 | Uttar Pradesh | Kanpur
| 14 MLD STP Bandipur | 14 | West Bengal | Bandipur
| 100 MLD STP at Noida Sector 168 | 100 | Uttar Pradesh | Noida
| 40 MLD STP Mapan | 40 | Uttar Pradesh | Bulandshahar
Annexure-B Active GIS layer -April 2026 (As on 30.04.2026)
S. No. | Type | GIS Layer
1 | BASIC | Ganga
2 |  | Ganga Centre line SoI
3 |  | Ganga River Basin
4 |  | Popular River
5 |  | Ganga State
6 |  | Ganga Basin Sub District Census
7 |  | Ganga Basin Town Census
8 |  | Census Sub District 2011
9 |  | Census Town 2011
10 | WATER RESOURCES | India River Network
11 |  | Major Aquifers
12 | ECOLOGY | Riverine Wetland (UP/Bihar/Jharkhand)
13 |  | Wetland PAN India (SAC)
14 | RIVER WATER QUALITY | Ganga Polluted Stretch, 2018
15 |  | Ganga Polluted Stretch, 2022
16 |  | Ganga Polluted Stretch, 2023
17 |  | Ganga Polluted Stretch, 2025
18 |  | Manual Water Quality Stations (Locations)
19 |  | RTQMS (Locations)
20 |  | Biomonitoring (Locations) (to be add)
21 | POLLUTION ASPECTS | Sewage Gap Analysis
22 |  | STP (Other than NMCG) (Locations)
23 |  | STP NMCG (Locations)
24 |  | GPIs (Locations)
25 |  | Solid Waste Dumps (IIRS data)
26 | MISC. | Ganga Centre line 1 km points SoI
27 |  | Ganga Final Survey SoI
28 |  | Point outfall 45N SoI
29 |  | Point outfall 44N SoI

## MPR 5.4-Jan Ganga Vertical_Comm
(April 2026 - March 2027)
For the Month of April 2026 (As on 1st May 2026)
MPR Communication
| Followers | Till previous Month (March 2026 ) | Current Month (April 2026)
1 | Twitter | 122686 | 123357
| Facebook | 542672 | 564038
| Instagram | 116408 | 122497
2 | In Current Month
a) | Webposts (excluding B and C) | Number of Images | Videos (Minutes)
| Twitter | 210 | 39 | 48 Minutes
| Facebook | 210 | 44 | 60 Minutes
| Instagram | 170 | 44 | 60 Minutes
b) | Rebuttals on
| Social Media | Nil
c) | Positive Stories | 12 Stories |  | Annex A
Social Media
3 | Youtube
4 | Print Media
a) | Rebutted | Nil
b) | Positive Stories | 10 |  | Annex A
5 | Publication through PIB
a) | Press Release ( Atleast One per month )
i) | Press Release-Event Based | 18th meeting of the Empowered Task Force press release | 1st April, 2026 | https://www.pib.gov.in/PressReleasePage.aspx?PRID=2247055&reg=3&lang=1#:~:text=Strengthening%20the%20momentum%20of%20river,Paatil.
|  | Central Monitoring Committee (Part-II) Press Release | 9th April, 2026 | https://www.pib.gov.in/PressReleasePage.aspx?PRID=2250579&reg=3&lang=2
ii) | Press Release- Success Story | NMCG Milestones in FY 2025–26 Press Release | 21st April, 2026 | https://www.pib.gov.in/PressReleasePage.aspx?PRID=2254266&reg=3&lang=1
b) | Backgrounder ( One per Quarter ) | Planned for next month
c) | Articles/Op-eds in Newspapers ( One article -Half Yearly) | Planned for next month
|  | Number of Events | Participation
6 | Events Organised by NMCG |  |  | Annex B
a) | Cleanliness Drives on Yamuna | 4 | Approx. 2000
b) | World Earth Day Celanliness Drive | 1 | Approx. 200
7 | Events through Partner |  |  | Annex B
a) | DGC & SMCG
b) | NGO
c) | Institutes
| Total | 428 | Approx. 3,30,777
8 | Sponsorship | Nil
9 | Capacity Building Training /Workshop (Communication Unit ) | Nil
Annex B
| Annex A | S. No 2 C, 4 B | Coverage
S. No. | Title | Date | Twitter | Facebook | Instagram
1 | Public Review, Patna | 2026-04-27 | https://x.com/cleanganganmcg/status/2048652095470071959?s=20 | https://www.facebook.com/share/r/1E1gNLzVSS/ | https://www.instagram.com/reel/DXoBc65mqlU/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
2 | Maeva Ghat, Prayagraj | 2026-04-23 | https://x.com/cleanganganmcg/status/2047264232807276749?s=20 | https://www.facebook.com/share/p/1CkrPNGTT2/ | https://www.instagram.com/p/DXeKiKTDE0f/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
3 | Public review, Banaras | 2026-04-21 | https://x.com/cleanganganmcg/status/2046556050464166359?s=20 | https://www.facebook.com/share/r/1DrvLFkZ2C/ | https://www.instagram.com/reel/DXZHxusDUg5/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
4 | Cleanliness drive Koyla Ghat, Kanpur | 2026-04-19 | https://x.com/cleanganganmcg/status/2046146175053754467?s=20 | https://www.facebook.com/share/v/1Azukom6yJ/ | https://www.instagram.com/reel/DXWOYUhj_ZN/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
5 | Radha Kund, Mathura | 2026-04-17 | https://x.com/cleanganganmcg/status/2045892477559672975?s=20 | https://www.facebook.com/share/p/1BeV2snZDB/ | ------------------------------------
6 | Organic Farming | 2026-04-17 | https://x.com/cleanganganmcg/status/2045161236875387324?s=20 | https://www.facebook.com/share/v/1CajniU6j6/ | https://www.instagram.com/reel/DXPQGsIj4eN/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
7 | Swachhta Hero, Patna | 2026-04-16 | https://x.com/cleanganganmcg/status/2045023349253054666?s=20 | https://www.facebook.com/share/p/1FbLoytoFo/ | https://www.instagram.com/p/DXOQYWvDMGu/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
8 | Public Review Banaras | 2026-04-15 | https://x.com/cleanganganmcg/status/2044751783600513053?s=20 | https://www.facebook.com/share/r/14aikHS7jMt/ | https://www.instagram.com/reel/DXMUBbuDABC/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
9 | Maduri Devi Natural farming | 2026-04-15 | https://x.com/cleanganganmcg/status/2044391122475327568?s=20 | https://www.facebook.com/share/r/1CsQkQVWXB/ | https://www.instagram.com/reel/DXJvpaoj3zK/?utm_source=ig_web_copy_link
10 | Bandi Mata Ghat, Kanpur | 2026-04-13 | https://x.com/cleanganganmcg/status/2044366119868498288?s=20 | https://www.facebook.com/share/p/1Lio1M8u5L/ | ---------------------------------
11 | Bhadra ghat, mahavir and Naujar ghat, Patna | 2026-04-10 | https://x.com/cleanganganmcg/status/2043657342882025965?s=20 | https://www.facebook.com/share/p/1EV398kksn/ | https://www.instagram.com/p/DXElaisDzCN/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
12 | Chandrashekhar Azad Ghat, Prayagraj | 2026-04-02 | https://x.com/cleanganganmcg/status/2042506556546171163?s=20 | https://www.facebook.com/share/p/18QpiaxSTe/ | https://www.instagram.com/p/DW8aOZ-D4Tw/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
13 | Uttarakhand leads the way in Ganga Rejuvantion | 1st April, 2026
14 | Ganga Turns Cleaner in Devbhoomi Ahead of Ardh Kumbh | 2nd April , 2026
15 | Jal Shakti Ministry Reviews Progress Made by States on River Rejuvenation | 10th April , 2026
16 | Ganga Cleaning Gains Momentum with 538 MLD Capacity Added in 2025–26 | 22nd April , 2026
17 | Ganga Meets Bathing Standards as Pollution Levels Continue to Decline | 4th April , 2026
18 | PM Narendra Modi to Lay Foundation for Ninth STP to Strengthen Ganga Cleaning Efforts | 25th April , 2026
19 | ‘Arth Ganga Trail’ Project to Boost Holistic Tourism Development in Bhagalpur | 28th April , 2026
20 | 3 STPs to Become Operational Before Magh Mela Ensuring Full Sewage Treatment | 24th April , 2026
21 | 37 Projects Completed Under the Namami Gange Mission in Uttarakhand | 3rd April, 2026
22 | Central Team to Revisit Kali River Over Pollution Flowing into Ganga | 26th April , 2026
| Annex B | S. No 5,6,7
S. No. | Event Name (Activity Type) | Agency | Date | Venue | Participants
1 | Cleanliness Drives on Yamuna | NMCG with NGOs (Delhi) | Every Sunday | Geeta Colony, Sonia Vihar 2.5 Dhai Pushta, Thokar No. 17 Geeta Colony & Yameshwar Ghat Wazirabad | NGOs- Saksham Bhoomi Foundation, Yuva Parivartan Foundation, Friends of Yamuna Swachh Yamuna Abhiyaan; Schools, Colleges, Youth Groups, NGOs and Yamuna Task Force etc.
2 | World Earth Day | YSS Foundation, NMCG, Noida Authority & Raddison Blue MBD Hotel | 22.04.2026 | Yuva Shakti Ghat, Noida | School/ College students, Youth Groups, Volunteers, Representatives of Noida Development Authority and local communities.
UTTARAKHAND
3 | Swachhta Abhiyaan (Public Awareness, Cleanliness Drive, Workshops, Quiz, Sports Competitions, Signature Campaign, Swachhta Rallies, Nukkad Natak & Cultural Program | DGCs, Academic Institutes (Govt. PG/Degree Colleges) & Universities | Entire month | Govt. PG/Degree Colleges (Augustmuni, Dehradun, Gopeshwar, Joshimath, Jawalapur Haridwar, Khadi, Ramnagar, Maldevta, Paithani, Lohaghat, Thalisian, Pauri, Majra Mahadev, Haldwani, Chandrabani, Devprayag, Jahrikhal, Rishikesh, Uttarkashi & Rudraprayag | College Students, Teachers, Volunteers & Local Communities
4 | Ganga Run, Yog Workshops, Street Art Competitions, Ganga Shapath & Ganga Aarti | Govt. PG Colleges, Doon University & SMCG-UK | different dates throughout the month | Govt. Women College (Haldwani), Govt. PG College (Thalisian) and Omkaranand Saraswati Govt. College, Devprayag, Banks of Nair River Pauri Garhwal, Various Ghats of Haridwar & other Districts | College Students, Teachers & Volunteers
5 | Namami Gange Wall Painting | Govt. PG College, Augustmuni | 20.04.2026 | Govt. PG College- Augustmuni | College Students, Teachers & Volunteers
6 | World Earth Day (Swachhta Drives, Plantation, Nukkad Natak, Waste to Best Competition | Govt. PG College & Govt. Degree College | 22.04.2026 | Govt. PG College (Haldwani) & Govt. Degree College (Thalisian) | College Students, Teachers, Youth Groups, Volunteers & Local Communities
UTTAR PRADESH
7 | World Earth Day | DGC & Forest Department- Rampur, Hathras, Bareily, Muzzaffarnagar, Maharajganj | 22.04.2026 | Rampur (Sahis-e-Azam Sports Stadium), Hathras (Divisional Forest Office), Bareily (AVM Public School), Muzzaffarnagar (Holy Child Inter College), Maharajganj (GSVS Maharajganj) | Forest Dept., School/College Students & Volunteers
8 | Cultural Prog. (Bhakti & Ganga Song, Goshti), Rampur, Uttar Pradesh | DGC-Rampur, Schools/Colleges & NGOs | 30.03.2026 | Vikas Bhawan & Ram Ganga Ghat | School/College Students, Teachers, Youth Groups, Volunteers & Local Communities
9 | Namami Gange Exhibition, Competitions, Discussion on Conservation of Rivers & Aquatic Animals, Gonda, Uttar Pradesh | DGC-Gonda, Forest Depaartment & NGO (TSAFI) | 10.04.2026 | Block Sansadhan Kendra, BRC Paraspur, Gonda | Youth, Volunteers & Local Communities
10 | 1 Hour Shramdaan on Ghats | DGC-Rampur, Saharanpur, Lalitpur & Kheeri & NGO (Prakarti Rakshak in Lalitpur) and Schools/Colleges | Every Sunday | Rampur (Nahal Barraj, Ramganag Ghat), Lalitpur (Mansarovar Lake), Saharanpur (Chajja, Mirzapur, Barauli), Kheeri (Gayi Ganga Ghat) | School/College Students, Youth, Volunteers, NGO representatives & local communities
11 | Cleanliness & Awareness Drives, Swachhta Shapth, Plantation, Quiz & Competitions | DGC-Ambedkarnagar, Muzzaffarnagar, Ballia, Prayagraj, Kushinagar, Chitrakoot, Sonbhadra, Rampur & Buladshahr, Nagar Nigam and School/Colleges | different dates throughout the month | Ambedkarnagar (Gyatri Mandir Ghat), Muzzaffarnagar (Shukratal Ghat), Ballia (GIC School & Van Vihar Park), Prayagraj (Rasulabad Ghat), Chitrakoot (Sunder Ghat, Kasturba Vidhyalaya), Kushinagar (Hanuman Sarovar & Buddha Ghat), Rampur ( Green Field International School, Shri Dalchand Sharma Inter College, Vikas Bhawan & Ram Ganga Ghat), Bulandshahr (LDAV Inter College & Ganga Ghat) | School/ College Students, Youth Groups, Volunteers, NGOs & Local Communities
12 | Maha Ganga Aarti, Swachhta & Cultural Program | DGC- Barabanki | Every Tuesday & Saturday | Ram Sanehi Ghat, Kalyani River, Awsaneswar Temple, Shukhipur | Volunteers & Local Communities
BIHAR
13 | Swachhta Abhiyaan, Jal Sapath, Swachhta Rally, Pad Yatra, Nukkad Natak, Plantation & Ganga Aarti | DGCs and various schools & colleges | different dates throughout the month | DGCs- Darbhanga, Buxar, Begusarai, Katihar, Samastipur, Patna, Vaishali, Bhojpur, Madhubani, Jahanabad, Sitamarhi, Sheohar & & Bhagalpur | School & College Students, Teachers, Youth Groups, Volunteers, NGOs & Local Communities
JHARKHAND
14 | Awareness Sessions & Cleanliness Drives and anti-littering campaign and Nukkad Natak | Chas Municipal Corporation, Phurso Nagar Parishad, DGC, District Education Department, Clubs (Youth, Lions, Rotary), Police Dept., Sports Association- Bokaro, NGOs and school/colleges | 15.04.2026 to 22.04.2026 | Chas Municipal & Phurso Nagar Parishad, various schools/colleges, community & market areas and key locations | School & College Students, Teachers, Youth Groups, Club Members, Volunteers, NGOs & Local Communities
15 | Riverbank Cleanlines and Awareness Drives on Damodar & Ganga River Banks | DGCs, Schools/Colleges & NGOs (Damodar Bachhao Andolan) | 17.04.2026 | 10 Ghats of Bokaro and Various Locations | School & College Students, Teachers, Youth Groups, Volunteers, NGOs & Local Communities
16 | Morning Yoga and Aarti on Ghats | DGC- Sahibganj & Ramgarh | 07.04.2026, 14.04.2026 & 21.04.2026 | Mukteshwar Dham Ghat, Korambe & Kumhardhaga Panchayat | School Students, Teachers, Religious Groups, Sports & Youth groups, Volunteers & NGOs
17 | World Earth Day | DGC- Dhanbad, Dept. of Education, UNICEF | 22.04.2026 | Various schools | School & College Students & Teachers
WEST BENGAL
18 | Swachhta Abhiyaan | DGC Malda, SMCG WB, Schools & Colleges | 01,03 & 05.04.2026 | Bengal BN NCC Unit, Malda College Campus, English Bazar Municipal Area, Rathbari, Maheshpur River Ghat, Mahananda Bandh Road River Ghat, Madhabnagar River Ghat, Kali Mandir River Ghat, Bada Moni School Para River Ghat | School & College Students, NCC/NSS, Youth Groups, Volunteers & Local Communities
19 | Workshop on protection of Gangetic Dolphin | DGC Nadia | 11.04.2026 | Matiari High School, Kaliganj Block | School Students, Teachers and Volunteers

## MPR 5.5 RCA
(April 2025 - March 2026)
For the month of APRIL 2026
Organisation: River Cities Alliance
Sl. No. | Activity | Till Mar 2026 | 2026-04-01 | Total
1 | Web posts | 72 | 10 | 82
2 | Workshops (excluding 5b /URMP Workshops) | 17 | 2 | 19
3 | Seminar/ Webinar/Meetings | 31 | 9 | 40
4 | Exposure Visits | 2 | 0 | 2
5 | URMP Related (Non Ganga Basin)
| a) Meetings in States | 7 | 0 | 7
| b) Workshops in States | 2 | 0 | 2
6 | Publications
| a) Newsletter | 4 | 1 | 5
| b) Others | 21 | 0 | 21
7 | Concept Notes | 9 | 0 | 9
8 | Demands Received
| a) Cities | 14 | 1 | 15
| b) Academia | 7 | 0 | 7
Annexures
List (Type 2,3,4,5) March
Sl. No. | Event Topic | Type | Venue | Date/Days /Duration | Number of Participants
1 | Training Programme on "Eco-friendly riverfront development" | 2 | Haridwar | 08.04.2026 - 09.04.2026 | 30
2 | Webinar on 'Participatory Groundwater Mapping: Aquifer Systems and Surface - Sub Surface Water Interactions' | 3 | Online | 10.04.2026 | 105
3 | Expert Lecture on Urban River Systems and their Management | 3 | Online | 10.04.2026 | 50
4 | Expert Lecture on Urban Ecology and Urban River Management | 3 | Sri Venkateswara College, New Delhi | 07.04.2026 | 80
5 | Meeting with SPA Bhopal (AMRUT Centre ) for ongoing engagement and potential synergies | 3 | NIUA | 13.04.2026 | 20
6 | Webinar on 'Interlinkages Between Municipal Solid Waste Management (MSWM) and Aquatic Ecosystems' | 3 | Online | 17.04.2026 | 35
7 | Webinar on 'Tackling Invasive Aquatic Species in Cities : From Silent Spread to Strategic Control' | 3 | Online | 24.04.2026 | 35
8 | Integrated Academic Studio Workshop on ‘Visioning for Water Resilient Development’ in the case of Guwahati | 2 | SPA Bhopal | 24.04.2026 | 35
9 | Expert Lecture on Urban Water Challenges for SAU students | 3 | NIUA | 24.04.2026 | 40
10 | Jhansi - Meeting with Municipal Commissioner | 3 | Jhansi | 28.04.2026 | 5
11 | Pilibhit - Meeting with DM and Eo | 3 | Pilibhit | 29.04.2026 | 16
List (Type 1,6) March
Sl. No. | Subject | Type | Date
1 | Quiz series 8: RCA: Rivers, Cities, and Answers | 1 | 01.04.2026
2 | Inspirational Monday Series on "AI-powered cleanup initiative on the Pasig River in Manila" | 1 | 06.04.2026
3 | Quiz series 9: RCA: Rivers, Cities, and Answers | 1 | 08.04.2026
4 | Inspirational Monday Series on "Waste collection drive inititative along Mula - Mutha river in Pune by Jeevit Nadi NGO " | 1 | 13.04.2026
5 | Quiz series 10: RCA: Rivers, Cities, and Answers | 1 | 15.04.2026
6 | Inspirational Monday Series on "Restoration of Lal Bagh Lake within Lal Bagh Botanical Garden, Bangalore " | 1 | 20.04.2026
7 | Quiz series 11: RCA: Rivers, Cities, and Answers | 1 | 22.04.2026
8 | Inspirational Monday Series on "Restoration of Ariyalur Lake, Chennai" | 1 | 27.04.2026
9 | Quiz series 12: Rivers, Cities, and Answers | 1 | 29.04.2026
10 | RCA Newsletter (Q1 - 2026) | 6a | 30.04.2026
List (Type 7) March
Sl. No. | Subject | Type | Date
1 |  | 7
Demands for RCA (Type 8) March
Sl. No. | Subject | Type | Date
1 | Request from Imphal (Manipur) for onboarding into RCA and conducting RSMP training programme | 8 | 15.04.2026

## COE-IT BHU
(April 2026 - March 2027)
For the month of April 2026
Smart Laboratory on Clean Rivers (MPR 5.6a)
Sl. No. | Activity | Till Mar-26 | 2026-04-01 | Total
1 | Workshops / Conference - Organised | 5 | 0 | 5
2 | Capacity Building Workshops - Organised | 4 | 1 | 5
3 | Publications | 0 | 0 | 0
4 | STP Performance Evaluation (Number of STPs) | 7 | 0 | 7
5 | DSS Project (Physical progress %) | 60% | 2% | 62%
5a | No. Draft Modules Finalized | 10 | 0 | 10
6 | Characterisation of Emerging Pollutants (Physical progress %) | 63% | 0% | 63%
6a | No. of Draft SOPs Finalized | 5 | 0 | 5
7 | Hydrogeological Model of Varuna Basin for MAR sites (Physical progress %) | 61% | 0% | 61%
7a | No. of Sites implemented | 0 | 0 | 0
Annexure
List (Type 1, 2)
Sl. No. | Event Topic | Type | Venue | Date/Days/ Duration | Number of Participants
1 | Groundwater direction, modelling, TEM data interpretation, recharge structures and DSS modules with CGWB. | Type 2 | Seminar Hall, IIT (BHU) | 20.04.2026 to 22.04.2026 / 3 Days | 10
List (Type 3)
Sl. No. | Name of Publication | Date | Submitted
List (Type 4)
Sl. No. | Name of STP | Date visited | Report submitted
List (Type 5, 6, 7,)
Sl. No. | Project Details | Type | Activities
1 | DSS Project | Type 5 | The STP modules were further refined by incorporating centralized and decentralized wastewater treatment systems, with a focus on appropriate technology selection. In addition, a detailed discussion was held with experts from the Central Ground Water Board (CGWB) to enhance the groundwater modules. The river water quality and water budget draft modules have also been successfully integrated into the DSS. Furthermore, continuous improvements are being made to the user interface to ensure better usability and ease of navigation.
2 | Characterisation of Emerging Pollutants | Type 6 | An LC-HRMS method development for a new degradant of Ethofumesate is completed. Data acquisition for the collected Varuna Basin samples is ongoing.
3 | Hydrogeological Model of Varuna Basin for MAR sites | Type 7 | FloaTEM Data acquisition and TEM data analysis for identification of potential zones for Managed Aquifer Recharge (MAR) to enhance river–aquifer exchange in the Varuna River. Potential sites for the MAR have been identified.
List (Type 5a, 6a, 7a)
Sl. No. | Draft Finalized | Type | Comments
1
2
3
4
5