## MPR 1.3_Project under progress
(April 2025 - March 2026)
For the month (As on 1 Jan 26)
MPR Project Wing/Projects under progress
A. Under Progress - Sewage inflow to STP started- under trial operations; COD to be Declared
Sl. No. | Project | HAM/DBOT | Total Sanctioned Cost(Cr) | STP Capacity - New (MLD) | Date of start of trial operation | Reasons for delay in COD declaration
1 | I&D and STP at Unnao | HAM | 102.2 | 15 | 2023-11-07 | Trunk sewer along the original alignment has settled. Repair of the same is in progress.
2 | Pollution Abatement works for River Ganga at Hooghly Chinsurah | DBOT | 161.99 | 26.5 | Work yet to be completed | The STP is operational with partial flow. The remaining work of the I&D sewer line could not be completed earlier as open-cut excavation was not feasible. Now, under the approved variation, the balance work will be completed through trenchless pipeline laying.
3 | I&D and STP at Digha | HAM | 824 | 100 | 2025-03-01 | CoD will be declared after the completion of the trial run and successful achievement of the KPIs.
4 | I&D and STP at Khankharbagh | HAM | 578.89 | 50 | 2025-03-01 | CoD will be declared after the completion of the trial run and successful achievement of the KPIs.
5 | I&D and STP at Moradabad | HAM | 149.23 | 25 | 2025-07-01 | Power connection provided on 10th December 2025. STP under Trial and COD expected to be declared by 15th March'2026.
6 | I&D and STP at Jangipur | DBOT | 68.47 | 13 | 2025-06-01 | Under trial run and successful achievement of the KPIs.
7 | I & D and STP at Kota | DBOT | 258.48 | 36 | Work yet to be completed | The STP is operational from Dec-2022
8 | I&D and STP at Muzaffarnagar | HAM | 234.03 | 54.5 |  | COD declared for 22 MLD STP; Partial COD declared for 32.5 MLD STP due to pending work on IPS 2A. The IPS 2A work has been completed. Full COD declaration documentation under review at UPJN.
9 | I&D and STP at Lucknow | DBOT | 240.93 | 42.5 | 2024-09-01 | 3.5 MLD under progress (39 MLD operational)
10 | I&D and STP at Howrah, Bally and Kamrahati & Baranagar | HAM | 595.72 | 187 |  | Partially COD declared
B. Under Progress - Effective Date to be declared
Sl. No. | Project | HAM/DBOT | Total Sanctioned Cost(Cr) | STP Capacity - New (MLD) | Date of award of LOA | Reasons for delay in Effective date declaration
1 | Interception & Diversion and STP works at Lucknow, Phase-II Part-II | HAM | 351.03 | 100 | 02-06-2025 (Concession Agreement executed on 26/08/2025) | Effective Date to be declared by 3rd week of Jan'26. Pending Conditions precedent include (i) Financial closure; (ii) BEP Approval; (iii) Construction Plan approval; (iv) Phase I design drawing Submission; (v) Escrow Agreement. Financial closure documents received and under examination. Site survey, soil investigations, site clearing completed.
2 | I & D and STP at Dhanbad | HAM | 808.33 | 192 | 2025-10-15 | Due to land permission. Land for two STPs is clear for which spearate effective date may be given.

## MPR 1.4_KSDC
(April 2025 - March 2026)
For the month of December
Organisation: Knowledge-cum-Skill Development Centre (KSDC)
Sl. No. | Activity | Till November 25 | 2025-12-01 | Total
1 | Web posts | 0 | 0 | 0
2 | Training/ Workshops | 1 | 0 | 1
3 | Seminar/ Webinar | 0 | 0 | 0
4 | Exposure Visits | 0 | 0 | 0
5 | URMP Related | 0 | 0 | 0
6 | Technical Support | 0 | 0 | 0
7 | Research/ Academic | 0 | 0 | 0
8 | Publications | 0 | 0 | 0
Annexure
List (Type 2,3,4,5) December
Sl. No. | Event Topic | Type | Venue | Number of Participants | Date/Days /Duration
11.09.2025 to 13 .09.2025
List (Type 1,6) December
Sl. No. | Subject |  | Date
List (Type 7) December
Sl. No. | Subject |  | Date
1
2
3

## MPR 3.1 CPCB
(April 2025 - March 2026)
For the month of December, 2025
Technical Division / CPCB related
Sl. No. | Activity | Till Nov-25 | 2025-12-01
1 | STP Inspection Reports Received **
| Uttrakhand | Apr'25- Jul'2025 | -
| Uttar Pradesh | Apr'25- Jul'2025 | -
| Bihar | Apr'25- Jul'2025 | -
| Jharkhand | Apr'25- Jul'2025 | -
| West Bengal | Apr'25- Jul'2025 | -
2 | River water Quality Data Received *
| Uttrakhand | Apr'25- Jun'2025 | Jul'25- Sep'2025
| Uttar Pradesh | Apr'25- Jun'2025 | Jul'25- Sep'2025
| Bihar | Apr'25- Jun'2025 | Jul'25- Sep'2025
| Jharkhand | Apr'25- Jun'2025 | Jul'25- Sep'2025
| West Bengal | Apr'25- Jun'2025 | Jul'25- Sep'2025
3 | GPI Inspection Report received *
| Target (8th Round - till 15th Jan2026) | Covered | Annexure A
| 3726 (Ganga: 1299; Yamuna2427) | 3542 | 3681
4 | River water Quality Data upload on GKC *
| Uttrakhand | Jan'25- Jun'2025 | -
| Uttar Pradesh | Jan'25- Jun'2025 | -
| Bihar | Jan'25- Jun'2025 | -
| Jharkhand | Jan'25- Jun'2025 | -
| West Bengal | Jan'25- Jun'2025 | -
5 | Number of Publications/Reports | 24 | 4
* Pls indicate period
** Pls indicate month
Annexure for S.No 5
S.No. | Name of Document | Date
1 | CPCB Report of 52 Yamuna Drains monitoring (May-Oct'2025) | 2025-12-14
2 | MoM of Joint meeting of Supervisiory Committee and Executive Committee (in compliance of OA 200/2014) dtd. 17.11.2025-under Chairmanship of PS Forest & Envt UK, regarding Septage Management; Sewage Collection and disposal; Joint monitoring to avoid variation in STPs test results; Solidwaste Management and Floodplain zoning Compliances | 2025-12-04
3 | Manual Water Quality Monitoring Stations Data under SER - WB (Namami Gange) Funded Projects (Jul-Sept,2025) received by email | 2025-12-12
4 | SOP for Site Selection Criteria for sampling Benthic Macroinvertebrates | 2025-12-09
Annexure A for S.No 3
| Total GPIs | 3726
| Inspected | 3681
| Complied | 1906
| Non-Complied | 640
| Temporary Closed | 316
| Permanently Closed | 60

## MPR 3.2_Regulatory Cell
(April 2025 - March 2026)
For the month of December (As on 30th Dec 25)
Technical Division / Regulatory Cell
A | Pending Applications
1 | Pending Application at the end of Nov 25 | 12
2 | Application returned back in Dec 25 | 3
3 | Applications decided in Dec 25 | 2
4 | New Applications received in Dec 25 | 3
5 | Pending Application at the end of Dec 25 | 10
6 | Out of S.No. 5, applications pending more than 3 months ( Received before 1st Sep) | 6
5= 1-2-3+4
B | Regulatory Cell meeting
Date | Meeting Number | Cases Considered | Cases Deferred | Cases Recommended
2025-11-29 | 13 | 5 | 4 | 1
Annexure for A/S.No 6
S.No. | Subject | Applicant | Date | Status
1 | Construction of Water Sport Ramp Boat Shed Retaining Wall and Jetty on the Banks of Saryu River in Ayodhya | Project Manager U.P.S.T.D.C. | 2025-04-24 | Forwarded to DGC & SGC letter dated 02/12/2025
2 | Construction of Proposed State of the art Bathing Ghat on the Banks of the Ganges from Panchal Ghat to old Ghatiya in Farrukhabad | Project Manager U.P.S.T.D.C. | 2025-05-02 | Forwarded to DGC & SGC letter dated 02/12/2025
3 | Withdrawal of additional 110 Cusec water from River Gomti for capacity enhancement of Tandwa (proposed 50 Cusec), Bhainsa (proposed 30 Cusec), and Niyardeeh (proposed 30 Cusec) Pump Canals near Kerakat Rajwaha, Jaunpur, Uttar Pradesh. | Chief Engineer (Water Resource), Irrigation & Water Resource Department, Lucknow, Uttar Pradesh, | 05/05/2025 | Forwarded to SGC letter dated 02/12/2025
4 | Renewal for 7 years Ram anubhav kendra | Ayodhaya Development Authority | 2025-07-02 | considered in 13th Cell meeting, Cell requested to proponent submit a new proposals with observations
5 | Construction of a Major Bridge over the River Ghaghara | General Manager (Tech)/Project Director, NHAI, PIU-Lucknow | 2025-07-31 | considered in 13th Cell meeting, Cell decided to return the file with observations
6 | Construction of New Rail cum Road bridge over River Ganga in Varanasi | Northern Railway | 2025-09-15 | considered in 13th Cell meeting held on 29/12/2025, Cell recommended with observations

## MPR 4.1_E-file status
eOffice closed files summary
(With initial total number of eFiles =7,375 on 25th Oct 2025)
Period | No. of eFiles closed
From 1st April 2020 –till 25th Oct 2025 | 104
26th Oct 2025 – till 31st Oct 2025 | 48
1st November 2025 to 30th November 2025 | 299
1st December 2025 to 31st December 2025 | 1
Total | 452
Wing/Section/ Unit wise summary from 26th Oct 2025 till 30th November 2025
i. SMD Section: 271
ii. Finance Wing: 42
iii. Communication Wing: 21
iv. Admin Wing: 13
Total: 347
Wing/Section/ Unit wise summary from 1st December 2025 to 31st December 2025
i. SMD Section: 1
Total: 1

## MPR 5.2_GKC
Monthly Progress Report- Gyanganga.ai (December 2025)
Generated on 1st January 2026
Sl. No. | Title | Till 30th November 2025 | 2025-12-01 | Total (as on 1st January 2026)
1 | Total Number Document on GKP | 1294 | 21 | 1315
2 | Other Literature on River Ganga | 2780 | 7220 | 10000
Categories-wise details of documents uploaded between 1st to 31st December 2025 2025
Categories | Sub-categories | No. of documents
Publications |  | 0
Journals |  | 0
| Student Thesis Competition (STC) | 0
Articles |  | 0
Books |  | 0
Studies/Reports |  | 6
Guidelines |  | 0
Misellaneous |  | 0
Ganga River (Main Stem)Water Quality Data |  | 0
Data Set | River Atlas | 0
| Ganga River (Main Stem) Water Quality Data (CPCB) | 0
Coffes Table Books |  | 0
River Series |  | 15
Total |  | 21
Details of documents uploaded between 1st to 31st December 2025 :-
S.No | Category | Subject
1 | Reports | Conservation, Reintroduction and Rehabilitation of Threatened Turtles Along Ganga Basin in Uttar Pradesh,India
2 | Reports | Report on Water Quality Hot spots in Rivers of India January-December 2024
3 | Reports | Report on Water Quality Hot spots in Rivers of India January-December 2023
4 | Reports | Status of trace & toxic metals in rivers of India January-December 2024
5 | Reports | Status of trace & toxic metals in rivers of India January-December 2023
6 | River Series | Nandakini river
7 | River Series | Punpun river
8 | River Series | Tons river
9 | River Series | Sind river
10 | River Series | Sai river
11 | River Series | Morhar river
12 | River Series | Mandakini river
13 | River Series | Kosi river
14 | River Series | Ken river
15 | River Series | Karmanasa river
16 | River Series | Dhauliganga river
17 | River Series | Bhagirathi river
18 | River Series | Betwa river
19 | River Series | Barakar river
20 | River Series | Alaknanda river
21 | Reports | Scientific Exploration of Floral Diversity Near the Ganga Riverbanks for Ethnobotanical Purposes along with their Conservation and Economic Development of the Region via Skill Development Programs

## MPR 5.3-Prayag status
(April 2025 - March 2026)
For the month of December (As on 1st Jan 26)
MPR Prayag/GeoPortal etc
A | OCEMS Status
1 | Installation and Data Staus *
a | No. of STPs with OCEMS Installed | 270
b | No. of STPs with Flow Data received | 175
c | No. of STPs with Influent Characteristic Data received # | 115
d | No. of STPs with Effluent Characteristic Data received | 162
2 | Data Reliability Status **
a | No. of STPs with Satisfactory Data received | 174
b | No. of STPs with Poor Data Quality (Annex A1) ** | 3
c | No. of STPs with No Data Received (Annex A2) | 95
B | OCEMS based Results communicated to States till Month | Communicated till Dec-2025
C | Eflows report updated till period | Updated till first quarter 2025
D | GDPMS
| No. of Meetings held in November 2025 | 66
| No. of Meetings held in December 2025 | 24
E | Prayag GEO Portal
| No. of Active GIS Layers (Annex B) | 30
| No. of Use Cases | 7

## MPR 5.4-Jan Ganga Vertical
(April 2025 - March 2026)
For the Month of November (As on 1st December. 25)
MPR Communication
| Followers | Till Previous Month (October) | Current Month (November)
1 | Twitter | 125761 | 123K
| Facebook | 456K | 476K
| Instagram | 94.3K | 92.7K
2 | In Current Month
a) | Webposts (excluding B and C) | Number of Images | Videos (Minutes)
| Twitter | 234 post | 30 videos (Total minutes approx 70 min)
| Facebook | 234 post | 68 videos (Total Minutes approx 96 min)
| Instagram | 171 | 79 Videos (Total minutes approx 60 min)
b) | Rebuttals on | Nil
| Social Media | Nil
c) | Positive Stories | 12 Stories |  | Annex A
Social Media
3 | Youtube
4 | Print Media
a) | Rebutted | Nil
b) | Positive Stories | 10 |  | Annex A
|  | Number of Events | Participation
5 | Events Organised by NMCG |  |  | Annex B
| Ganga Utsav | 1 (Ayodhya) | Approx. 1000
6 | Events through Partner |  |  | Annex B
a) | DGC | 96 (Ganga Utsav) | Approx. 1,91,962
b) | NGO | 4 (Cleanliness Drives on Yamuna in Delhi ) | Approx. 1250
c) | Institutes | 43 (Ganga Utsav in Universities/Colleges- Uttarakhand) | Approx. 1.50 Lakh
7 | Sponsorship
| Third Party Events | 1 (Dev Deepawali- Yamuna Maha Aarti & Deeputasv- YSS Foundation) | Approx. 300-400 | Annex B
| Annex A | S. No 2 C, 4 B
S. No. | Title | Date | Coverage
1 | Murad Nagar Ganga Ghat Public Revie | 30th Nov, 2025
2 | Harnandi River Public review | 30th Nov, 2025
3 | Kashi corridor Befor- After | 28th Nov, 2025
4 | Banaras Ghat Befor- After | 27th Nov,2025
5 | Daulatgunj STP public review | 27th Nov,2025
6 | Jagjeet pur 68 MLD STP Before- After | 26th No, 2025
7 | Aadhikeshav Ghat Public review | 25th Nov, 2025
8 | Rajghat Public review | 25th Nov, 2025
9 | Kashi Public Review | 23rd Nov, 2025
10 | Kashi Public Review | 22nd Nov, 2025
11 | Kashi Public Review | 21st Nov, 2025
12 | Lucknow STP Progress | 19th Nov, 2025
13 | Agra Dayalbagh STP | 24th Nov, 2025
14 | Kanpur to Kaushambi paleochannels story | 18th Nov, 2025
15 | Prayagraj STP | 16th Nov, 2025
16 | Ganga Utsav 2026 | 6th Nov, 2025
17 | 67th EC inhouse draft coverage | 18th Nov, 2025
18 | Bhagalpur STP | 06th Nov, 2025
19 | Moradabad STP | 29th Nov, 2025
20 | Bhadohi STP | 12th Nov, 2025
21 | Ghaziabad STP | 16th Nov, 2025
22 | Rashtriya Nadi Sangam | 14th Nov-2025
| Annex B | S. No 5,6,7
S. No. | Event Name (Activity Type) | Agency | Date | Venue | Participants
1 | Ganga Utsav | NMCG | 5th November 2025 | Dr. Ram Manohar Lohiya Avadh University, Ayodhya | District Ganga Committee- Ayodhya, Students & Scholars of Dr. Ram Manohar Lohiya Avadh University, Ganga Prahari, volunteers and local communities
2 | Cleanliness Drives on Yamuna | NMCG with NGOs (Delhi) | Every Sunday | Signature Bridge, Sur Ghat-Wazirabad, Thokar No.17-Geeta Colony, 2.5 Pushta Ghat | Schools, Colleges,Yamuna Task Force, Youth Groups, NGOs etc.
3 | Ganga Utsav- DGCs | District Ganga Committees & SMCG | 4th November 2025 |  | District Administration, associated partners, academic institutes, schools, universities, youth groups, NGOs and local communities etc.
|  | Uttarakhand (13 Districts) |  | 4 States
Uttar Pradesh (70 Districts)
Bihar (NIL)- Elections
Jharkhand (4 Districts & 1 City)
West Bengal (8 Districts)
4 | Ganga Utsav- Universities | SMCG & Universities/ Colleges- Uttarakhand | 4th November 2025 | 43 Colleges | College Students & Voulnteers
5 | Yamuna Maha Aarti & Deeputsav | YSS Foundation, Delhi | 5th November 2025 | Yuva Shakti Ghat, Yamuna Bank, Sector 94, Noida | Students, Social Workers, Volunteers, Environmentalists, NGOs and local communities

## MPR 5.5 RCA
(April 2025 - March 2026)
For the month of DECEMBER
Organisation: River Cities Alliance
Sl. No. | Activity | Till November 25 | 2025-12-25 | Total
1 | Web posts | 47 | 5 | 52
2 | Workshops (excluding 5b /URMP Workshops) | 10 | 3 | 13
3 | Seminar/ Webinar/Meetings | 17 | 5 | 22
4 | Exposure Visits | 2 | 0 | 2
5 | URMP Related (Non Ganga Basin)
| a) Meetings in States | 6 | 0 | 6
| b) Workshops in States | 2 | 0 | 2
6 | Publications
| a) Newsletter | 3 | 0 | 3
| b) Others | 10 | 2 | 12
7 | Concept Notes | 7 | 0 | 7
Annexures
List (Type 2,3,4,5) December
Sl. No. | Event Topic | Type | Venue | Date/Days /Duration | Number of Participants
1 | Arcadis-UN Habitat Shelter Academy (training programme) on 'Urban Flood Resilience and River Management' | 2 | Delhi | 08.12.2025 to 11.12.2025 | 27
2 | STC 6 Proposal review workshop | 2 | NIUA | 10.12.2025 | 30
3 | MoU signing workshop with universities | 2 | NIUA | 11.12.2025 | 15
4 | Webinar on 'Green Bonds Simplified: A Practical Roadmap for Cities' | 3 | Online | 05.12.2025 | 35
5 | Expert talk on "Urban river management" in the Tata-IWMI Partners meeting | 3 | Anand | 05.12.2025 | 40
6 | Expert lecture on "Contemporary thinking for river management in India" in Youth for Water summit | 3 | Bhubanesar | 17.12.2025 | 50
7 | Panel discussion on "Innovations in infrastructure desiging for Viksit Bharat 2047" in IIT Gandhinagar Innovation bootcamp | 3 | Gandhinagar | 17.12.2025 | 300
8 | Expert lecture on "River Cities Alliance" in training programme on Urban Water Management by IIT Madras and Embassy of Israel | 3 | Chandigarh | 17.12.2025 | 55
List (Type 1,6) December
Sl. No. | Subject | Type | Date
1 | Inspirational Monday Series on "Water hyacinth management: A case of Rokhak women handicraft in Cambodia" | 1 | 01.12.2025
2 | Inspirational Monday Series on "Use of underground aquifers for groundwater storage system management': A case of Sacramento regional water bank, USA" | 1 | 08.12.2025
3 | Inspirational Monday Series on "Integrating constructed etlands into urban areas to manage stormwater: A case of Trin Warren Tam-boore wetland in Melbourne, Australia" | 1 | 15.12.2025
4 | Inspirational Monday Series on "CSR initiatives for water stewardship and environmental sustainability for the Wazirabad drain in Gurugram" | 1 | 22.12.2025
5 | Inspirational Monday Series on “The role of citizen science in monitoring water towers in Kenya.” | 1 | 29.12.2025
6 | Guidelines for "Considerations for developing an eco-friendly riverfront- Version 2" | 6b | 16.12.2025
7 | City Spotlight No.1: 'Students learn the ABCs of sewage treatment in RCA cities of West Bengal" | 6b | 10.12.2025
List (Type 7) December
Sl. No. | Subject | Type | Date
1
2
3

## COE-IT BHU
(April 2025 - March 2026)
For the month of December
Smart Laboratory on Clean Rivers
Sl. No. | Activity | Till November-25 | 2025-12-01 | Total
1 | Web posts | 64 | 16 | 80
2 | Workshops / Conference | 6 | 0 | 6
3 | Seminar/ Webinar | 5 | 2 | 7
4 | Exposure Visits | 13 | 3 | 16
5 | URMP Related (Non Ganga Basin) | NA | NA | NA
| a) Meetings in States | NA | NA | NA
| b) Workshops in States | NA | NA | NA
6 | Publications | 0 | 0 | 0
| a) Newsletter | 0 | 0 | 0
| b) Others | 4 | 0 | 4
7 | Consultative Meetings / Interactive Sessions | 10 | 5 | 15
Annexure
List (Type 2,3,5,4)
Sl. No. | Event Topic | Type | Venue | Date/Days/Duration | Number of Participants
1 | SLCR, IIT (BHU) Participated in Denmark, EU & India Joint Seminar on Collaborative Efforts for Water Resilience | Type 3 | Novotel, New Delhi City Centre | 04.12.25 | 1
2 | SLCR Team Visited the STP Plant | Type 4 | Patna,Bihar | 08.12.25 | 2
3 | SLCR team participated in the IWT-RRR National Symposium on Innovations in Water Treatment, Reuse and Resource Recovery organized by deptt. Of Civil Engg. IIT (BHU) | Type 3 | Deptt. Of Civil Engg. IIT (BHU) | 11.12.2025 to 12.12.2025 | 2
4 | SLCR Team Visited the STP Plant | Type 4 | Chappra & Patna, Bihar | 22.12.25 | 2
5 | SLCR Team Visited the STP Plant | Type 4 | Mirzapur, UP | 29.12.25 | 2
List (Type 6)
Sl. No. | Subject | Type | Date
1
2
List (Type 7)
Sl. No. | Consultative Meetings / Interactive Sessions | Type | Venue | Date
1 | SLCR team visited the CDO, Bhadohi, for approval for field demonstrations in respect of the Holistic plan of Varuna River-reg | Type 7 | Vikas Bhawan, Bhadohi | 01.12.2025
2 | SLCR team visited the CDO, Jaunpur, for approval for field demonstrations in respect of the Holistic plan of Varuna River-reg | Type 7 | Vikas Bhawan, Jaunpur | 01.12.2025
3 | SLCR team visited the Irrigation department, Prayagraj, for approval for field demonstrations in respect of the Holistic plan of Varuna River-reg | Type 7 | Prayagraj | 02.12.2025
4 | A four-day MIKE training programme was conducted by experts from Ramboll India. The programme focused on the fundamentals of surface water hydrological modelling through well-structured lectures and hands-on demonstrations. | Type 7 | Geoinformatics Lab, Deptt. Of Civil Engineering, IIT (BHU) | 16.12.25 to 19.12.25
5 | SLCR team visited the CDO, Varanasi, for approval for field demonstrations in respect of the Holistic plan of Varuna River-reg | Type 7 | Vikas Bhawan, Varanasi | 24.12.2025