## MPR 1.3_Project_COD effective
MPR 1.3
(April 2026 - March 2027)
For the month (As on 31st August 2026)
MPR Project Wing/Projects under progress
A. Under Progress - Sewage inflow to STP started- under trial operations; COD to be Declared
Sl. No. | Project | HAM/DBOT | Total Sanctioned Cost(Cr) | STP Capacity - New (MLD) | Date of start of trial operation | Reasons for delay in COD declaration
1 | I&D and STP at Unnao | HAM | 102.2 | 15 | 2023-11-07 | Trunk sewer along the original alignment has settled. Repair of the same is in progress.
2 | Pollution Abatement works for River Ganga at Hooghly Chinsurah | DBOT | 161.99 | 26.5 | 2024-03-01 | The STP is operational with partial flow. The remaining work of the I&D sewer line is in progress through trenchless pipeline laying. Additional scope variation approved in 71st EC meeting.
3 | I&D and STP at Digha | HAM | 824 | 100 | 2025-03-01 | Partial COD declared as 01.02.2026
4 | I&D and STP at Kankarbagh | HAM | 578.89 | 50 | 2025-03-01 | Partial COD declared as 01.01.2026
5 | I&D and STP at Jangipur | DBOT | 68.47 | 13 | 2025-06-01 | COD declared for 8 MLD (Jangipur) COD awaited for 5 MLD Raghunathgunj
6 | I & D and STP at Kota | DBOT | 258.48 | 36 | 2023-06-01 | The STP is operational from Dec-2022 The Project De-scoping is pending
7 | I&D and STP at Lucknow | DBOT | 240.93 | 42.5 | 2024-09-01 | 3.5 MLD under progress (39 MLD operational)
8 | I&D and STP at Howrah, Bally and Kamrahati & Baranagar | HAM | 595.72 | 187 | 2023-12-31 | Partial COD declared as 01.10.2024
9 | I&D with STP works at Sapera Basti, Dehradun | DBOT | 78.99 | 15 | 2025-12-01 | Under trial operations
10 | I & D and STP works at Muni ki reti, Neelkanth, Swarg aashram | DBOT | 94.06 | 12.8 | 01-08-2026 (Muni-Ki-Reti and Swargashram) | Under trial operations (Muni-Ki-Reti and Swargashram) Under Construction (Neelkanth 1.5 MLD)
11 | Interception and diversion of balance discharge of 13 drains and augmentation of Salori STP | DBOT | 331.75 | 43 | 2026-03-01 | Under trial operations
12 | I&D and STP Works at Vrindavan | DBOT | 77.7 | 13 | 2026-03-01 | Under trial operations
13 | Interception and Diversion with STP) at Chakdah Municipal Town | DBOT | 121.66 | 15 | 2026-02-14 | COD awaited
14 | Sewerage Scheme (I&D and STP Works for balance drains) at Gokul Barrage, Mathura | HAM | 292.56 | 60 | 2026-09-01 | Under trial run
B. Under Progress - Effective Date to be declared
Sl. No. | Project | HAM/DBOT | Total Sanctioned Cost(Cr) | STP Capacity - New (MLD) | Date of award of LOA | Reasons for delay in Effective date declaration
1 | I & D and STP at Dhanbad | HAM | 808.33 | 192 | Effective date for STP-1 ,2&3 has been declared as 02.03.2026. | Due to pending land NOC the effective date for remaining STPs (STP-4 &5) is yet to be declared.
2 | Interception & Diversion and 60 MLD STP works for Durga Drain at Varanasi | HAM | 274.31 | 60 | 2026-07-01 | The SPV formation has been completed. The Concession Agreement has been executed on 20.08.2026, and the Effective Date is targeted to be declared by 30.09.2026.
3 | Interception & Diversion and STP works at Pt. DDU Chandauli (HAM) | HAM | 262.78 | 45 | 2026-07-01 | The SPV formation has been completed. The Concession Agreement has been executed on 20.08.2026, and the Effective Date is targeted to be declared by 30.09.2026.

## MPR 1.5 Project Engg O&M
MPR 1.5
Details of Project Engineer Engagement in various STP projects, NMCG
S No. | Name of the project | STP Capacity | Name of the Bidder | Last MPR approved by NMCG | Last MPR submitted by PE | Last Payment Made by NMCG | Last Invoice submitted by PE | Project Staus | Tentative Payment (Rs. In Cr)
1 | PE Haridwar STP Project | 68 MLD | M/s. Shah Technical Consultants Pvt. Ltd. | PE contract Completed |  |  |  | O&M
2 | PE Prayagraj STP project | 14 MLD 42 MLD 16 MLD | M/s. AECOM India Pvt. Ltd. In JV with URS Scott Wilson India Consortium | 2025-03-01 | 2025-03-01 | 2025-03-01 | Mar-25 | O&M | 0.4
3 | PE Mathura STP Project | 30 MLD | M/s. Mahindra Consulting Engineers Ltd. (MACE) | PE contract Completed |  |  |  | O&M
4 | PE Budhana Muzaffarnagar STP Project | 10 MLD 22 MLD | M/s. Egis India Consulting Engineers Pvt. Ltd. | Jun-25 | Jun-25 | 2023-03-01 | 2025-06-01 | O&M
5 | PE Moradabad STP Project | 25 MLD |  | 2026-05-01 | 2026-06-01 | 2026-02-01 | 2026-05-01 | O&M
6 | PE Bareilly | 42 MLD 20 MLD 1 MLD | M/s. HaskoningDHV Consulting Pvt. Ltd. In JV with HaskoningDHV Nederland B.V | PE contract Completed |  |  |  | O&M
7 | PE Ayodhya | 32 MLD |  | 2026-02-01 | 2026-06-01 | 2026-02-01 | 2026-05-01 | O&M
8 | PE Farrukhabad-Fatehgarh | 30 MLD 20 MLD 2 MLD |  | PE contract Completed |  |  |  | O&M
9 | PE Kanpur STP project | 30 MLD 15 MLD 5 MLD | M/s. Shah Technical Consultants Pvt. Ltd. | 2026-04-01 | 2026-07-01 | Mar-25 | Mar-25 | O&M
10 | PE Varanasi STP Project | 50 MLD | M/s. Mahindra Consulting Engineers Ltd. (MACE) | PE contract Completed |  |  |  | O&M
11 | PE Mirzapur Ghazipur | 8.5 MLD 8.5 MLD 21 MLD | M/s. NJS Engineers India Pvt. Ltd. | 2026-06-01 | 2026-07-01 | 2025-12-01 | Apr-26 | O&M
12 | PE Digha & Kankarbagh STP Project | 150 MLD 50 MLD | M/s. Mahindra Consulting Engineers Ltd. (MACE) | 2025-12-01 | 2026-07-01 | 2025-06-01 | 2025-06-01 | Under Progress/ O&M
13 | PE Bhagalpur STP Project | 40 MLD 5 MLD | M/s. Egis India Consulting Engineers Pvt. Ltd. | 2026-03-01 | 2026-07-01 | 2026-02-01 | 2026-02-01 | Under Progress/ O&M
14 | PE North Barrackpore STP project | 30 MLD 8 MLD | M/s. MaRS Planning & Engineering Services Pvt. Ltd. | 2026-07-01 | 2026-07-01 | 2026-03-15 | 2026-07-01 | O&M
15 | PE Howrah, Bally & Baranagar | 65 MLD 40 MLD 60 MLD | M/s. HaskoningDHV Consulting Pvt. Ltd. In JV with HaskoningDHV Nederland B.V | 2025-12-01 | 2025-12-01 | Dec-25 | Dec-25 | O&M
16 | PE Maheshtala STP | 35 MLD | M/s. WAPCOS Limted | 2026-04-01 | 2026-07-01 | Aug-25 | Aug-25 | O&M

## MPR 1.5 Proj engg under progres
MPR 1.5
Details of Project Engineer Engagement in various STP projects, NMCG
Sl No. | Name of the project | STP Capacity | Name of the Bidder | Last MPR approved by NMCG | Last MPR submitted by PE | Last Payment Made by NMCG | Last Invoice submitted by PE | Project Staus | Tentative Payment (Rs. In Cr)
1 | PE Gokul Barrage STP Project | 60 MLD | M/s. NJS Engineers India Pvt. Ltd. | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-01 | Under Progress
2 | PE Agra STP Project | 31 MLD 35 MLD 100 MLD | M/s. NJS Engineers India Pvt. Ltd. | 2026-07-01 | 2026-07-01 | 2026-06-01 | 2026-06-01 | Under Progress
3 | PE Meerut STP Project | 220 MLD | M/s. AECOM India Pvt. Ltd. In JV with M/s. PDCOR Limited | 2026-07-01 | 2026-07-01 | 2026-06-01 | 2026-07-01 | Under Progress
4 | PE Saharanpur STP Project | 135 MLD | M/s. MSV International Tech Private Limited in consortium with M/s. MSV international Inc. & M/s. BMRV Engineering Consultant LLP | 2025-05-01 | 2025-10-01 | 2025-05-01 | 2025-05-01 | Under Progress
5 | PE Lucknow STP Project | 100 MLD | M/s. Shah Technical Consultants Pvt. Ltd. | 2026-06-01 | 2026-07-01 | 2026-05-01 | 2026-07-01 | Under Progress
6 | PE Garden Reach STP Project | 65 MLD | M/s. Fichtner Consulting Engineers (India) Pvt. Ltd. | 2026-07-01 | 2026-07-01 | 2026-04-01 | 2026-06-01 | Under Progress
7 | PE Dhanbad STP Project | 18 MLD 21 MLD 75 MLD 60 MLD 18 MLD | M/s. MSV International Tech Private Limited in consortium with M/s. MSV international Inc. & M/s. BMRV Engineering Consultant LLP | 2026-04-01 | 2026-07-01 | 2025-04-01 | 2025-04-01 | Under Progress
1 | Katihar | 55 MLD | [5 empty] | Under Tendering
2 | Aligarh | 113 MLD | [5 empty] | Under Tendering
13 | Siliguri | 49 MLD | [5 empty] | Under Tendering
3 | Moradabad | 80 MLD | [5 empty] | Under Tendering
4 | Durga Drain, Varanasi | 60 MLD | [5 empty] | Under Tendering
5 | Pt. DDU Nagar, Chandauli | 45 MLD | [5 empty] | Under Tendering
6 | Arrah | 47 MLD | [5 empty] | Under Tendering
Total

## MPR 1.4_KSDC
MPR 1.4
April 2026 - March 2027
For the month of Aug 2026
Knowledge-cum-Skill Development Centre (KSDC)
S.No | Activity | Till July, 2026 | Aug, 2026 | Total
1 | Web posts | 0 | 0 | 0
2 | Training/ Workshops | 3 | 4 | 7
3 | Seminar/ Webinar | 0 | 0 | 0
4 | Exposure Visits | 0 | 0 | 0
5 | URMP Related | 0 | 0 | 0
6 | Technical Support | 0 | 0 | 0
7 | Research/ Academic | 0 | 0 | 0
8 | Publications | 0 | 0 | 0
Annexure
List (Type 2,3,4,5) Aug 2026
S.No | Event Topic | Type | Venue | Date/Days/Duration | No. of Participants
1 | Capacity building program under KSDC for Hardoi, Uttar Pradesh | Off-site | DDA Biodiversity Park, Delhi | 04.08.2026-06.08.2026 | 18
2 | Capacity building program under KSDC for Nainital- Bhimtal, Uttarakhand | Off-site | DDA Biodiversity Park, Delhi | 11.08.2026-13.08.2026 | 16
3 | Capacity building program under KSDC for Bhadohi, Uttar Pradesh | Off-site | DDA Biodiversity Park, Delhi | 19.08.2026-21.08.2026 | 12
4 | Capacity building program under KSDC for Kasganj, Uttar Pradesh | Off-site | DDA Biodiversity Park, Delhi | 22.08.2026-24.08.2026 | 12
List (Type 1,6) Aug 2026
| Sl. No. | Subject |  | Date
List (Type 7) Aug 2026
| Sl. No. | Subject |  | Date
1
2
3

## MPR 3.1 CPCB
MPR 3.1
(April 2025 - July 2026)
For the month of July, 2026
Technical Division / CPCB related
Sl. No. | Activity | Till Jun-26 | 2026-07-01
1 | STP Inspection Reports Received **
| Uttrakhand | Dec'25 - Mar'26 | -
| Uttar Pradesh | Dec'25 - Mar'26 | -
| Bihar | Dec'25 - Mar'26 | -
| Jharkhand | Dec'25 - Mar'26 | -
| West Bengal | Dec'25 - Mar'26 | -
2 | River water Quality Data Received *
| Uttrakhand | Oct'25- Dec'2025 | Jan'26- Mar'2026
| Uttar Pradesh | Oct'25- Dec'2025 | Jan'26- Mar'2026
| Bihar | Oct'25- Dec'2025 | Jan'26- Mar'2026
| Jharkhand | Oct'25- Dec'2025 | Jan'26- Mar'2026
| West Bengal | Oct'25- Dec'2025 | Jan'26- Mar'2026
3 | GPI Inspection Report received *
A | Target (8th Round - till 15th Jan2026) | Covered | Annexure A
| 3703 (Ganga: 1296; Yamuna: 2407) | 3703 | 3703
B | Target (9th Round - till 15th Jan2027)
| 3938 (Ganga : 1306 ; Yamuna : 2632) | 921* | 281#
4 | River water Quality Data upload on GKC *
| Uttrakhand | Jan'25- Dec'2025 | -
| Uttar Pradesh | Jan'25- Dec'2025 | -
| Bihar | Jan'25- Dec'2025 | -
| Jharkhand | Jan'25- Dec'2025 | -
| West Bengal | Jan'25- Dec'2025 | -
5 | Number of Publications/Reports | 65 | 5
* Pls indicate period
** Pls indicate month
Annexure for S.No 5
S.No. | Name of Document | Date
1 | Review of Gap in data in NWMP-112 MWQM Stations with interstate (UK, UP & Bihar) data for 2024&25. | 2026-07-02
2 | Post Monsoon-2025 Monitoring of Drains in UP (Nov 2025-Feb 2026) discharging in River Ganga and its tributaries (Bijnor-Ghazipur) | 2026-07-08
3 | Post Monsoon-2025 Jt. Monitoring of 30 Drains (Dec. 2025-Feb. 2026) discharging in River RamGanga and its tributaries (Bijnor-Ghazipur) | 2026-07-06
4 | Progress report of NMCG funded projects -PIAS, SER and WQM - Jan-March 2026 | 2026-07-16
5 | Laboratory Audit reports (Draft) of Ganga Main Stem States | 2026-07-17
Annexure A for S.No 3 B
| Total GPIs (9th Round) | 3938
| * Inspected | 921*
| # Reports uploaded on CPCB Portal | 281# | Process of Report review 'In Progress' by SPCBs/ PCCs
| Complied | - | << Total Action Completed Till date
| Non-Complied | - | << Total Action Completed Till date
| Temporary Closed | - | << Total Action Completed Till date
| Permanently Closed | - | << Total Action Completed Till date

## MPR 3.2_Regulatory Cell
MPR 3.2
(April 2026 - March 2027)
For the month of August (As on 31st August 26)
Technical Division / Regulatory Cell
A | Pending Applications
1 | Pending Application at the end of July 26 | 13
2 | Application returned back in August 26 | 4
3 | Applications decided in August 26 | 1
4 | New Applications received in August 26 | 5
5 | Pending Application at the end of August 26 | 13
6 | Out of S.No. 5, applications pending more than 3 months ( Received before 1st May 2026) | 2
(5)= (1)-(2)-(3)+(4)
B | Regulatory Cell meeting
Date | Meeting Number | Cases Considered | Cases Deferred/Return | Cases Recommended
| 0 | 0 | 0 | 0
Annexure for A/S.No 6
S.No. | Subject | Applicant | Date | Status
1 | Construction of water intake structure for drawl of water from river Ganag at Mirzapur for meeting requirement of 2*800 MW Ultra Super Critical Thermal Power Project at Mirzapur, U.P. | Mirzapur Thermal Energy (UP) Pvt. Ltd. (Adani Group) | 2026-02-17 | To be considered in upcoming 17th cell meeting.
2 | Construction of water intake structure for withdrawal of water from river Ganga at Bhagalpur District, Bihar for 3*800 MW thermal power project | Adani Power Limited | APL/PIR/NMCG/016 dated 21.01.2026 on 23.04.2026 | Under Examination

## MPR 4.1_E-file status
eOffice closed files summary | MPR 4.1
(With initial total number of eFiles =7,375 on 31st January 2026)
Period | No. of eFiles closed
From 1st April 2020 –till 25th Oct 2025 | 104
26th Oct 2025 – till 31st Oct 2025 | 48
1st November 2025 to 30th November 2025 | 299
1st December 2025 to 31st December 2025 | 1
1st January 2026 to 31st January 2026 | 69
1st February 2026 to 28th February 2026 | 1
1st March 2026 to 31st March 2026 | 0
1st April 2026 to 30th April 2026 | 1
1st May 2026 to 31st May 2026 | 2
1st June 2026 to 30th June 2026 | 2
1st July 2026 to 31st July 2026 | 2
1st August 2026 to 31st August 2026 | 0
Total | 529
Wing/Section/ Unit wise summary from 26th Oct 2025 till 30th November 2025
i. SMD Section: 271
ii. Finance Wing: 42
iii. Communication Wing: 21
iv. Admin Wing: 13
Total: 347
Wing/Section/ Unit wise summary from 1st December 2025 to 31st December 2025
i. SMD Section: 1
Total: 1
Wing/Section/ Unit wise summary from 1st January 2026 till 31st January 2026
i. SMD Section: 67
ii. O/o ED (Tech): 2
Total: 69
Wing/Section/ Unit wise summary from 1st February 2026 till 28th February 2026
i. O/o ED/ Finance: 01
Wing/Section/ Unit wise summary from 1st March 2026 till 31st March 2026
i. Nill
Wing/Section/ Unit wise summary from 1st April 2026 till 30th April 2026
i. Communication Wing: 1
Wing/Section/ Unit wise summary from 1st May 2026 till 31st May 2026
i. Communication Wing: 1
ii. O/o ED (Tech): 1
Wing/Section/ Unit wise summary from 1st June 2026 till 30th June 2026
i. HR & Training: 1
ii. O/o ED (Tech): 1
iii.
Wing/Section/ Unit wise summary from 1st July 2026 till 31st July 2026
i. SMD Section: 1
ii. O/o ED (Tech): 1
Wing/Section/ Unit wise summary from 1st August 2026 till 31st August 2026
NIL

## MPR 5.2_GKC
MPR 5.2
Monthly Progress Report- Gyanganga.ai (August 2026)
Generated on 1st September 2026
Sl. No. | Title | Till 31st July 2026 | 2026-08-01 | FY 2026-27 | Total (as on 31st August 2026)
1 | Total Number Document on GKP | 1408 | 15 | 52 | 1423
2 | Other Literature on River Ganga | 10381 | 20 | 85 | 10401
Categories-wise details of documents uploaded between 1st to 31st August 2026
Categories | Sub-categories | No. of documents
Publications |  | 0
Journals |  | 0
| Student Thesis Competition (STC) | 0
Articles |  | 15
Books |  | 0
Studies/Reports |  | 0
Guidelines |  | 0
Misellaneous |  | 0
Ganga River (Main Stem)Water Quality Data |  | 0
Data Set | River Atlas | 0
| Ganga River (Main Stem) Water Quality Data (CPCB) | 0
Coffes Table Books |  | 0
River Series |  | 0
Maps |  | 0
Total |  | 15
Details of documents uploaded between 1st to 31st August 2026
S.No | Category | Subject | Organization
1 | Articles | Molecular traces of invasion: eDNA-based high-resolution mapping of Nile tilapia (Oreochromis niloticus) across freshwater habitats of West Bengal, India | CENTRAL INLAND FISHERIES RESEARCH INSTITUTE (CIFRI)
2 | Articles | Stock Status of Two Commercially Important Catfishes, Mystus gulio (Hamilton 1822) and Mystus cavasius (Hamilton 1822), in Relation to Environmental Variables Along the Lower Stretches of the River Ganga, India | CENTRAL INLAND FISHERIES RESEARCH INSTITUTE (CIFRI)
3 | Articles | Environmentally relevant concentrations of triclosan modulate the brain proteome profile of Labeo catla | CENTRAL INLAND FISHERIES RESEARCH INSTITUTE (CIFRI)
4 | Articles | Status of Ganges River dolphin Platanista gangetica (Lebeck, 1801) in the lower stretch of the Ganga River, India, with emphasis on threats, conservation, and recommendations | CENTRAL INLAND FISHERIES RESEARCH INSTITUTE (CIFRI)
5 | Articles | Adaptive Co-Management and Future Resilience of Coastal Winter Migratory Bag Net Fisheries in Indian Sundarbans: Ensuring Livelihood Sustainability Amidst Climate Change | CENTRAL INLAND FISHERIES RESEARCH INSTITUTE (CIFRI)
6 | Articles | Fate and Effects of Heavy Metals in Fishes: Antioxidant Defense System, miRNA/Gene Expression Response, and Histopathological Reproductive Manifestations | CENTRAL INLAND FISHERIES RESEARCH INSTITUTE (CIFRI)
7 | Articles | Hormonal symphony: The dynamic duo of IGF and EGF in gonadotropin-induced fish ovarian development and egg maturation | CENTRAL INLAND FISHERIES RESEARCH INSTITUTE (CIFRI)
8 | Articles | Clearing the path: Unraveling bisphenol a removal and degradation mechanisms for a cleaner future | CENTRAL INLAND FISHERIES RESEARCH INSTITUTE (CIFRI)
9 | Articles | Age-specific changes in the serum proteome of female anadromous, hilsa Tenualosa ilisha: a comparative analysis across developmental stages | CENTRAL INLAND FISHERIES RESEARCH INSTITUTE (CIFRI)
10 | Articles | Distribution patterns of antioxidants in the organs of anadromous fish Tenualosa ilisha (Hamilton, 1822)—a profiling in different age groups for future application in anti-aging | CENTRAL INLAND FISHERIES RESEARCH INSTITUTE (CIFRI)
11 | Articles | Unlocking the nutritional potential: amino acid profile of eight Indian food fishes and their role in meeting recommended dietary allowances | CENTRAL INLAND FISHERIES RESEARCH INSTITUTE (CIFRI)
12 | Articles | Indiscriminate pesticide use for fishing in the River Ganga raises alarm | CENTRAL INLAND FISHERIES RESEARCH INSTITUTE (CIFRI)
13 | Articles | Toxic Metal Element Concentration in 31 Food Fishes from River Ganga: Risk Assessment on Human Consumption | CENTRAL INLAND FISHERIES RESEARCH INSTITUTE (CIFRI)
14 | Articles | Amino Acid Composition of Thirty Food Fishes of the Ganga Riverine Environment for Addressing Amino Acid Requirement through Fish Supplementation | CENTRAL INLAND FISHERIES RESEARCH INSTITUTE (CIFRI)
15 | Articles | Hilsa fisheries in India: a socio-economic analysis of fishers in deltaic Ganga region of river Hooghly | CENTRAL INLAND FISHERIES RESEARCH INSTITUTE (CIFRI)

## MPR 5.3-Prayag status
MPR 5.3
(April 2026 - March 2027)
For the month of August (As on 1st September 2026)
MPR PRAYAG/ GeoPortal etc
A | OCEMS Status
1 | Installation and Data Status
a | No. of STPs with OCEMS Installed | 284
b | No. of STPs with Flow Data received | 197
c | No. of STPs with Influent Characteristic Data received | 178
d | No. of STPs with Effluent Characteristic Data received | 249
2 | Data Reliability Status
a | No. of STPs with Satisfactory Data received | 240
b | No. of STPs with Poor Data Quality (Annex A1) | 4
c | No. of STPs with No Data Received (Annex A2) | 29
B1 | OCEMS based results communicated to States till Month | Communicated till August 2026
B2 | Alerts, STPs _NGP ( Annexure (B1)) | STPs=9 (Alerts=63)
| Alerts, STPs _Non-NGP ( Annexure (B2)) | STPs=6 (Alerts=26)
C1 | Eflow reports _Ganga_ updated till period | Q1, 2026
C2 | EFlow reports _Yamuna_ updated till period | Q1, 2026
D | GDPMS | VM inaccessible post Vulnerability assessment, VM upgrade pending with GIS Cell
| No. of Meetings held in July 2026 | -
| No. of Meetings held in June 2026 | -
E | PRAYAG_GEO Portal
| No. of Active GIS Layers (Annex B) | 29
| No. of Use Cases | 3
PRAYAG/ Geoportal-MPR August 2026 (Item 5.3, MPR)
Annexure A1 - No. of STPs with Poor Data Quality
S. No. | State | STP | Data Availability (%)
1 | Jharkhand | 1.5 MLD STP Harmu | 22.6
2 | Uttar Pradesh | 17.7 MLD STP Farrukhabad | 0.35
3 | Uttar Pradesh | 50 MLD STP at Sector-168 | 27.64
4 | Uttar Pradesh | 78 MLD STP Dandupura Agra | 34.62
Annexure A2 - No. of STPs with No Data Received
S. No. | State | STP
1 | Delhi | 0.66 MGD Molar Band
2 | Delhi | 20 MGD Nilothi Phase II
3 | Jharkhand | 1.5 MLD STP Chutia
4 | Jharkhand | 11.4 MLD STP Bokaro
5 | Jharkhand | 2.57 MLD STP Bokaro
6 | Uttar Pradesh | 1 MLD STP ANUPSHAHAR
7 | Uttar Pradesh | 1.5 MLD STP Anupshahar (UPJN)
8 | Uttar Pradesh | 10.445 MLD STP Etawah
9 | Uttar Pradesh | 100 MLD STP at Noida Sector 168
10 | Uttar Pradesh | 120 MLD STP Goitha Varanasi
11 | Uttar Pradesh | 13.50 MLD STP Tixi Nala
12 | Uttar Pradesh | 14 MLD STP Baghpat
13 | Uttar Pradesh | 15 MLD STP Baniyapur UPJN
14 | Uttar Pradesh | 15 MLD STP SHUKLAGANJ
15 | Uttar Pradesh | 20 MLD CETP Jajmau
16 | Uttar Pradesh | 21 MLD STP ETAWAH
17 | Uttar Pradesh | 21 MLD STP Pakka Bagh
18 | Uttar Pradesh | 3 MLD STP Firozabad
19 | Uttar Pradesh | 30 MLD STP JAUNPUR
20 | Uttar Pradesh | 33 MLD STP Ayodhya
21 | Uttar Pradesh | 40 MLD STP Mapan
22 | Uttar Pradesh | 43 MLD STP Salori
23 | Uttar Pradesh | 80 MLD STP Dinapur
24 | West Bengal | 26.5 MLD STP at Chinsurah
25 | West Bengal | 35 MLD STP Maheshtala Waste Water Management Pvt Ltd
26 | West Bengal | 40 MLD STP at Bally Howarh
27 | West Bengal | 6.5 MLD STP Naihati
28 | West Bengal | 60 MLD STP Baranagar
29 | West Bengal | 65 MLD STP Arupara Howrah
Annexure-B Active GIS layer - August 2026 (As on 01.09.2026)
S. No. | Type | GIS Layer
1 | BASIC | Ganga
2 |  | Ganga Centre line SoI
3 |  | Ganga River Basin
4 |  | Popular River
5 |  | Ganga State
6 |  | Ganga Basin Sub District Census
7 |  | Ganga Basin Town Census
8 |  | Census Sub District 2011
9 |  | Census Town 2011
10 | WATER RESOURCES | India River Network
11 |  | Major Aquifers
12 | ECOLOGY | Riverine Wetland (UP/Bihar/Jharkhand)
13 |  | Wetland PAN India (SAC)
14 | RIVER WATER QUALITY | Ganga Polluted Stretch, 2018
15 |  | Ganga Polluted Stretch, 2022
16 |  | Ganga Polluted Stretch, 2023
17 |  | Ganga Polluted Stretch, 2025
18 |  | Manual Water Quality Stations (Locations)
19 |  | RTQMS (Locations)
20 |  | Biomonitoring (Locations) (to be add)
21 | POLLUTION ASPECTS | Sewage Gap Analysis
22 |  | STP (Other than NMCG) (Locations)
23 |  | STP NMCG (Locations)
24 |  | GPIs (Locations)
25 |  | Solid Waste Dumps (IIRS data)
26 | MISC. | Ganga Centre line 1 km points SoI
27 |  | Ganga Final Survey SoI
28 |  | Point outfall 45N SoI
29 |  | Point outfall 44N SoI

## MPR 5.3 - Annx B1 B2
Annexure B1 & B2
STP Alerts and Exceedances Report - August 2026
A.) NGP
S. No. | STP Name | State | Total Alerts | Total Exceedances | BOD | pH | TSS | NGP/Other
1 | 43 MLD STP Beur | Bihar | 15 | 332 | 30 | 0 | 302 | NGP
2 | 100 MLD STP at Digha | Bihar | 2 | 286 | 94 | 0 | 192 | NGP
3 | 130 MLD STP Jajmau Kanpur | Uttar Pradesh | 19 | 1089 | 94 | 906 | 89 | NGP
4 | 50 MLD STP Ramana Varanasi | Uttar Pradesh | 7 | 441 | 0 | 441 | 0 | NGP
5 | 29 MLD STP Salori (UP Jal Nigam) | Uttar Pradesh | 6 | 99 | 63 | 0 | 36 | NGP
6 | 80 MLD STP Naini 1 (UP Jal Nigam) | Uttar Pradesh | 5 | 96 | 62 | 0 | 34 | NGP
7 | 55 MLD STP Bhagwanpur | Uttar Pradesh | 4 | 384 | 0 | 384 | 0 | NGP
8 | 43 MLD STP Jajmau Kanpur | Uttar Pradesh | 3 | 278 | 46 | 0 | 232 | NGP
9 | 50 MLD STP Numayadahi | Uttar Pradesh | 2 | 79 | 26 | 0 | 53 | NGP
Total alerts generated |  | 63 |  | STPs with alerts |  | 9
Parameter frequency |  | BOD: 415 ¦ pH: 1731 ¦ TSS: 938
B.) Others
S. No. | STP Name | State | Total Alerts | Total Exceedances | BOD | pH | TSS | NGP/Other
1 | 345 MLD STP Bharwara | Uttar Pradesh | 10 | 176 | 0 | 0 | 176 | Others
2 | 70 MLD STP Dhundhahera | Uttar Pradesh | 8 | 214 | 12 | 0 | 202 | Others
3 | 42 MLD STP Daulatganj | Uttar Pradesh | 3 | 124 | 0 | 124 | 0 | Others
4 | 45 MLD STP Aligarh | Uttar Pradesh | 2 | 141 | 29 | 0 | 112 | Others
5 | 32.5 MLD STP Kidwai nagar | Uttar Pradesh | 2 | 66 | 66 | 0 | 0 | Others
6 | 56 MLD STP Dhundhahera | Uttar Pradesh | 1 | 14 | 14 | 0 | 0 | Others
Total alerts generated |  | 26 |  | STPs with alerts |  | 6
Parameter frequency |  | BOD: 121 ¦ pH: 124 ¦ TSS: 490

## MPR 5.4-Jan Ganga Vertical_Comm
MPR 5.4
(April 2026 - March 2027)
For the Month of August 2026 (As on 1st September 2026)
MPR Communication
| Followers | Till Previous Month-July 2026 | Current Month- August 2026
1 | Twitter | 124983 | 125045
| Facebook | 627430 | 652430
| Instagram | 154824 | 152350
2 | In Current Month
a) | Webposts (excluding B and C) | Number of Images | Videos (Minutes)
| Twitter | 223 | 35 | 48 Min
| Facebook | 223 | 35 | 48 Min
| Instagram | 154 | 38 | 55 Min
b) | Rebuttals on | 4 | 1 post from NMCG page and 3 post from influencer
Social Media
c) | Positive Stories | 22 |  | Annex A
Social Media
3 | Youtube
4 | Print Media
a) | Rebutted | No
b) | Positive Stories | 14 |  | Annex A
5 | Publication through PIB
a) | Press Release ( Atleast One per month )
i) | Press Release-Event Based | Departmental Summit , 31st Augsut
ii) | Press Release- Success Story | People River Connect , PIB to release it as explainer
b) | Backgrounder ( One per Quarter ) | Planned for next month
c) | Articles/Op-eds in Newspapers ( One article -Half Yearly) | Work is currently in progress
|  | Number of Events | Participation
6 | Events Organised by NMCG |  |  | Annex B
i). | Cleanliness Drives on Yamuna | 5 | Approx. 2500
7 | Events through Partner |  |  | Annex B
a) | DGC & SMCG | 264 | Approx. 78258
b) | NGO | Nil | Nil
c) | Institutes | Nil | Nil
| Total | 264 | Approx. 78258
8 | Sponsorship | Nil
9 | Capacity Building Training /Workshop (Communication Unit ) | Nil
Annex B
| Annex A | S. No 2 C, 4 B | Coverage
S. No. | Title | Date | Twitter | Facebook | Instagram
1 | National Framework on Safe Reuse of Treated Wastewater | 2026-08-03 | https://x.com/cleanganganmcg/status/2084125250137346551?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid035y3RyjXqLQatBpbsS9ijbcPGX3QUFqVcqFMLQZph1Ws5kXVv8qF7HU3uTs6VUg3Vl | www.instagram.com/reel/DbkIr2VPVNS/?utm_source=ig_web_copy_link&igsi=NTc4MTIwNjQ2YQ==
2 | Wetland, Prayagraj | 2026-08-05 | https://x.com/cleanganganmcg/status/2084854563115593741?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid036g77MAxCF14Mp4KWQTHUTyfuB4Xg73DmYBr4wMpY5BZUth1swBdAYehczMzc2ZJrl | https://www.instagram.com/p/DbpQ7EQvnh3/?utm_source=ig_web_copy_link&igsi=NTc4MTIwNjQ2YQ==
3 | Project update, Mirzapur | 2026-08-06 | https://x.com/cleanganganmcg/status/2085299799914598689?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid029kmseixYeVhLsRQ99MkgBUsHT74DhezY1SR72G7xHeNH8zW96MspoiudoMVgAufVl | https://www.instagram.com/p/Dbsa4pQgJ2i/?utm_source=ig_web_copy_link&igsi=NTc4MTIwNjQ2YQ==
4 | Turtle Rescue | 2026-08-06 | https://x.com/cleanganganmcg/status/2085314069259813267?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid0kDyYjz32owy48YnxY26YcvyXjJnugEJAXmCdaBKXG6ZYzvPTRzA7q3xaVZ4Xpuhkl | https://www.instagram.com/p/DbshGpbjNb_/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==&igsi=MzRlODBiNWFlZA==
5 | Cleanliness Drive, Delhi | 2026-08-09 | https://x.com/cleanganganmcg/status/2086384002743849342?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid02mzXKAJULxYv5eAPC1fcpRh6YPCDmsUvSQTnmxzEdpYtEv1tg9fdMU33uGonCfeVEl | https://www.instagram.com/p/Db0KJTHj0yS/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==&igsi=MzRlODBiNWFlZA==
6 | Wetland, Budaun | 2026-08-10 | https://x.com/cleanganganmcg/status/2086681243345883260?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid0w2J8ZX5crHnRceKNrS3SdHtseBp1QqM5RttnscWxJt1vMeayyLTm9jegr3rbqc8gl | https://www.instagram.com/p/Db2PL5kDIuP/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==&igsi=MzRlODBiNWFlZA==
7 | Cleanliness Drive by Being Helper Foundation, Bihar | 2026-08-10 | https://x.com/cleanganganmcg/status/2086702872184619338?s=20 | https://facebook.com/reel/1021401107425577/ | https://www.instagram.com/reel/Db2TdAzMxkT/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==&igsi=MzRlODBiNWFlZA==
8 | Project Update, Ghazipur STP | 2026-08-11 | https://x.com/cleanganganmcg/status/2087127091724910811?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid02uwPabZTGgPhPVLBxJPmR3qBpEihFkSYuULEATSYZ6ZmFw5Y4didz7DzfGiC9ySKol | https://www.instagram.com/p/Db5TppsgD0y/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==&igsi=MzRlODBiNWFlZA==
9 | Wetland Aligarh | 2026-08-11 | https://x.com/cleanganganmcg/status/2087054932067450917?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid034NS4o7A3vDNETeaC5juYiYzqALWHLTHszCtEHQXwxDGXoW15aCfB3yyuSH8Y1ZYCl | https://www.instagram.com/p/Db4548ajNz_/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==&igsi=MzRlODBiNWFlZA==
10 | Gharial Rescue, Kanpur | 2026-08-12 | https://x.com/cleanganganmcg/status/2087524350459285672?s=20 | https://fb.watch/J6pGxizmRE/ | https://www.instagram.com/reel/Db8OPF8if41/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==&igsi=MzRlODBiNWFlZA==
11 | Cleanliness Drive by Kanpur Ploggers | 2026-08-16 | https://x.com/cleanganganmcg/status/2088939493927874678?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid02dQk4uJkVcLccbvM7EpQe5MZhvX5qcgFZzG8yZMi6F6gbGxXMywwfLuSQc214hfryl | https://www.instagram.com/p/DcGR4nPjzX-/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==&igsi=MzRlODBiNWFlZA==
12 | Wetland, Kasgunj | 2026-08-19 | https://x.com/cleanganganmcg/status/2089926067993858525?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid0GYhNLCptYgUtr3Du1e2SJ5kJWjgDZ1LHDBpDZtnsTM7yHQg1SwgHLu2ppQjUKfbRl | https://www.instagram.com/p/DcNXlQ8D1bS/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==&igsi=MzRlODBiNWFlZA==
13 | Public review, Patna | 2026-08-19 | https://x.com/cleanganganmcg/status/2090059203805073431?s=20 | https://facebook.com/reel/1062542436151643/ | https://www.instagram.com/reel/DcN_ETksW5x/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==&igsi=MzRlODBiNWFlZA==
14 | Tamsa river | 2026-08-19 | https://x.com/cleanganganmcg/status/2090305748832297080?s=20 | https://www.facebook.com/share/v/1BoKMPouv5/ | https://www.instagram.com/reel/DcQA7aQMI0G/?utm_source=ig_web_copy_link&igsi=MzRlODBiNWFlZA==
15 | Two Concession Agreements signed, strengthening wastewater management in Uttar Pradesh | 2026-08-21 | https://x.com/cleanganganmcg/status/2090691643263660400?s=20 | https://www.facebook.com/share/p/19GR4gzrjU/ | https://www.instagram.com/p/DcSuUwgj35N/?utm_source=ig_web_copy_link&igsi=MzRlODBiNWFlZA==
16 | Kali Ghat, Prayagraj | 2026-08-22 | https://x.com/cleanganganmcg/status/2091061832002007434?s=20 | https://www.facebook.com/share/v/1Bweu3S6gV/ | https://www.instagram.com/reel/DcTsk3nvjMu/?utm_source=ig_web_copy_link&igsi=MzRlODBiNWFlZA==
17 | Jeremy Wade (Rebuttal post) | 2026-08-24 | https://x.com/cleanganganmcg/status/2091848509519794232?s=20 | https://www.facebook.com/share/p/1MiTJux7in/ | https://www.instagram.com/p/Dca8-bBCGIg/?utm_source=ig_web_copy_link&igsi=MzRlODBiNWFlZA==
18 | Cleanliness drive by BHF, Patna | 2026-08-24 | https://x.com/cleanganganmcg/status/2091820308022079497?s=20 | https://www.facebook.com/share/r/199CkZ2yiX/ | https://www.instagram.com/reel/DcavsNEinKc/?utm_source=ig_web_copy_link&igsi=MzRlODBiNWFlZA==
19 | Kham River | 2026-08-24 | https://x.com/cleanganganmcg/status/2091761059552227347? | https://www.facebook.com/share/v/1LZ6e6nEEY/ | https://www.instagram.com/reel/DcaW133FaqX/?utm_source=ig_web_copy_link&igsi=MzRlODBiNWFlZA==
20 | Project Update, Ayodhaya | 2026-08-25 | https://x.com/cleanganganmcg/status/2092107365680398420?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid036eoFN9jW95f7hGW2ut29mBeCoFWbvZNXN49ButNRf2wLSYBuPAzm3x5c9pQe2zqgl | https://www.instagram.com/p/DcczEu3sHJm/?utm_source=ig_web_copy_link&igsi=MzRlODBiNWFlZA==
21 | Moran River | 2026-08-27 | https://x.com/cleanganganmcg/status/2092840824182919556?s=20 | https://fb.watch/JkTfxvAf2i/ | https://www.instagram.com/reel/DciADtFlUPO/?utm_source=ig_web_copy_link&igsi=MzRlODBiNWFlZA==
22 | Yamuna Cleanliness Drive | 2026-08-30 | https://x.com/cleanganganmcg/status/2093999613288300672?s=20 | https://www.facebook.com/share/p/1J3zWbdLEH/ | https://www.instagram.com/p/DcqNQE0j0Q0/?utm_source=ig_web_copy_link&igsi=MzRlODBiNWFlZA==
23 | Kalindi to Be Free of Toxic Pollution; First 100 MLD STP Ready | 02nd August, 2026
24 | National Mission for Clean Ganga Seeks Chief Secretary’s Update on Pollution Action | 09th August, 2026
25 | Dirty Water from Small Drains to Be Treated Before Entering the Ganga | 11th August, 2026
26 | New Definition of Ganga Floodplain Area Finalised; ‘Construction-Free Zone’ Term Removed | 13th August, 2026
27 | Ganga’s Health Begins to Improve, Presence of Hilsa Signals Positive Change | 13th August, 2026
28 | Measures to Curb Pollution from Non-Point Sources into the Ganga | 14th August, 2026
29 | Gomti River Set for Major Rejuvenation Drive | 14th August, 2026
30 | 43 Yamuna-Polluting Drains to Be Tapped at a Cost of ₹127 Crore | 18th August, 2026
31 | Three Kasganj wetlands entered in UP gazette: NMCG | 19th August, 2026 | https://www.hindustantimes.com/cities/lucknow-news/three-kasganj-wetlands-entered-in-up-gazette-says-nmcg-101787127323471.html
32 | Two new STP projects to strengthen waste water management in UP | 21st August, 2026 | https://theprint.in/india/two-new-stp-projects-to-strengthen-waste-water-management-in-up/3021228/
33 | ₹2.36 Crore Project Launched to Protect the Ganga and Sustain River Flows | 23rd August, 2026
34 | Ganga to Be Free from Polluting Drains; ₹256 Crore Project Takes Shape | 23rd August, 2026
35 | From pollution to revival, Kham emerges as model for seasonal rivers: NMCG | 24th August, 2026 | https://theprint.in/india/from-pollution-to-revival-kham-emerges-as-model-for-seasonal-rivers-nmcg/3023871/
36 | ‘Namami Gange’ Brings Transformation; Saryu Riverbank Gets a New Lease of Life | 26th August, 2026
37 | From Awareness to Ownership: Building a People's Movement for River Conservation | 16th Aug, 2026 | To be Released as a Explainer | PIB
38 | Ministry of Jal Shakti to host the First Departmental Summit under Hon'ble Prime Minister's Vision of Cooperative Federalism | 31st Aug 2026 | https://www.pib.gov.in/PressReleasePage.aspx?PRID=2305197&reg=48&lang=1 | PIB
| Annex B | S. No 5,6,7
S. No. | Event Name (Activity Type) | Agency | Date | Venue | Participants
1 | Cleanliness Drives on Yamuna | NMCG with NGOs (Delhi) | Every Sunday | ITO Chhath Ghat, Signature Bridge, Soor Ghat & Thokar No. 18, Geeta Colony | NGOs- Saksham Bhoomi Fgoundation; YSS Foundation; Friends of Yamuna & Swachh Yamuna Abhiyaan; Schools, Colleges, Youth Groups, NGOs and Yamuna Task Force etc.
UTTARAKHAND
2 | Har Ghar-Har Ghat Tiranga (Flag Hoisting, Evening Programs on or near River Banks, Collective Singing of Vande Matram Song, Tiranga Yatra and rallies etc.) | DGCs, academic institutes (Govt. PG/Degree Colleges) & Universities | 09 to 17.08.2026 | Govt. PG/Degree Colleges (Agastyamuni, Uttarkashi, Dehradun, Gopeshwar, Joshimath, Jawalapur, Khadi, Narayan Nagar Didihat, Thalisain, Pithoragarh, Ramnagar, Maldevta, Paithani, Lohaghat, Majra Mahadev, Haldwani, Chandrabani, Jahrikhal Devprayag & Rudraprayag and Phoenics University, Roorkee and Sparsh Himalaya University | College Students, Teachers, Volunteers & Local Communities
3 | Cultural Program, Competitions (Quiz, Rangoli, Essay, Drawing & Wall Painting) | Empanelled Govt. PG Colleges | 08.08.2026 | PM SHRI GGIC Jwalapur (Haridwar); Government Post Graduate College Joshimath, Didihat, Lohaghat, Pithoragarh, Maldevta, Raipur & Dehradun; Thalisain, Pauri Garhwal; Government Post Graduate College Lohaghat, Government Post Graduate College Uttarkashi, Women's Commerce College Haldwani; Sant Narayan Swami Government Post Graduate College Narayan Nagar, Didihat; PG College Ramnagar, Government College Chandrabadni and Karanprayag | College Students, Teachers & Volunteers
4 | Environmental conservation, cleanliness drive and plantation drives | Empanelled Govt. PG Colleges | 14 to 19.08.2026 | Champawat, Nainital, Bageshwar and Tehri, Balganga-Sendul, Rishikesh, Uttarkashi, Didihat, Thalisain, Paithani, Chandrabadni, Agastyamuni, Haldwani, Lohaghat, Ramnagar, Gopeshwar, Jwalapur, and Joshimath | College Students, Teachers, Volunteers & Local Communities
UTTAR PRADESH
5 | Har Ghar- Har Ghat Tiranga Campaign (Flag Hoisting, Tiranga Rallies, Shapath, Collective Singing of National Song, Tiranga Yatra/Raalies, Signature & Selfie Campaign, Kavi Sammelan, Cultural programs etc.) | DGCs, Nagar Palika Parishad, Education Department, Schools/Colleges, Forest Department, NSS/NCC, Gram Panchayats & NGOs | 09 to 17.08.2026 | Various Locations Ghats, Community Parks, Schools, Colleges, Public Places and other strategic locations | District Administration, Officials of other Departments, School/College Students, Teachers, Youth Groups, Volunteers & Local Leaders and ommunities
6 | Plantation Campaign | DGCs, Forest Department, Wildlife Range, Irrigation Department, Academic Institutions | 17 to 27.08.2026 | Various locations- Schools, Colleges, Ghats, DFO Office and other strategic locations | School/College Students, Teachers, DFO, Youth Groups, Volunteers & Local Communities
7 | Regular Awareness, Cleanliness and Public Outreach Activities (Ghat Cleaning, Nukkad Natak, Awareness Rallies, Prabhat Pheri, Quiz & Competitions etc.) | DGCs & academic institutions | Entire Month | Various Locations | Students, Volunteers & Local Communities
8 | Workshop on 'River, Water & Environment Conservation' | Forest Division (Sonbhadra), Nagar Palika Praishad (Robertsganj), Kaimur Wildlife Robertsganj Range, Irrigation Depratment Sonbhadra | 06.08.2026 | Govt. Polytechnic College, Roberttsganj, Sonbhadra | District Administration, CDO, BDO other officials of the Departmets and Students
BIHAR
9 | Har Ghar- Har Ghat Tiranga (Flag Hoisting, Evening Programs on or near River Banks, Collective Singing of Vande Matram Song, Tiranga Yatra and rallies etc.) | DGCs & academic institutions | 09 to 17.08.2026 | Various Locations, Ghats, Schools & Colleges | School & College Students, Teachers, Youth Groups, Volunteers, NGOs & Local Communities
10 | Other regular IEC Activities (Cleanliness Drives, Aarti, Quiz & Competitions, Nukkad Natak, Plantation activities etc.) | DGCs | Entire Month | Various Locations | School & College Students, Teachers, Youth Groups & Local Communities
JHARKHAND
11 | Har Ghar- Har Ghat Tiranga (Flag Hoisting, Evening Programs on or near River Banks, Collective Singing of Vande Matram Song, Tiranga Yatra and rallies etc.) | DGC & Nagar Parishad-Sahibganj, Bokaro, Rajmahal, Chatra, Dhanbadh & Ramgarh and District Education Department | 09 to 17.08.2026 | Shibu Sorean Smriti Bhawan Townhall, Collectorate, Police Line (Bokaro); Chatra Block (Chatra); Townhall, Jora Talab, Barkakana, Haribandh, Gola, Collectorate (Ramgarh) and PHED Meeting Hall (Dhanbad), UPG High School, Kaitha, Mukteshwar Dham Ghat & town (Sahibganj), Suryadev Ghat (Rajmahal) | Youth, Students, Volunteers & Local Communities
12 | Independence Day Celebrations | DGCs | 15.08.2026 | Various Locations | School & College Students, Teachers, Youth Groups, Volunteers, NGOs & Local Communities
13 | Other regular IEC Activities (Cleanliness Drives, Aarti, Quiz & Competitions, Nukkad Natak etc.) | DGCs- Sahibganj & Bokaro, Nagar Parishad and academic institutions | Entire Month | Various Locations | School & College Students, Teachers, Youth Groups, Religious groups, Volunteers, NGOs & Local Communities
WEST BENGAL
14 | Sensitization Workshop for Protection of Gangetic Dolphin | DGC- Murshidabad | 29.07.2026 | Conference Hall, SDO Office, Jangipur Municipal Area, Murshidabad | Block Administration, Sub Divisional Officials, Municipal Officials, WWF Trainers, Professors, Teachers, Fisheries Officials, Forest Department Officials, School/College Students, Local Community People
15 | Har Ghar Tiranga Campaign | DGCs- Malda,Murshidabad, North 24 Parganas, South 24 Parganas, Purba Medinipur, Nadia, Hooghly & Howrah | 09 to 17.08.2026 | Various Locations- Block Development Offices, Municipal Offices, Ghats, Near River banks, Project Sites, Schools/Colleges & Gram Panchayats etc. | District Administration and other Department Officials, School & College Students, Youth Groups, Women Self Help Groups, Volunteers, Villages, Local leaders & representatives and Communities
16 | Regular IEC Activitives (Cleanliness Drives, Awareness Drives & Public Outreach Campaigns) | DGCs | Entire Month | Various Locations | School & College Students, Teachers, Youth Groups, Religious groups, Volunteers, NGOs & Local Communities
17 | 29th National Exhibition | SMCG-West Bengal | 20 to 22.08.2026 | Central Park Maidan, Salt Lake, Kolkata | Students, Teachers and Local Communities

## MPR 5.5 RCA
MPR 5.5
(April 2025 - March 2026)
For the month of AUGUST
Organisation: River Cities Alliance
Sl. No. | Activity | Till Jul 2026 | 2026-08-26 | Total
1 | Web posts | 108 | 9 | 117
2 | Workshops (excluding 5b /URMP Workshops) | 23 | 5 | 28
3 | Seminar/ Webinar/Meetings | 52 | 2 | 54
4 | Exposure Visits | 2 | 0 | 2
5 | URMP Related (Non Ganga Basin)
| a) Meetings in States | 7 | 0 | 7
| b) Workshops in States | 2 | 0 | 2
6 | Publications
| a) Newsletter | 5 | 0 | 5
| b) Others | 22 | 8 | 30
7 | Concept Notes | 9 | 0 | 9
8 | Demands Received
| a) Cities | 14 | 0 | 14
| b) Academia | 7 | 0 | 7
Annexures
List (Type 2,3,4,5) March
Sl. No. | Event Topic | Type | Venue | Date/Days /Duration | Number of Participants
1 | Lecture 2 at SCET Surat on 'Basics of River Basin and Hydrology' as part of the course ' Principles of Urban River Management' | 3 | Online | 6.08.2026 | 22
2 | Eco Friendly Waterfront Development Course - Third Lecture on 'Hydrological Fundamentals , Principles and Risks' | 2 | SPA Bhopal | 11.08.2026 | 19
3 | Lecture 3 at SCET Surat on 'Rivers are intricately connected to groundwater -Understanding rivers, groundwater, aquifers, watersheds and traditional recharge systems' as part of the course ' Principles of Urban River Management' | 3 | Online | 13.08.2026 | 22
4 | Launch and Inception Lecture at O P Jindal on 'Urban Water Cycle and Management Approach' | 2 | O P Jindal | 14.08.2026 | 20
5 | Eco Friendly Waterfront Development Course - Fourth Lecture on 'Floodplain Management' | 2 | SPA Bhopal | 25.08.2026 | 19
6 | Lecture at 'From RIsk to Resilience - Rethinking Flood Management' Symposium at SCET Surat | 2 | SCET Surat | 19.08.2026 | 22
7 | Lecture 4 at SCET Surat on 'Understanding Urban Rivers and Their Transformation' as part of the course ' Principles of Urban River Management' | 2 | SCET Surat | 20.08.2026 | 22
List (Type 1,6) March
Sl. No. | Subject | Type | Date
1 | Inspirational Monday Series on "The Billion Oyster Project, New York " | 1 | 03.08.2026
2 | Quiz series 25: Rivers, Cities, and Answers | 1 | 05.08.2026
3 | Inspirational Monday Series on "Ghata Bundh Restoration Initiative, Gurgaon" | 1 | 09.08.2026
4 | Quiz series 26: Rivers, Cities, and Answers | 1 | 12.08.2026
5 | Inspirational Monday Series on "Coimbatore Lake System Restoration Initiative" | 1 | 17.08.2026
6 | Quiz series 27: Rivers, Cities, and Answers | 1 | 19.08.2026
7 | Inspirational Monday Series on "San Vicente Creek Restoration " | 1 | 24.08.2026
8 | Quiz series 28: Rivers, Cities, and Answers | 1 | 30.08.2026
9 | River Sensitive Master Plans - Recommendations for Ranchi Master Plan | 6b | 06.08.2026
10 | River Sensitive Master Plans - Recommendations for Patna Master Plan | 6b | 06.08.2026
11 | River Sensitive Master Plans - Recommendations for Chapra Master Plan | 6b | 06.08.2026
12 | River Sensitive Master Plans - Recommendations for Prayagraj Master Plan | 6b | 06.08.2026
13 | River Sensitive Master Plans - Recommendations for Kanpur Master Plan | 6b | 06.08.2026
14 | River Sensitive Master Plans - Recommendations for Guwahati Master Plan | 6b | 06.08.2026
15 | River Sensitive Master Plans - Recommendations for Hyderabad Master Plan | 6b | 06.08.2026
16 | River Sensitive Master Plans - Recommendations for Pune Master Plan | 6b | 06.08.2026
17 | Inspirational Monday Series on "Chitlapakkam Lake Restoration Initiative" | 1 | 31.08.2026
List (Type 7) March
Sl. No. | Subject | Type | Date
Demands for RCA (Type 8) March
Sl. No. | Subject | Type | Date
1 |  | 8a
2 |  | 8a
3 |  | 8a

## MPR 5.6 COE-IT BHU
MPR 5.6
(April 2026 - March 2027)
For the month of August
Smart Laboratory on Clean Rivers (MPR 5.6a)
Sl. No. | Activity | Till Jul-26 (A) | Aug-26 (B) | Total (A+B) | FY 26-27
1 | Workshops / Conference - Organised | 9 | 0 | 9 | 4
2 | Capacity Building Workshops - Organised | 7 | 0 | 7 | 3
3 | Publications | 0 | 0 | 0 | 0
4 | STP Performance Evaluation (Number of STPs) | 8 | 0 | 8 | 8
5 | DSS Project (Physical progress %) | 76% | 7% | 83% | 23%
5a | No. Draft Modules Finalized | 10 | 0 | 10 | 0
6 | Characterisation of Emerging Pollutants (Physical progress %) | 66% | 1% | 67% | 4%
6a | No. of Draft SOPs Finalized | 8 | 0 | 8 | 3
7 | Hydrogeological Model of Varuna Basin for MAR sites (Physical progress %) | 76% | 10% | 86% | 25%
7a | No. of Sites implemented | 0 | 0 | 0 | 0
Annexure
List (Type 1, 2)
Sl. No. | Event Topic | Type | Venue | Date/Days/ Duration | Number of Participants
1
2
3
List (Type 3)
Sl. No. | Name of Publication | Date | Submitted
List (Type 4)
Sl. No. | Name of STP | Date visited | Report submitted
1
2
List (Type 5, 6, 7,)
Sl. No. | Project Details | Type | Activities
1 | DSS Project | Type 5 | A review meeting was convened under the chairmanship of Hon’ble DG Sir, NMCG to assess the projects being undertaken under the SLCR. During the meeting, the Decision Support System (DSS) was also presented. Hon’ble DG Sir advised that a modular chart-cum-schematic be prepared, clearly depicting and listing all the modules, sub-modules, and sections of the DSS, to facilitate the finalisation of the scope and components for the subsequent phase of DSS development. Meanwhile, efforts are underway to finalise the remaining modules of the DSS, and further enhance the already developed modules, incorporating the recommendations and feedback received through the stakeholder consultations.
2 | Characterisation of Emerging Pollutants | Type 6 | Eight SOPs namely, Diclofenac, Eplerenone, Telmisartan, Ethofumesate, Metformin, Carbamazepine, Trimethoprim, and Celecoxib have been finalized and submitted to NMCG. An additional SOP for Norfloxacin is currently under preparation.
3 | Hydrogeological Model of Varuna Basin for MAR sites | Type 7 | Development of a groundwater module to understand river–aquifer interactions and exchanges: Construction of Managed Aquifer Recharge (MAR) structures along the Varuna River has commenced.
List (Type 5a, 6a, 7a)
Sl. No. | Draft Finalized | Type | Comments
1
2

## MPR 5.6 COE-IIT Delhi
For the month of August 2026
India-Netherlands Centre of Excellence on Water (MPR 5.6b)
Sl. No. | Activity | Till Jul-26 | 2026-08-01
1 | Workshops / Conference/ Talks Organised | 9 | 1
2 | Capacity Building Workshops | 0 | 0
3 | Publications | 2 | 0
4 | STP Performance Evaluation (No of STPs) | 2 | 0
5 | Digital Twin project | 0 | 0
Annexure
List (Type 1,2)
Sl. No. | Event Topic | Type | Venue | Number of Participants
1 | 7th Gyan Ganga Distinguished Lecture Series in River Sustainability | 1 | Senate Room, IIT Delhi | 50
(Dr. Sujay V. Kumar, NASA Hydrological Sciences Laboratory)
List (Type 3)
Sl. No. | Title | Date of Submission
List (Type 4)
Sl. No. | Name of STP | Date Visited | Report submitted
List (Type 5)
Sl. No. | Details | Remarks
List (Type 7)
Sl. No. | Topic | Category | Date | Venue