## MPR 1.3_Project_COD effective
(April 2026 - March 2027)
For the month June 2026
MPR Project Wing/Projects under progress (MPR 1.3 - JUNE 2026)
A. Under Progress - Sewage inflow to STP started- under trial operations; COD to be Declared
Sl. No. | Project | HAM/DBOT | Total Sanctioned Cost(Cr) | STP Capacity - New (MLD) | Date of start of trial operation | Reasons for delay in COD declaration
1 | I&D and STP at Unnao | HAM | 102.2 | 15 | 2023-11-07 | Trunk sewer along the original alignment has settled. Repair of the same is in progress.
2 | Pollution Abatement works for River Ganga at Hooghly Chinsurah | DBOT | 161.99 | 26.5 | Work yet to be completed | The STP is operational with partial flow. The remaining work of the I&D sewer line could not be completed earlier as open-cut excavation was not feasible. Now, under the approved variation, the balance work will be completed through trenchless pipeline laying.
3 | I&D and STP at Digha | HAM | 824 | 100 | 2025-03-01 | CoD will be declared after the completion of the trial run and successful achievement of the KPIs. NMCG's approval for declaration of Partial COD sent on 09.06.2026.
4 | I&D and STP at Kankarbagh | HAM | 578.89 | 50 | 2025-03-01 | CoD will be declared after the completion of the trial run and successful achievement of the KPIs. NMCG's approval for declaration of Partial COD sent on 09.06.2026.
5 | I&D and STP at Moradabad | HAM | 149.23 | 25 | 2025-07-01 | COD declared - 04/03/2026
6 | I&D and STP at Jangipur | DBOT | 68.47 | 13 | 2025-06-01 | Under trial run and successful achievement of the KPIs.
7 | I & D and STP at Kota | DBOT | 258.48 | 36 | Work yet to be completed | The STP is operational from Dec-2022
8 | I&D and STP at Lucknow | DBOT | 240.93 | 42.5 | 2024-09-01 | 3.5 MLD under progress (39 MLD operational)
9 | I&D and STP at Howrah, Bally and Kamrahati & Baranagar | HAM | 595.72 | 187 |  | Partial COD declared
10 | I&D with STP works at Sapera Basti, Dehradun | DBOT | 78.99 | 15 |  | Under trial operations
11 | I & D and STP works at Muni ki reti, Neelkanth, Swarg aashram | DBOT | 94.06 | 12.8 |  | Under trial operations (Muni-Ki-Reti and Swargashram) Under Construction (Neelkanth)
12 | Interception and diversion of balance discharge of 13 drains and augmentation of Salori STP | DBOT | 331.75 | 43 |  | Under trial operations
13 | I&D and STP Works at Vrindavan | DBOT | 77.7 | 13 |  | Under trial operations
14 | I&D and STP Works for Assi-BHU Area (Phase II), Varanasi, Uttar Pradesh’ under Namami Gange Programme | DBOT | 308.09 | 55 |  | Completed. O&M Start Date - 17/03/2026
15 | I & D and STP Project at Phusro | DBOT | 61.05 | 14 | 10 MLD - Trial started on 15th Jan 2026. 4 MLD- Trial run started on 16th Feb 2026
16 | Interception and Diversion with STP) at Chakdah Municipal Town | DBOT | 121.66 | 15 | trial run started on 14th Feb 2026.
17 | Pollution Abatement Works for River Ganga at North Barrackpore municipality | HAM | 154.27 | 38 | 30 MLD- under trial run since 15.12.2025. | COD for 30 MLD STP declared as 25.03.2026
B. Under Progress - Effective Date to be declared
Sl. No. | Project | HAM/DBOT | Total Sanctioned Cost(Cr) | STP Capacity - New (MLD) | Date of award of LOA | Reasons for delay in Effective date declaration
1 | Interception & Diversion and STP works at Lucknow, Phase-II Part-II | HAM | 351.03 | 100 | 02-06-2025 (Concession Agreement executed on 26/08/2025) | Effective Date declared as 23/06/2026
2 | I & D and STP at Dhanbad | HAM | 808.33 | 192 | Effective date for STP-1 ,2&3 has been declared as 02.03.2026. | Due to pending land NOC the effective date for remaining STPs (STP-4 &5) is yet to be declared.

## MPR 1.5 Project Engg O&M
Details of Project Engineer Engagement in various STP projects, NMCG (MPR 1.5 - JUNE 2026)
Sl No. | Name of the project | STP Capacity | Name of the Bidder | Last MPR approved by NMCG | Last MPR submitted by PE | Last Payment Made by NMCG | Last Invoice submitted by PE | Project Staus | Tentative Payment (Rs. In Cr)
1 | PE Haridwar STP Project | 68 MLD | M/s. Shah Technical Consultants Pvt. Ltd. | PE contract Completed |  |  |  | O&M
2 | PE Varanasi STP Project | 50 MLD | M/s. Mahindra Consulting Engineers Ltd. (MACE) | PE contract Completed |  |  |  | O&M
3 | PE Mathura STP Project | 30 MLD | M/s. Mahindra Consulting Engineers Ltd. (MACE) | PE contract Completed |  |  |  | O&M
4 | PE Prayagraj STP project | 14 MLD 42 MLD 16 MLD | M/s. AECOM India Pvt. Ltd. In JV with URS Scott Wilson India Consortium | Nov-24 | 2025-03-01 | 2024-08-01 | Mar-25 | O&M | 0.4
5 | PE Kanpur STP project | 30 MLD 15 MLD 5 MLD | M/s. Shah Technical Consultants Pvt. Ltd. | 2026-04-01 | 2026-04-01 | Mar-25 | Mar-25 | O&M
6 | PE Howrah, Bally & Baranagar | 65 MLD 40 MLD 60 MLD | M/s. HaskoningDHV Consulting Pvt. Ltd. In JV with HaskoningDHV Nederland B.V | 2025-12-01 | 2025-12-01 | Dec-25 | Dec-25 | O&M
7 | PE Budhana Muzaffarnagar STP Project | 10 MLD 22 MLD | M/s. Egis India Consulting Engineers Pvt. Ltd. | Jun-25 | Jun-25 | 2024-06-01 | Sep-25 | O&M
8 | PE Moradabad STP Project | 25 MLD |  | 2026-02-01 | 2026-04-01 |  | Jan-25 | O&M
9 | PE Mirzapur Ghazipur | 8.5 MLD 8.5 MLD 21 MLD | M/s. NJS Engineers India Pvt. Ltd. | 2026-04-01 | 2026-04-01 | 2025-12-01 | Apr-26 | O&M
10 | PE Maheshtala STP | 35 MLD | M/s. WAPCOS Limted | 2026-04-01 | 2026-04-01 | Aug-25 | Aug-25 | O&M
11 | PE Bareilly | 42 MLD 20 MLD 1 MLD | M/s. HaskoningDHV Consulting Pvt. Ltd. In JV with HaskoningDHV Nederland B.V | PE contract Completed |  |  |  | O&M
12 | PE Ayodhya | 32 MLD |  | PE contract Completed |  |  |  | O&M
13 | PE Farrukhabad-Fatehgarh | 30 MLD 20 MLD 2 MLD |  | PE contract Completed |  |  |  | O&M
Total
Details of Project Engineer in various CETP Projects, NMCG
Sl No. | Name of the project | CETP Capacity | Name of the Bidder
1 | Project Engineer Services for Implementation of 20 MLD Tannery CETP & associated components at Jajmau, Kanpur, Uttar Pradesh | 20 MLD | M/s. Tamil Nadu Water Investment Company Limted (TWIC)
2 | Project Engineer Services for the upgradation of 4.5 MLD CETP for Tanneries with Soak Stream Treatment, Common Chrome Recovery System, Composite Stream Treatment on ZLD Technology at Banthar, Unnao Uttar Pradesh | 4.5 MLD | M/s. NJS Engineers India Pvt. Ltd.

## MPR 1.5 Proj engg under progres
Details of Project Engineer Engagement in various STP projects, NMCG (MPR 1.5 - JUNE 2026)
Sl No. | Name of the project | STP Capacity | Name of the Bidder | Last MPR approved by NMCG | Last MPR submitted by PE | Last Payment Made by NMCG | Last Invoice submitted by PE | Project Staus | Tentative Payment (Rs. In Cr)
1 | PE Digha & Kankarbagh STP Project | 150 MLD 50 MLD | M/s. Mahindra Consulting Engineers Ltd. (MACE) | 2025-12-01 | 2026-04-01 | 2025-06-01 | 2025-06-01 | Under Progress
2 | PE Bhagalpur STP Project | 40 MLD 5 MLD | M/s. Egis India Consulting Engineers Pvt. Ltd. | 2026-03-01 | 2026-04-01 | 2026-02-01 | 2026-02-01 | Under Progress
3 | PE Agra STP Project | 31 MLD 35 MLD 100 MLD | M/s. NJS Engineers India Pvt. Ltd. | 2026-04-01 | 2026-04-01 | 2026-02-01 | 2026-04-01 | Under Progress
4 | PE North Barrackpore STP project | 30 MLD 8 MLD | M/s. MaRS Planning & Engineering Services Pvt. Ltd. | 2025-09-01 | 2026-05-01 | 2026-02-01 | 2026-02-01 | Under Progress
5 | PE Meerut STP Project | 220 MLD | M/s. AECOM India Pvt. Ltd. In JV with M/s. PDCOR Limited | 2026-04-01 | 2026-04-01 | 2026-02-01 | 2026-04-01 | Under Progress
6 | PE Saharanpur STP Project | 135 MLD | M/s. MSV International Tech Private Limited in consortium with M/s. MSV international Inc. & M/s. BMRV Engineering Consultant LLP | 2025-05-01 | 2026-02-01 | 2025-05-01 | 2026-02-01 | Under Progress
7 | PE Garden Reach STP Project | 65 MLD | M/s. Fichtner Consulting Engineers (India) Pvt. Ltd. | 2026-04-01 | 2026-04-01 | 2026-02-01 | 2026-04-01 | Under Progress
8 | PE Gokul Barrage STP Project | 60 MLD | M/s. NJS Engineers India Pvt. Ltd. | 2026-04-01 | 2026-04-01 | 2026-02-01 | 2026-04-01 | Under Progress
9 | PE Dhanbad STP Project | 18 MLD 21 MLD 75 MLD 60 MLD 18 MLD | M/s. MSV International Tech Private Limited in consortium with M/s. MSV international Inc. & M/s. BMRV Engineering Consultant LLP |  |  | 2025-04-01 |  | Under Progress
10 | PE Lucknow STP Project | 100 MLD | M/s. Shah Technical Consultants Pvt. Ltd. | 2026-04-01 | 2026-04-01 | 2026-02-01 | 2026-02-01 | Under Progress
11 | Katihar | 55 MLD | [5 empty] | Under Tendering
12 | Aligarh | 113 MLD | [5 empty] | Under Tendering
13 | Siliguri | 49 MLD | [5 empty] | Under Tendering
14 | Moradabad | 80 MLD | [5 empty] | Under Tendering
15 | Durga Drain, Varanasi | 60 MLD | [5 empty] | Under Progress
16 | Pt. DDU Nagar, Chandauli | 45 MLD | [5 empty] | Under Progress
17 | Arrah | 47 MLD | [5 empty] | Under Tendering
Total
Details of Project Engineer in various CETP Projects, NMCG
Sl No. | Name of the project | CETP Capacity | Name of the Bidder
1 | Project Engineer Services for Implementation of 20 MLD Tannery CETP & associated components at Jajmau, Kanpur, Uttar Pradesh | 20 MLD | M/s. Tamil Nadu Water Investment Company Limted (TWIC)
2 | Project Engineer Services for the upgradation of 4.5 MLD CETP for Tanneries with Soak Stream Treatment, Common Chrome Recovery System, Composite Stream Treatment on ZLD Technology at Banthar, Unnao Uttar Pradesh | 4.5 MLD | M/s. NJS Engineers India Pvt. Ltd.

## MPR 1.4_KSDC
MPR 1.4
April 2026 - March 2027
For the month of June 2026
Knowledge-cum-Skill Development Centre (KSDC)
S.No | Activity | Till May, 2026 | June, 2026 | Total
1 | Web posts | 0 | 0 | 0
2 | Training/ Workshops | 0 | 2 | 2
3 | Seminar/ Webinar | 0 | 0 | 0
4 | Exposure Visits | 0 | 0 | 0
5 | URMP Related | 0 | 0 | 0
6 | Technical Support | 0 | 0 | 0
7 | Research/ Academic | 0 | 0 | 0
8 | Publications | 0 | 0 | 0
Annexure
List (Type 2,3,4,5) June 2026
S.No | Event Topic | Type | Venue | Date/Days/Duration | No. of Participants
List (Type 1,6) June 2026
| Sl. No. | Subject |  | Date
List (Type 7) June 2026
| Sl. No. | Subject |  | Date
1
2
3

## MPR 3.1 CPCB
MPR 3.1
(April 2025 - March 2026)
For the month of June, 2026
Technical Division / CPCB related
Sl. No. | Activity | Till Jun-26 | 2026-07-01
1 | STP Inspection Reports Received **
| Uttrakhand | Dec'25 - Mar'26 | -
| Uttar Pradesh | Dec'25 - Mar'26 | -
| Bihar | Dec'25 - Mar'26 | -
| Jharkhand | Dec'25 - Mar'26 | -
| West Bengal | Dec'25 - Mar'26 | -
2 | River water Quality Data Received *
| Uttrakhand | Oct'25- Dec'2025 | -
| Uttar Pradesh | Oct'25- Dec'2025 | -
| Bihar | Oct'25- Dec'2025 | -
| Jharkhand | Oct'25- Dec'2025 | -
| West Bengal | Oct'25- Dec'2025 | -
3 | GPI Inspection Report received *
| Target (8th Round - till 15th Jan2026) | Covered | Annexure A
| 3703 (Ganga: 1296; Yamuna: 2407) | 3703 | 3703
4 | River water Quality Data upload on GKC *
| Uttrakhand | Jan'25- Dec'2025 | -
| Uttar Pradesh | Jan'25- Dec'2025 | -
| Bihar | Jan'25- Dec'2025 | -
| Jharkhand | Jan'25- Dec'2025 | -
| West Bengal | Jan'25- Dec'2025 | -
5 | Number of Publications/Reports | 57 | 8
* Pls indicate period
** Pls indicate month
Annexure for S.No 5
S.No. | Name of Document | Date
1 | CPCB email on '163 Yamuna Drains Monitoring during Post Monsoon-2025' in four States (UK, UP, HP and Haryana) | 2026-06-30
2 | Status of Sewage Treatment Plant in Ganga Front Towns of Bihar | 2026-06-11
3 | Status of Sewage Treatment Plant in Ganga Front Towns of UP | 2026-06-11
4 | Status of Sewage Treatment Plant in Ganga Front Towns of West Bengal | 2026-06-11
5 | Status of Sewage Treatment Plant in Ganga Front Towns of Jharkhand | 2026-06-11
6 | Status of Sewage Treatment Plant in ganga Front Towns of Uttarakhand | 2026-06-03
7 | CPCB Report of 52 Yamuna Drains monitoring (May2025-Apr'2026) | 2026-06-16
8 | CPCB letter regarding continuation of 40RTWQMs Project after 19.06.2026 | 2026-06-02
Annexure A for S.No 3
| Total GPIs | 3703
| Inspected | 3703
| Complied | 2834 | << Total Action Completed Till date
| Non-Complied | 329 | << Total Action Completed Till date
| Temporary Closed | 429 | << Total Action Completed Till date
| Permanently Closed | 111 | << Total Action Completed Till date

## MPR 3.2_Regulatory Cell
MPR 3.2
(April 2026 - March 2027)
For the month of June (As on 30th June 26)
Technical Division / Regulatory Cell
A | Pending Applications
1 | Pending Application at the end of May 26 | 15
2 | Application returned back in June 26 | 5
3 | Applications decided in June 26 | 3
4 | New Applications received in June 26 | 5
5 | Pending Application at the end of June 26 | 12
6 | Out of S.No. 5, applications pending more than 3 months ( Received before 1st March 2026) | 1
(5)= (1)-(2)-(3)+(4)
B | Regulatory Cell meeting
Date | Meeting Number | Cases Considered | Cases Deferred/Return | Cases Recommended
2026-06-12 | 15 | 8 | 3 | a). 4 (NoC issued 3; NoC put up 1); b). 1 Decision pending for want of clarification
Annexure for A/S.No 6
S.No. | Subject | Applicant | Date | Status
1 | Construction of water intake structure for drawl of water from river Ganag at Mirzapur for meeting requirement of 2*800 MW Ultra Super Critical Thermal Power Project at Mirzapur, U.P. | Mirzapur Thermal Energy (UP) Pvt. Ltd. (Adani Group) | 2026-02-17 | Under examination

## MPR 4.1_E-file status
MPR 4.1
eOffice closed files summary
(With initial total number of eFiles =7,375 on 31st January 2026)
Period | No. of eFiles closed
From 1st April 2020 –till 25th Oct 2025 | 104
26th Oct 2025 – till 31st Oct 2025 | 48
1st November 2025 to 30th November 2025 | 299
1st December 2025 to 31st December 2025 | 1
1st January 2026 to 31st January 2026 | 69
1st February 2026 to 28th February 2026 | 1
1st March 2026 to 31st March 2026 | 0
1st April 2026 to 30th April 2026 | 1
1st May 2026 to 31st May 2026 | 2
1st June 2026 to 30th June 2026 | 2
Total | 527
Wing/Section/ Unit wise summary from 26th Oct 2025 till 30th November 2025
i. SMD Section: 271
ii. Finance Wing: 42
iii. Communication Wing: 21
iv. Admin Wing: 13
Total: 347
Wing/Section/ Unit wise summary from 1st December 2025 to 31st December 2025
i. SMD Section: 1
Wing/Section/ Unit wise summary from 1st January 2026 till 31st January 2026
i. SMD Section: 67
ii. O/o ED (Tech): 2
Wing/Section/ Unit wise summary from 1st February 2026 till 28th February 2026
i. O/o ED/ Finance: 01
Wing/Section/ Unit wise summary from 1st March 2026 till 31st March 2026
i. Nill
Wing/Section/ Unit wise summary from 1st April 2026 till 30th April 2026
i. Communication Wing: 1
Wing/Section/ Unit wise summary from 1st May 2026 till 31st May 2026
i. Communication Wing: 1
ii. O/o ED (Tech): 1
Wing/Section/ Unit wise summary from 1st June 2026 till 31st June 2026
iii. HR & Training: 1
iv. O/o ED (Tech): 1

## MPR 5.2_GKC
Monthly Progress Report- Gyanganga.ai (June 2026)
Generated on 1st July 2026
MPR 5.2
Sl. No. | Title | Till 31st May 2026 | 2026-06-01 | FY 2026-27 | Total (as on 30th June 2026)
1 | Total Number Document on GKP | 1404 | 4 | 37 | 1408
2 | Other Literature on River Ganga | 10342 | 19 | 45 | 10361
Categories-wise details of documents uploaded between 1st to 30th June 2026
Categories | Sub-categories | No. of documents
Publications |  | 0
Journals |  | 0
| Student Thesis Competition (STC) | 0
Articles |  | 0
Books |  | 0
Studies/ Reports |  | 4
Guidelines |  | 0
Misellaneous |  | 0
Ganga River (Main Stem)Water Quality Data |  | 0
Data Set | River Atlas | 0
| Ganga River (Main Stem) Water Quality Data (CPCB) | 0
Coffes Table Books |  | 0
River Series |  | 0
Maps |  | 0
Total |  | 4
Details of documents uploaded between 1st to 30th June 2026
S.No | Category | Subject | Organization
1 | Reports | Collaboration in Confidence: Building Quality Infrastructure for the Ganga River | Physikalisch-Technische Bundesanstalt (PTB)
2 | Reports | Ganga Water Quality Monitoring: Data Management Methodologies | Physikalisch-Technische Bundesanstalt (PTB)
3 | Reports | Socio Ecological Status of Gomti River for Conservation Planning | WII
4 | Reports | Survey of Drains in Ganga main-stem Districts of Uttar Pradesh (December 2025-May 2026) | NMCG

## MPR 5.3-Prayag status
MPR 5.3
(April 2026 - March 2027)
For the month of June (As on 1st July 2026)
MPR PRAYAG/ GeoPortal etc
A | OCEMS Status
1 | Installation and Data Status
a | No. of STPs with OCEMS Installed | 282
b | No. of STPs with Flow Data received | 203
c | No. of STPs with Influent Characteristic Data received | 181
d | No. of STPs with Effluent Characteristic Data received | 252
2 | Data Reliability Status
a | No. of STPs with Satisfactory Data received | 236
b | No. of STPs with Poor Data Quality (Annex A1) | 6
c | No. of STPs with No Data Received (Annex A2) | 25
B | OCEMS based results communicated to States till Month | Communicated till June 2026
C | Eflow reports updated till period | Updated till Oct-Dec 2025
D | GDPMS
| No. of Meetings held in June 2026 | 25
| No. of Meetings held in May 2026 | 98
E | PRAYAG_GEO Portal
| No. of Active GIS Layers (Annex B) | 29
| No. of Use Cases | 3
PRAYAG/ Geoportal-MPR June 2026 (Item 5.3, MPR)
Annexure - A1
No. of STPs with Poor Data Quality
S No. | STP Name | Data availability percentage
1 | 1.5 MLD STP Chutia | 4.71%
2 | 29 MLD STP Salori (UP Jal Nigam) | 8.19%
3 | 5 MLD STP SHUKLAGANJ | 22.16%
4 | 16 MLD STP Jhunsi | 29.2%
5 | 6.5 MLD STP Naihati | 37.18%
6 | 1.5 MLD STP Harmu | 38.69%
Annexure - A2
No. of STPs with No Data Received
S No. | STP Name | State
1 | 0.66 MGD Molar Band | Delhi
2 | 11.4 MLD STP Bokaro | Jharkhand
3 | 2.57 MLD STP Bokaro | Jharkhand
4 | 1 MLD STP ANUPSHAHAR | Uttar Pradesh
5 | 1.5 MLD STP Anupshahar (UPJN) | Uttar Pradesh
6 | 10.445 MLD STP Etawah | Uttar Pradesh
7 | 100 MLD STP at Noida Sector 168 | Uttar Pradesh
8 | 13.50 MLD STP Tixi Nala | Uttar Pradesh
9 | 14 MLD STP Baghpat | Uttar Pradesh
10 | 15 MLD STP Baniyapur UPJN | Uttar Pradesh
11 | 2.76 MLD STP Goverdhan | Uttar Pradesh
12 | 20 MLD CETP Jajmau | Uttar Pradesh
13 | 21 MLD STP ETAWAH | Uttar Pradesh
14 | 21 MLD STP Pakka Bagh | Uttar Pradesh
15 | 25 MLD STP sector 50 noida | Uttar Pradesh
16 | 30 MLD STP JAUNPUR | Uttar Pradesh
17 | 34 MLD STP sector 50 | Uttar Pradesh
18 | 40 MLD STP Mapan | Uttar Pradesh
19 | 43 MLD STP Salori | Uttar Pradesh
20 | 7 MLD STP Mirzapur | Uttar Pradesh
21 | 26.5 MLD STP at Chinsurah | West Bengal
22 | 35 MLD STP Maheshtala Waste Water Management Pvt Ltd | West Bengal
23 | 40 MLD STP at Bally Howarh | West Bengal
24 | 60 MLD STP Baranagar | West Bengal
25 | 65 MLD STP Arupara Howrah | West Bengal
Annexure-B
Active GIS layer - June 2026 (As on 01.07.2026)
S. No. | Type | GIS Layer
1 | BASIC | Ganga
2 |  | Ganga Centre line SoI
3 |  | Ganga River Basin
4 |  | Popular River
5 |  | Ganga State
6 |  | Ganga Basin Sub District Census
7 |  | Ganga Basin Town Census
8 |  | Census Sub District 2011
9 |  | Census Town 2011
10 | WATER RESOURCES | India River Network
11 |  | Major Aquifers
12 | ECOLOGY | Riverine Wetland (UP/Bihar/Jharkhand)
13 |  | Wetland PAN India (SAC)
14 | RIVER WATER QUALITY | Ganga Polluted Stretch, 2018
15 |  | Ganga Polluted Stretch, 2022
16 |  | Ganga Polluted Stretch, 2023
17 |  | Ganga Polluted Stretch, 2025
18 |  | Manual Water Quality Stations (Locations)
19 |  | RTQMS (Locations)
20 |  | Biomonitoring (Locations) (to be add)
21 | POLLUTION ASPECTS | Sewage Gap Analysis
22 |  | STP (Other than NMCG) (Locations)
23 |  | STP NMCG (Locations)
24 |  | GPIs (Locations)
25 |  | Solid Waste Dumps (IIRS data)
26 | MISC. | Ganga Centre line 1 km points SoI
27 |  | Ganga Final Survey SoI
28 |  | Point outfall 45N SoI
29 |  | Point outfall 44N SoI

## MPR 5.4-Jan Ganga Vertical_Comm
MPR 5.4
(April 2026 - March 2027)
For the Month of June 2026 (As on 1st July 2026)
MPR Communication
| Followers | Current Month (May 2026) | Current Month-June 2026
1 | Twitter | 123899 | 125552
| Facebook | 592956 | 622655
| Instagram | 131368 | 150296
2 | In Current Month
a) | Webposts (excluding B and C) | Number of Images | Videos (Minutes)
| Twitter | 260 | 43 | 70 Minutes
| Facebook | 260 | 43 | 70 Minutes
| Instagram | 150 | 55 | 80 Minutes
b) | Rebuttals on
| Social Media | Nil
c) | Positive Stories |  |  | Annex A
| Social Media | 32
3 | Youtube
4 | Print Media
a) | Rebutted | Nil
b) | Positive Stories | 11 |  | Annex A
5 | Publication through PIB
a) | Press Release ( Atleast One per month )
i) | Press Release-Event Based | 21st June -NMCG Organises International Day of Yoga 2026 Celebrations in New Delhi; Events Held Across Ganga Basin
ii) | Press Release- Success Story | 24th June -NMCG Scales Up Urban River Management Plans Across 63 Ganga Basin Cities
b) | Backgrounder ( One per Quarter ) | Under Submission
c) | Articles/Op-eds in Newspapers ( One article -Half Yearly) | Under Submission
|  | Number of Events | Participation
6 | Events Organised by NMCG |  |  | Annex B
i). | Cleanliness Drives on Yamuna | 4 | Approx. 2000
ii). | International Day of Yoga- Delhi Event | 1 | Approx. 650
7 | Events through Partner |  |  | Annex B
a) | DGC & SMCG
| World Environment Day | 639 | 62172
| Ek Ped Maa K Naam | 50 | 10400
| International Day of Yoga | 257 | 63003
b) | NGO | Nil | Nil
c) | Institutes | Nil | Nil
| Total | 946 | 135575
8 | Sponsorship | Aao Yamuna Sawaro' event organised by YPF | 500
9 | Capacity Building Training /Workshop (Communication Unit ) | Online Conference - AI , Media & Democracy
Annex B
| Annex A | S. No 2 C, 4 B | Coverage
S. No. | Title | Date | Twitter | Facebook | Instagram
1 | Ye kiya hai Namami Gange ne (Afforestation) | 2026-06-29 | https://x.com/cleanganganmcg/status/2071487677342564409?s=20 | https://www.facebook.com/share/r/1RZ5mLjkMK/ | https://www.instagram.com/reel/DaKSmi5geoS/?utm_source=ig_web_copy_link
2 | Public awarness | 2026-06-27 | https://x.com/cleanganganmcg/status/2070867490268422324?s=20 | https://fb.watch/I1PVUz90Ki/ | https://www.instagram.com/reel/DaF3YeOvoce/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
3 | Public review Kanpur | 2026-06-25 | https://x.com/cleanganganmcg/status/2070106893549547880?s=20 | https://fb.watch/I1Qrh-USio/ | https://www.instagram.com/reel/DaAdwQUAIY-/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
4 | Ye kiya hai Namami Gange ne (Fish ranching) | 2026-06-24 | https://x.com/cleanganganmcg/status/2069658709266161917?s=20 | https://fb.watch/HXdaFg6-Xr/ | https://www.instagram.com/reel/DZ9R7r-Mi9d/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
5 | Public review | 2026-06-23 | https://x.com/cleanganganmcg/status/2069309328641888430?s=20 | https://www.facebook.com/reel/1454537710034471 | https://www.instagram.com/reel/DZ6y5E8vO1G/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
6 | Ye kiya hai Namami Gange ne (Ganga prahari) | 2026-06-22 | https://x.com/cleanganganmcg/status/2069054045466079590?s=20 | https://facebook.com/reel/1556690389104739/ | https://www.instagram.com/reel/DZ4-zMvlTmE/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
7 | Volunteer story | 2026-06-22 | ________________ | https://www.facebook.com/reel/1361120735934561 | https://www.instagram.com/reel/DZ4lChUjkQo/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
8 | Yamuna cleanliness drive | 2026-06-20 | https://x.com/cleanganganmcg/status/2068199823975776258?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid02BMF5FkF71WYHMRCczCfpUdB5bUGhS6531nUbbWEjAtN5aXLwPWhyxruK1NhMTrgFl | https://www.instagram.com/p/DZy7Fd0DxgM/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
9 | Project update (12 years) | 2026-06-18 | https://x.com/cleanganganmcg/status/2067506606842183992?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid01BBXRxJxTabEV7ffrsPz4EX8HFkAYznE2bmepgNGGVNHF16a4XNdXRbcQN62Tn1nl | https://www.instagram.com/p/DZt_Wq7jB9a/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
10 | Ganga Biodiversity | 2026-06-18 | https://x.com/cleanganganmcg/status/2067607261992943920?s=20 | https://facebook.com/reel/1570902827757752/ | https://www.instagram.com/reel/DZutF06inbY/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
11 | Volunteer story | 2026-06-17 | https://x.com/cleanganganmcg/status/2067176627881316846?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid02xsqN63yp4F4pzPJmbDK5w8HkFjU5MTLkZKTzZ6kWEyDqvozJyJbS1dgkZKa16y24l | ___________________
12 | Three Crocodile, One District | 2026-06-17 | https://x.com/cleanganganmcg/status/2067194802316394843?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid02YJRZiqBNyaGWowVR6tvQjWBdPRQXv8o3tSVTjovcya1XhHXLZCDfUkFhfETxtAmtl | https://www.instagram.com/p/DZrxYStDPRH/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
13 | Project update (12 years) | 2026-06-16 | https://x.com/cleanganganmcg/status/2066753642871640332?s=2 | https://www.facebook.com/cleanganganmcg/posts/pfbid02SgKgffYLs642dDez8x5cpfqZaViD8btpTQzfNRECjRAH6FVDyPqtJrsLvCoidz3El | https://www.instagram.com/p/DZoo_uwMxdf/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
14 | Public review (12 saal) | 2026-06-15 | https://x.com/cleanganganmcg/status/2066510103629754467?s=20 | https://www.facebook.com/reel/1380754410541682 | https://www.instagram.com/reel/DZm6FZ5P0LO/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
15 | Project update (12 saal) | 2026-06-15 | https://x.com/cleanganganmcg/status/2066386554176839950?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid02sDsoXSWcAQetG5JXzTAyuvLDaVyCTyKkbURQdNvVdTcqBepTsWKeXTLNR1zk8fECl | https://www.instagram.com/p/DZmEjm_DID6/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
16 | Weekly Cleanloness Drive ( Smt. Rekha Gupta- CM Delhi) | 2026-06-14 | https://x.com/cleanganganmcg/status/2066103975599088122?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid02HdtvSTJaqTMWVDjPDAXabidNDzjtH7Dydc9aoCGC2ePcN4Zioorqes6j8mtAog3Bl | https://www.instagram.com/p/DZjpIEUjya3/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
17 | Public review (12 saal) | 2026-06-12 | https://x.com/cleanganganmcg/status/2065315662088880214?s=20 | https://www.facebook.com/reel/1484171289691336 | https://www.instagram.com/reel/DZeacTWDF1a/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
18 | Project update (12 saal) | 2026-06-12 | https://x.com/cleanganganmcg/status/2065301030854635785?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid0H5MPqHHucPzxw8JXLYjWMn3zdzZ5EAA9Y6TAMaRRaVr65nf2XBvks4WfupSQ7FrHl | https://www.instagram.com/p/DZeVhNtDNoT/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
19 | STP (12 saal) | 2026-06-11 | https://x.com/cleanganganmcg/status/2064936904379019410?s=20 | https://facebook.com/reel/1374443988067726/ | https://www.instagram.com/reel/DZbvSdtsy23/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
20 | Public review (12 saal) | 2026-06-10 | https://x.com/cleanganganmcg/status/2064610632343941293?s=20 | https://www.facebook.com/reel/4490476557908553 | https://www.instagram.com/reel/DZZaJNOlKkP/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
21 | Gandak Ghariyal | 2026-06-09 | https://x.com/cleanganganmcg/status/2064234061116395818?s=20 | https://www.facebook.com/reel/1468175338447804 | https://www.instagram.com/reel/DZWu606gCUa/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
22 | Public review (GVM) | 2026-06-09 | https://x.com/cleanganganmcg/status/2064220471336579434?s=20 | https://www.facebook.com/reel/858587860624902 | https://www.instagram.com/reel/DZWo5X2MH63/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
23 | Public review (12 saal) | 2026-06-09 | https://x.com/cleanganganmcg/status/2064381055650640246?s=20 | https://facebook.com/reel/2057221791880184/ | _____________________
24 | Project update | 2026-06-08 | https://x.com/cleanganganmcg/status/2063861744431509669?s=20 | https://facebook.com/reel/27395300233494314/ | https://www.instagram.com/reel/DZUBApqMbRp/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
25 | Volunteer story | 2026-06-07 | https://x.com/cleanganganmcg/status/2063591554414178424?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid0rko1VdsmCTy4XmGfLhjAr3jpWznYoBVUaXRtFLbYxY3TViFYnkVrhinJoJvNXkf4l | __________________
26 | Public review (12 saal) | 2026-06-04 | https://x.com/cleanganganmcg/status/2062475824201335015?s=20 | https://fb.watch/HXqB4AkLN7/ | https://www.instagram.com/reel/DZKPwQ-jx8F/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
27 | Project update (12 saal) | 2026-06-04 | https://x.com/cleanganganmcg/status/2062414329719480593?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid02pza8HUuSyPYrCTWXVwrCdLDjz9eYTjJ5TK3dnt9rWW5kajt3ZZDT4SyfyebkKciAl | https://www.instagram.com/p/DZJ1CIjMrsH/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
28 | Project update Uttarakhand | 2026-06-04 | https://x.com/cleanganganmcg/status/2062369114333827381?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid0YzHdMGCP6rQJow6MLUHJSjdJn3GXhmumNxkc2XArgMeM4AhenCWU6grX8ouynKepl | https://www.instagram.com/reel/DZJfucHPw3s/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
29 | Dolphin story | 2026-06-03 | https://x.com/cleanganganmcg/status/2062164904199569745?s=20 | https://facebook.com/reel/26954476417579402/ | https://www.instagram.com/reel/DZIB-uqCpe5/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
30 | Public review (Rajesh Shukla) | 2026-06-03 | https://x.com/cleanganganmcg/status/2062132478798864755?s=20 | https://facebook.com/reel/1470526654364570/ | https://www.instagram.com/reel/DZHzsEbAPwt/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
31 | Project Update | 2026-06-02 | https://x.com/cleanganganmcg/status/2061671145276154010?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid0Rwd5TeLdJZvzoDsYx2gmhVrYnKZM6JEy9nEs7QYf4r5fSL5JpQukgzmdxxw7iYcdl | https://www.instagram.com/p/DZEjJX4skZO/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
32 | 12 years of Namami Gange | 2026-06-01 | https://x.com/cleanganganmcg/status/2061415388882047318?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid0mZNexGonu8CtPfnp6LWFPKCgHrszJWduH7Po1nBFeAfrR7qqxNL1rg3RL3RPfF4ml | https://www.instagram.com/p/DZCuFVev_L4/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
33 | Bhagalpur's Enduring Commitment to Protecting the Ganga Dolphin | 5th June
34 | Jharkhand Sets a Benchmark with Seven Consecutive Pollution-Free Years for the Ganga | 5th June
35 | NMCG launces citizen guide to protect urban wetlands | 9th June
36 | Ganga Sees 60% Drop in Industrial Pollution Since 2017 | 10th June
37 | NMCG Approves ₹115 Crore to Ensure a Clean and Safe Haridwar Kumbh 2027 | 12th June
38 | NMCG's Ecological Revival Efforts Reflected in Record Gangetic Dolphin Count | 15th June
39 | NMCG Completes Drone Mapping of Drains from Gangotri to Gangasagar | 17th June
40 | Raj Bhushan Choudhary Highlights NMCG's Success Through Improved Water Quality and Rising Dolphin Numbers | 18th June
41 | NMCG Demonstrates Cleaner Ganga Through Scientific Monitoring | 19th June
42 | NMCG to Deploy Six Advanced FSTPs for a Cleaner Ardh Kumbh | 20th June
43 | NMCG Completes Urban River Management Plans for 13 Ganga Basin Cities | 25th June
44 | NMCG Organises International Day of Yoga 2026 Celebrations in New Delhi; Events Held Across Ganga Basin | 21st June | https://www.pib.gov.in/PressReleasePage.aspx?PRID=2276309&reg=48&lang=1 | PIB Release
45 | NMCG Scales Up Urban River Management Plans Across 63 Ganga Basin Cities | 24th June | https://www.pib.gov.in/PressReleasePage.aspx?PRID=2277477&v=6&reg=48&lang=2 | PIB Release
| Annex B | S. No 5,6,7
S. No. | Event Name (Activity Type) | Agency | Date | Venue | Participants
1 | Cleanliness Drives on Yamuna | NMCG with NGOs (Delhi) | Every Sunday | Soor Ghat, Wazirabad; Geeta Colony; Sonia Vihar 2.5 Pushta; Geeta Colony Thokar 1.7 | NGOs- Saksham Bhoomi Foundation, Yuva Parivartan Foundation, Friends of Yamuna Swachh Yamuna Abhiyaan; Schools, Colleges, Youth Groups, NGOs and Yamuna Task Force etc.
2 | International Day of Yoga- Delhi | NMCG | 21.06.2026 | District Park, Hauz Khas, Delhi | Ministry of Jal Shakti and allied departments, partner organisations, NGOs, Ganga Task Force, School/College students
3 | Aao Yamuna Sawaro | YPF | 7.06.2026 | Zero Pushta , Sonia Vihar , delhi | Kyaking Sports Trainees, Students , Local Community , YTF , NGOs
UTTARAKHAND
4 | World Environment Day | SMCG, DGCs (13) and academic institutions (Govt. PG Collges & Universities-20) | 01 to 07.06.2026 | Different places | Students, Youth Groups, Volunteers & Local Communities
5 | Ek Ped Maa Ke Naam | DGCs (13), Colleges & Universities | 05.06.2026 | different places, areas designated by ditsrict forest areas, schools, colleges, community parks and other strategic places | District Forest Dept., NGOs, Students, Youth Groups, Volunteers & Local Communities
6 | International Day of Yoga | DGCs (11), academic institutions, youth groups, NGOs | 21.06.2026 | Ganga Ghats, near riverbanks, schools & college premises, community halls and other strategic places | College Students, Teachers & Volunteers and local communities
UTTAR PRADESH
7 | World Environment Day | SMCG, DGCs (67) and academic institutions | 05.06.2026 | different places (indoor/outside venues, academic institutions, Ghats) | School/College Students, Youth, Volunteers, NGOs & local communities
8 | Ek Ped Maa Ke Naam | DGC (48) & Forest Department, academic institutions, community based organisations | 05.06.2026 | various locations, areas designated by ditsrict forest areas, schools, colleges, community parks and other strategic places | Forest Departments, School/College Students, Teachers, Youth Groups, Volunteers & Local Communities
9 | International Day of Yoga | DGCs (67), academic institutions, youth groups, NGOs | 21.06.2026 | Ganga Ghats, near riverbanks, schools & college premises, community halls and other strategic places | School/ College Students, Youth Groups, Volunteers, NGOs & Local Communities
10 | 1 Hour Shramdan Drive | DGC-Rampur, NGOs, Schools/Colleges | Every Sunday | Rampur (Group Centre-CRPF, Patwai Talab and Kosi Ghat) | School/College Students, Youth, Volunteers, NGO representatives & local communities
BIHAR
11 | World Environment Day | DGCs, Nagar Parishad & academic institutions | 05.06.2026 | different places (indoor/outside venues, academic institutions, Ghats) | School & College Students, Teachers, Youth Groups, Volunteers, NGOs & Local Communities
12 | Ek Ped Maa Ke Naam | DGCs, Nagar Parishad, Forest departments academic institutions | 05.06.2026 | different places, areas designated by ditsrict forest areas, schools, colleges, community parks and other strategic places | Forest Department, DGC, School & College Students, Youth Groups, Volunteers, NGOs & Local Communities
13 | International Day of Yoga | DGCs and academic institutions | 21.06.2026 | Ganga Ghats, near riverbanks, schools & college premises, community halls and other strategic places | School & College Students, Teachers, Youth Groups, Religious Groups, Volunteers, NGOs & Local Communities
JHARKHAND
14 | World Environment Day | DGCs (4 DGCs & 2 Cities)- Dhanbad, Sahibganj, Ramgarh, Bokaro & Chatra, Nagar Parishad, Education Department, Self Help Groups, Schools/Colleges | 05.06.2026 | various schools/colleges, community & market areas and key locations | School/College Students, Teachers, SHGs, Youth, Volunteers, NGOs & local communities
15 | Ek Ped Maa Ke Naam | DGCs (4 DGCs & 2 Cities)- Dhanbad, Sahibganj, Ramgarh, Bokaro & Chatra, Nagar Parishad, Forest Department, Schools/Colleges, NGOs and volunteers | 05.06.2026 | school/college premises, forest areas, nursuries, public parks and other locations | School & College Students, Teachers, Youth Groups, Volunteers, NGOs & Local Communities
16 | International Day of Yoga | DGCs and academic institutions | 21.06.2026 | Ganga Ghats, river banks, auditorium, indoor/outside premises and other key locations | School/ College Students, Youth Groups, Volunteers, NGOs & Local Communities
WEST BENGAL
17 | World Environment Day | DGCs (9), KMC Kolkata, Forest Departments and other organisations & institutions | 05.06.2026 | Durgakinkar Sada Auditorium, Malda College, English Bazar Municipal Area (Malda), Laldighi , Sahanagar Ganga Ghat, Kanchantala Ganga Ghat, Jangirpur & Azimganj Municipal Area (Berhampore, Murshidabad), Kalna Hibdu Girls (Purba Bardhaman), Gabtala Math (Nadia), Telinipara Girls High School, Sarada Pally Kanya Vidyapith (Hooghly), B ally Rabindra Bhavan (Howrah) and other municipal areas, schools and Ghats | District Administration, Municipal corporations, Block Representatives, SHG Members, Teachers, NCC/NSS, School & College Students, Environment experts, youth groups, panchayat officials, NGOs.
18 | Ek Ped Maa Ke Naam | DGCs (9), KMC Kolkata, Forest Departments and other organisations & institutions | 05.06.2026 | Mukta manchan area, college premises (Malda), Laldighi, Sahanagar Ganga Ghat, Kanchantala Ganga Ghat, Jangirpur, Azimganj Municipal Area, Anupnagar BPHC Ground (Murshidabad),Kalna Hindu Girls School (Purba Bardhman), Kukrahati Ferry Ghat, Bipin Behari Ganguly Park (Halishahr), Kalidas Sarkar Ghat (Kolkata), schools/colleges, villages & gram panchayats, forest areas and other strategic locations | District Administration, Forest Departments, Municipal corporations, Block Representatives, SHG Members, NCC/NSS, School & College Students, youth groups, panchayat officials, NGOs.
19 | International Day of Yoga | DGC (9), KMD, KMDA, NGOS, Shool/Colleges | 21.06.2026 | Ganga Ghats- Sarkar Tola Ghat (Malda), Gouripur Malopara, Bagsipara Ganga Ghat (Murshidabad), Katwa Mora Ghat (Purba Bardhman), Mahishadal Rajbari Ground & Geonkhali River Side (Purba Medinipur); ISKCON premises, Nadia (Nabadwip), Ganga Ghat Mithapukar (Hooghly), Rajgunj Ghat (Howrah), Gandhi Ghat (Barrackpore), Duttbari, Shyamsundarpur (South 24 Parganas), Rabindra Sarobar, Subhas sarobar and Unnayan Bhawan (Kolkata) and other strategic locations | Block Administration, panchyat representatioves, local leaders, VBDC workers, SHGs, religious leaders, school/college students, NGOs, women & youth volunteers etc.

## MPR 5.5 RCA
MPR 5.5
(April 2025 - March 2026)
For the month of JUNE 2026
Organisation: River Cities Alliance
Sl. No. | Activity | Till May 2026 | 2026-06-26 | Total
1 | Web posts | 91 | 9 | 100
2 | Workshops (excluding 5b /URMP Workshops) | 19 | 0 | 19
3 | Seminar/ Webinar/Meetings | 44 | 4 | 48
4 | Exposure Visits | 2 | 0 | 2
5 | URMP Related (Non Ganga Basin)
| a) Meetings in States | 7 | 0 | 7
| b) Workshops in States | 2 | 0 | 2
6 | Publications
| a) Newsletter | 5 | 0 | 5
| b) Others | 23 | 0 | 23
7 | Concept Notes | 9 | 0 | 9
8 | Demands Received
| a) Cities | 14 | 3 | 14
| b) Academia | 7 | 0 | 7
Annexures
List (Type 2,3,4,5) March
Sl. No. | Event Topic | Type | Venue | Date/Days /Duration | Number of Participants
1 | Webinar on 'Solid waste management rules' | 3 | Online | 5.06.2026 | 82
2 | Webinar on 'Next Gen Rivers : Youth Leadership in Urban Water Care' | 3 | Online | 12.06.2026 | 50
3 | Webinar on 'Data - Driven Decision Making for Sustainable River Management' ' | 3 | Online | 19.06.2026 | 56
4 | Meeting with Mahestala Municipality | 3 | Online | 10.06.2026 | 4
List (Type 1,6) March
Sl. No. | Subject | Type | Date
1 | Inspirational Monday Series on "Use of treated used water for irrigation in Gwalior " | 1 | 01.06.2026
2 | Quiz series 17: Rivers, Cities, and Answers | 1 | 03.06.2026
3 | Inspirational Monday Series on "Dumas Sea Wall, Surat " | 1 | 08.06.2026
4 | Quiz series 18: Rivers, Cities, and Answers | 1 | 10.06.2026
5 | Inspirational Monday Series on "Chauka System in Rajasthan" | 1 | 15.06.2026
6 | Quiz series 19: Rivers, Cities, and Answers | 1 | 18.06.2026
7 | Inspirational Monday Series on "Anandvan Urban Forests Initiative, Pune " | 1 | 22.06.2026
8 | Quiz series 20: Rivers, Cities, and Answers | 1 | 24.06.2026
9 | Inspirational Monday Series on "Observatory Wetland Restoration Project, Capetown, South Africa" | 1 | 29.06.2026
List (Type 7) March
Sl. No. | Subject | Type | Date
Demands for RCA (Type 8) March
Sl. No. | Subject | Type | Date
1 | RCA Follow Up visit to Jhansi | 8a | 03.06.2026 - 04.06.2026
2 | Visit to Dadra & Nagar Haveli and Daman & Diu for IUWMP | 8a | 29.06.2026 - 01.07.2026
3 | Request from Maheshtala Municipality | 8a | 10.06.2026

## MPR 5.6 COE-IT BHU
MPR 5.6
(April 2026 - March 2027)
For the month of June
Smart Laboratory on Clean Rivers (MPR 5.6a)
Sl. No. | Activity | Till May-26 (A) | Jun-26 (B) | Total (A+B) | FY 26-27
1 | Workshops / Conference - Organised | 5 | 2 | 7 | 2
2 | Capacity Building Workshops - Organised | 5 | 1 | 6 | 2
3 | Publications | 0 | 0 | 0 | 0
4 | STP Performance Evaluation (Number of STPs) | 10 | 2 | 12 | 5
5 | DSS Project (Physical progress %) | 67% | 3% | 70% | 10%
5a | No. Draft Modules Finalized | 10 | 0 | 10 | 0
6 | Characterisation of Emerging Pollutants (Physical progress %) | 64% | 1% | 65% | 2%
6a | No. of Draft SOPs Finalized | 5 | 0 | 5 | 0
7 | Hydrogeological Model of Varuna Basin for MAR sites (Physical progress %) | 65% | 5% | 70% | 9%
7a | No. of Sites implemented | 0 | 0 | 0 | 0
Annexure
List (Type 1, 2)
Sl. No. | Event Topic | Type | Venue | Date/ Days/ Duration | Number of Participants
1 | World Environment Day (Inspired by Nature, for climate, for our future) | Type 1 | Geoinformatics Lab, IIT (BHU) | 05.06.2026 (1 Day) | 51
2 | River Water Quality Sampling, Parameters and Advanced Research | Type 1 | Seminar Hall, IIT (BHU) | 24.06.2026 (1 Day) | 30
3 | Application of SCALGO Live for Climate-Resilient Planning and Water Resources Management | Type 2 | Seminar Hall, IIT (BHU) | 25.06.2026 (1 Day) | 65
List (Type 3)
Sl. No. | Name of Publication | Date | Submitted
List (Type 4)
Sl. No. | Name of STP | Date visited | Report submitted
1 | Muni ki Reti, Rishikesh, Uttrakhand STP | 18.06.26 | -
2 | Lakkarghat, Rishikesh, Uttrakhand STP | 18.06.26 | -
List (Type 5, 6, 7,)
Sl. No. | Project Details | Type | Activities
1 | DSS Project | Type 5 | The revised framework of the DSS, along with the dedicated workspace management system, has been successfully developed. The individual modules are currently undergoing testing and integration within the updated DSS framework to ensure seamless functionality in this new system. In parallel, work is underway to enhance the DSS report generation process and ensure smooth end-to-end integration of all system components.
2 | Characterisation of Emerging Pollutants | Type 6 | The samples from Varuna River Basin are going through data acquisition process. SOPs for Carbamazepine, Trimethoprim, and Celecoxib are going through drafting finalization. The emerging contaminant remediation is ongoing with the help of the synthesized and characterized sewage sludge-based material.
3 | Hydrogeological Model of Varuna Basin for MAR sites | Type 7 | Conducting high-resolution sTEM surveys for groundwater model development and TEM surveys in the dry channel bed to assess and identify the suitable dredging depth.
List (Type 5a, 6a, 7a)
Sl. No. | Draft Finalized | Type | Comments
1 | SOPs for Carbamazepine, Trimethoprim and Celecoxib | Type 6a | Drafting of SOPs for Carbamazepine,Trimethoprim and Celecoxib is being finalized.
2 | Two sites for MAR structures at Rameshwar & Isharwar | Type 7a | The tender has been finalized, and issuance of the work award is under administrative process.
3
4
5

## MPR 5.6 COE-IIT Delhi
MPR 5.6 (b)
(April 2025 - June 2026)
For the month of June
India-Netherlands Centre of Excellence on Water (MPR 5.6b)
Sl. No. | Activity | Till May-26 | 2026-06-01
1 | Workshops / Conference Organised | 9 | 0
2 | Capacity Building Workshops | 0 | 0
3 | Publications | 2 | 0
4 | STP Performance Evaluation (No of STPs) | 1 | 1
5 | Digital Twin project | 0 | 0
6 | Web Posts | 91 | 8
7 | Outreach | 2 | 2
Note | Digital Twin project not started. Amended AA&ES awaited.
Annexure
List (Type 1,2)
Sl. No. | Event Topic | Type | Venue | Number of Participants
List (Type 3)
Sl. No. | Title | Date of Submission
List (Type 4)
Sl. No. | Name of STP | Date Visited | Report submitted
1 | Field Visit to 1MLD Capacity Sewage Treatment Plant (STP) in Gangotri | 2026-02-06 | Due in July
List (Type 5)
Sl. No. | Details | Remarks
List (Type 7)
Sl. No. | Topic | Category
1 | “National Workshop on R&D in Water” organised by the Ministry of Jal Shakti, Department of Water Resources, RD & GR, Govt. of India | 7
2 | 3rd Indo-French Biodiversity Talks on Nature-Based Solutions for Integrated Resilient Ecoscapes, jointly organised by Agence Française de Développement (AFD) and WWF-India | 7