## MPR 1.3_Project_COD effective
(April 2026 - March 2027)
For the month (As on 10th June 2026)
MPR Project Wing/Projects under progress
A. Under Progress - Sewage inflow to STP started- under trial operations; COD to be Declared
Sl. No. | Project | HAM/DBOT | Total Sanctioned Cost(Cr) | STP Capacity - New (MLD) | Date of start of trial operation | Reasons for delay in COD declaration
1 | I&D and STP at Unnao | HAM | 102.2 | 15 | 2023-11-07 | Trunk sewer along the original alignment has settled. Repair of the same is in progress.
2 | Pollution Abatement works for River Ganga at Hooghly Chinsurah | DBOT | 161.99 | 26.5 | Work yet to be completed | The STP is operational with partial flow. The remaining work of the I&D sewer line could not be completed earlier as open-cut excavation was not feasible. Now, under the approved variation, the balance work will be completed through trenchless pipeline laying.
3 | I&D and STP at Digha | HAM | 824 | 100 | 2025-03-01 | CoD will be declared after the completion of the trial run and successful achievement of the KPIs. NMCG's approval for declaration of Partial COD sent on 09.06.2026.
4 | I&D and STP at Kankarbagh | HAM | 578.89 | 50 | 2025-03-01 | CoD will be declared after the completion of the trial run and successful achievement of the KPIs. NMCG's approval for declaration of Partial COD sent on 09.06.2026.
5 | I&D and STP at Moradabad | HAM | 149.23 | 25 | 2025-07-01 | COD declared - 04/03/2026
6 | I&D and STP at Jangipur | DBOT | 68.47 | 13 | 2025-06-01 | Under trial run and successful achievement of the KPIs.
7 | I & D and STP at Kota | DBOT | 258.48 | 36 | Work yet to be completed | The STP is operational from Dec-2022
8 | I&D and STP at Lucknow | DBOT | 240.93 | 42.5 | 2024-09-01 | 3.5 MLD under progress (39 MLD operational)
9 | I&D and STP at Howrah, Bally and Kamrahati & Baranagar | HAM | 595.72 | 187 |  | Partial COD declared
10 | I&D with STP works at Sapera Basti, Dehradun | DBOT | 78.99 | 15 |  | Under trial operations
11 | I & D and STP works at Muni ki reti, Neelkanth, Swarg aashram | DBOT | 94.06 | 12.8 |  | Under trial operations (Muni-Ki-Reti and Swargashram) Under Construction (Neelkanth)
12 | Interception and diversion of balance discharge of 13 drains and augmentation of Salori STP | DBOT | 331.75 | 43 |  | Under trial operations
13 | I&D and STP Works at Vrindavan | DBOT | 77.7 | 13 |  | Under trial operations
14 | I&D and STP Works for Assi-BHU Area (Phase II), Varanasi, Uttar Pradesh’ under Namami Gange Programme | DBOT | 308.09 | 55 |  | Completed. O&M Start Date - 17/03/2026
15 | I & D and STP Project at Phusro | DBOT | 61.05 | 14 | 10 MLD - Trial started on 15th Jan 2026. 4 MLD- Trial run started on 16th Feb 2026
16 | Interception and Diversion with STP) at Chakdah Municipal Town | DBOT | 121.66 | 15 | trial run started on 14th Feb 2026.
17 | Pollution Abatement Works for River Ganga at North Barrackpore municipality | HAM | 154.27 | 38 | 30 MLD- under trial run since 15.12.2025. | COD for 30 MLD STP declared as 25.03.2026
B. Under Progress - Effective Date to be declared
Sl. No. | Project | HAM/DBOT | Total Sanctioned Cost(Cr) | STP Capacity - New (MLD) | Date of award of LOA | Reasons for delay in Effective date declaration
1 | Interception & Diversion and STP works at Lucknow, Phase-II Part-II | HAM | 351.03 | 100 | 02-06-2025 (Concession Agreement executed on 26/08/2025) | Effective Date declared as 23/06/2026
2 | I & D and STP at Dhanbad | HAM | 808.33 | 192 | Effective date for STP-1 ,2&3 has been declared as 02.03.2026. | Due to pending land NOC the effective date for remaining STPs (STP-4 &5) is yet to be declared.

## MPR 1.5 Project Engg O&M
Details of Project Engineer Engagement in various STP projects, NMCG
Sl No. | Name of the project | STP Capacity | Name of the Bidder | Last MPR approved by NMCG | Last MPR submitted by PE | Last Payment Made by NMCG | Last Invoice submitted by PE | Project Staus | Tentative Payment (Rs. In Cr)
1 | PE Haridwar STP Project | 68 MLD | M/s. Shah Technical Consultants Pvt. Ltd. | PE contract Completed |  |  |  | O&M
2 | PE Varanasi STP Project | 50 MLD | M/s. Mahindra Consulting Engineers Ltd. (MACE) | PE contract Completed |  |  |  | O&M
3 | PE Mathura STP Project | 30 MLD | M/s. Mahindra Consulting Engineers Ltd. (MACE) | PE contract Completed |  |  |  | O&M
4 | PE Prayagraj STP project | 14 MLD 42 MLD 16 MLD | M/s. AECOM India Pvt. Ltd. In JV with URS Scott Wilson India Consortium | Nov-24 | 2025-03-01 | 2024-08-01 | Mar-25 | O&M | 0.4
5 | PE Kanpur STP project | 30 MLD 15 MLD 5 MLD | M/s. Shah Technical Consultants Pvt. Ltd. | 2026-04-01 | 2026-04-01 | Mar-25 | Mar-25 | O&M
6 | PE Howrah, Bally & Baranagar | 65 MLD 40 MLD 60 MLD | M/s. HaskoningDHV Consulting Pvt. Ltd. In JV with HaskoningDHV Nederland B.V | 2025-12-01 | 2025-12-01 | Dec-25 | Dec-25 | O&M
7 | PE Budhana Muzaffarnagar STP Project | 10 MLD 22 MLD | M/s. Egis India Consulting Engineers Pvt. Ltd. | Jun-25 | Jun-25 | 2024-06-01 | Sep-25 | O&M
8 | PE Moradabad STP Project | 25 MLD |  | 2026-02-01 | 2026-04-01 |  | Jan-25 | O&M
9 | PE Mirzapur Ghazipur | 8.5 MLD 8.5 MLD 21 MLD | M/s. NJS Engineers India Pvt. Ltd. | 2026-04-01 | 2026-04-01 | 2025-12-01 | Apr-26 | O&M
10 | PE Maheshtala STP | 35 MLD | M/s. WAPCOS Limted | 2026-04-01 | 2026-04-01 | Aug-25 | Aug-25 | O&M
11 | PE Bareilly | 42 MLD 20 MLD 1 MLD | M/s. HaskoningDHV Consulting Pvt. Ltd. In JV with HaskoningDHV Nederland B.V | PE contract Completed |  |  |  | O&M
12 | PE Ayodhya | 32 MLD |  | PE contract Completed |  |  |  | O&M
13 | PE Farrukhabad-Fatehgarh | 30 MLD 20 MLD 2 MLD |  | PE contract Completed |  |  |  | O&M
Details of Project Engineer in various CETP Projects, NMCG
Sl No. | Name of the project | CETP Capacity | Name of the Bidder
1 | Project Engineer Services for Implementation of 20 MLD Tannery CETP & associated components at Jajmau, Kanpur, Uttar Pradesh | 20 MLD | M/s. Tamil Nadu Water Investment Company Limted (TWIC)
2 | Project Engineer Services for the upgradation of 4.5 MLD CETP for Tanneries with Soak Stream Treatment, Common Chrome Recovery System, Composite Stream Treatment on ZLD Technology at Banthar, Unnao Uttar Pradesh | 4.5 MLD | M/s. NJS Engineers India Pvt. Ltd.

## MPR 1.5 Proj engg under progres
Details of Project Engineer Engagement in various STP projects, NMCG
Sl No. | Name of the project | STP Capacity | Name of the Bidder | Last MPR approved by NMCG | Last MPR submitted by PE | Last Payment Made by NMCG | Last Invoice submitted by PE | Project Staus | Tentative Payment (Rs. In Cr)
1 | PE Digha & Kankarbagh STP Project | 150 MLD 50 MLD | M/s. Mahindra Consulting Engineers Ltd. (MACE) | 2025-12-01 | 2026-04-01 | 2025-06-01 | 2025-06-01 | Under Progress
2 | PE Bhagalpur STP Project | 40 MLD 5 MLD | M/s. Egis India Consulting Engineers Pvt. Ltd. | 2026-03-01 | 2026-04-01 | 2026-02-01 | 2026-02-01 | Under Progress
3 | PE Agra STP Project | 31 MLD 35 MLD 100 MLD | M/s. NJS Engineers India Pvt. Ltd. | 2026-04-01 | 2026-04-01 | 2026-02-01 | 2026-04-01 | Under Progress
4 | PE North Barrackpore STP project | 30 MLD 8 MLD | M/s. MaRS Planning & Engineering Services Pvt. Ltd. | 2025-09-01 | 2026-05-01 | 2026-02-01 | 2026-02-01 | Under Progress
5 | PE Meerut STP Project | 220 MLD | M/s. AECOM India Pvt. Ltd. In JV with M/s. PDCOR Limited | 2026-04-01 | 2026-04-01 | 2026-02-01 | 2026-04-01 | Under Progress
6 | PE Saharanpur STP Project | 135 MLD | M/s. MSV International Tech Private Limited in consortium with M/s. MSV international Inc. & M/s. BMRV Engineering Consultant LLP | 2025-05-01 | 2026-02-01 | 2025-05-01 | 2026-02-01 | Under Progress
7 | PE Garden Reach STP Project | 65 MLD | M/s. Fichtner Consulting Engineers (India) Pvt. Ltd. | 2026-04-01 | 2026-04-01 | 2026-02-01 | 2026-04-01 | Under Progress
8 | PE Gokul Barrage STP Project | 60 MLD | M/s. NJS Engineers India Pvt. Ltd. | 2026-04-01 | 2026-04-01 | 2026-02-01 | 2026-04-01 | Under Progress
9 | PE Dhanbad STP Project | 18 MLD 21 MLD 75 MLD 60 MLD 18 MLD | M/s. MSV International Tech Private Limited in consortium with M/s. MSV international Inc. & M/s. BMRV Engineering Consultant LLP |  |  | 2025-04-01 |  | Under Progress
10 | PE Lucknow STP Project | 100 MLD | M/s. Shah Technical Consultants Pvt. Ltd. | 2026-04-01 | 2026-04-01 | 2026-02-01 | 2026-02-01 | Under Progress
11 | Katihar | 55 MLD | [5 empty] | Under Tendering
12 | Aligarh | 113 MLD | [5 empty] | Under Tendering
13 | Siliguri | 49 MLD | [5 empty] | Under Tendering
14 | Moradabad | 80 MLD | [5 empty] | Under Tendering
15 | Durga Drain, Varanasi | 60 MLD | [5 empty] | Under Tendering
16 | Pt. DDU Nagar, Chandauli | 45 MLD | [5 empty] | Under Tendering
17 | Arrah | 47 MLD | [5 empty] | Under Tendering
Details of Project Engineer in various CETP Projects, NMCG
Sl No. | Name of the project | CETP Capacity | Name of the Bidder
1 | Project Engineer Services for Implementation of 20 MLD Tannery CETP & associated components at Jajmau, Kanpur, Uttar Pradesh | 20 MLD | M/s. Tamil Nadu Water Investment Company Limted (TWIC)
2 | Project Engineer Services for the upgradation of 4.5 MLD CETP for Tanneries with Soak Stream Treatment, Common Chrome Recovery System, Composite Stream Treatment on ZLD Technology at Banthar, Unnao Uttar Pradesh | 4.5 MLD | M/s. NJS Engineers India Pvt. Ltd.

## MPR 1.4_KSDC
April 2026 - March 2027
For the month of May
Knowledge-cum-Skill Development Centre (KSDC)
S.No | Activity | April, 2026 | May, 2026 | Total
1 | Web posts | 0 | 0 | 0
2 | Training/ Workshops | 0 | 0 | 0
3 | Seminar/ Webinar | 0 | 0 | 0
4 | Exposure Visits | 0 | 0 | 0
5 | URMP Related | 0 | 0 | 0
6 | Technical Support | 0 | 0 | 0
7 | Research/ Academic | 0 | 0 | 0
8 | Publications | 0 | 0 | 0
Annexure
List (Type 2,3,4,5) May
S.No | Event Topic | Type | Venue | Date/Days/Duration | No. of Participants
List (Type 1,6) May
| Sl. No. | Subject |  | Date
List (Type 7) May
| Sl. No. | Subject |  | Date
1
2
3

## MPR 3.1 CPCB
(April 2025 - March 2026)
For the month of May, 2026
Technical Division / CPCB related
Sl. No. | Activity | Till Apr-26 | 2026-05-01
1 | STP Inspection Reports Received **
| Uttrakhand | Aug'25 - Nov'25 | Dec'25 - Mar'26
| Uttar Pradesh | Aug'25 - Nov'25 | -
| Bihar | Aug'25 - Nov'25 | Dec'25 - Mar'26
| Jharkhand | Aug'25 - Nov'25 | Dec'25 - Mar'26
| West Bengal | Aug'25 - Nov'25 | -
2 | River water Quality Data Received *
| Uttrakhand | Oct'25- Dec'2025 | -
| Uttar Pradesh | Oct'25- Dec'2025 | -
| Bihar | Oct'25- Dec'2025 | -
| Jharkhand | Oct'25- Dec'2025 | -
| West Bengal | Oct'25- Dec'2025 | -
3 | GPI Inspection Report received *
| Target (8th Round - till 15th Jan2026) | Covered | Annexure A
| 3703 (Ganga: 1296; Yamuna: 2407) | 3703 | 3703
4 | River water Quality Data upload on GKC *
| Uttrakhand | Jan'25- Dec'2025 | -
| Uttar Pradesh | Jan'25- Dec'2025 | -
| Bihar | Jan'25- Dec'2025 | -
| Jharkhand | Jan'25- Dec'2025 | -
| West Bengal | Jan'25- Dec'2025 | -
5 | Number of Publications/Reports | 50 | 7
* Pls indicate period
** Pls indicate month
Annexure for S.No 5
S.No. | Name of Document | Date
1 | CPCB email on 'Continuation of 40RTWQMs Project beyond 19.06.2026' | 2026-05-29
2 | Status of Sewage Treatment Plant in Ganga Front Towns of Bihar | 2026-05-27
3 | CPCB directions US 5 of E (P) Act, 1986 to M/s Islam Leather Finishers, JajMau, Kanpur | 2026-05-27
4 | Status of Sewage Treatment Plant in ganga Front Towns of Jharkhand | 2026-05-20
5 | Tentative List of STPs of Yamuna basin | 2026-05-20
6 | Status of Sewage Treatment Plant in ganga Front Towns of Uttarakhand | 2026-05-16
7 | CPCB Report of 52 Yamuna Drains monitoring (May2025-Mar'2026) | 2026-05-16
Annexure A for S.No 3
| Total GPIs | 3703
| Inspected | 3703
| Complied | 2727 | << Total Action Completed Till date
| Non-Complied | 436 | << Total Action Completed Till date
| Temporary Closed | 432 | << Total Action Completed Till date
| Permanently Closed | 108 | << Total Action Completed Till date

## MPR 3.2_Regulatory Cell
(April 2026 - March 2027)
For the month of May (As on 31st May 26)
Technical Division / Regulatory Cell
A | Pending Applications
1 | Pending Application at the end of April 26 | 15
2 | Application returned back in May 26 | 7
3 | Applications decided in May 26 | 2
4 | New Applications received in May 26 | 9
5 | Pending Application at the end of May 26 | 15
6 | Out of S.No. 5, applications pending more than 3 months ( Received before 1st Feb 2026) | 0
5= 1-2-3+4
B | Regulatory Cell meeting
Date | Meeting Number | Cases Considered | Cases Deferred/Return | Cases Recommended
00-00-0000 | 0 | 0 | 0 | 0
Annexure for A/S.No 6
S.No. | Subject | Applicant | Date | Status

## MPR 4.1_E-file status
eOffice closed files summary
(With initial total number of eFiles =7,375 on 31st January 2026)
Period | No. of eFiles closed
From 1st April 2020 –till 25th Oct 2025 | 104
26th Oct 2025 – till 31st Oct 2025 | 48
1st November 2025 to 30th November 2025 | 299
1st December 2025 to 31st December 2025 | 1
1st January 2026 to 31st January 2026 | 69
1st February 2026 to 28th February 2026 | 1
1st March 2026 to 31st March 2026 | 0
1st April 2026 to 30th April 2026 | 1
1st May 2026 to 31st May 2026 | 2
Total | 525
· Wing/Section/ Unit wise summary from 26th Oct 2025 till 30th November 2025
i. SMD Section: 271
ii. Finance Wing: 42
iii. Communication Wing: 21
iv. Admin Wing: 13
Total: 347
· Wing/Section/ Unit wise summary from 1st December 2025 to 31st December 2025
i. SMD Section: 1
· Wing/Section/ Unit wise summary from 1st January 2026 till 31st January 2026
i. SMD Section: 67
ii. O/o ED (Tech): 2
· Wing/Section/ Unit wise summary from 1st February 2026 till 28th February 2026
i. O/o ED/ Finance: 01
· Wing/Section/ Unit wise summary from 1st March 2026 till 31st March 2026
i. Nill
· Wing/Section/ Unit wise summary from 1st April 2026 till 30th April 2026
i. Communication Wing: 1
· Wing/Section/ Unit wise summary from 1st May 2026 till 31st May 2026
i. Communication Wing: 1
ii. O/o ED (Tech): 1

## MPR 5.2_GKC
Monthly Progress Report- Gyanganga.ai (May 2026)
Generated on 1st June 2026
Sl. No. | Title | Till 30th April 2026 | 2026-05-01 | FY 2026-27 | Total (as on 31st May 2026)
1 | Total Number Document on GKP | 1380 | 24 | 33 | 1404
2 | Other Literature on River Ganga | 10337 | 5 | 26 | 10342
Categories-wise details of documents uploaded between 1st to 31st May 2026
Categories | Sub-categories | No. of documents
Publications |  | 0
Journals |  | 0
| Student Thesis Competition (STC) | 0
Articles |  | 0
Books |  | 7
Studies/Reports |  | 14
Guidelines |  | 0
Misellaneous |  | 1
Ganga River (Main Stem)Water Quality Data |  | 0
Data Set | River Atlas | 0
| Ganga River (Main Stem) Water Quality Data (CPCB) | 2
Coffes Table Books |  | 0
River Series |  | 0
Maps |  | 0
Total |  | 24
Details of documents uploaded between 1st to 31st May 2026
S.No | Category | Subject | Organization
1 | Books | Chambal Swachhchata main bashi Jaiv vividhta | WII
2 | Books | Chambal The clean flow of Wilderness | WII
3 | Books | फील्ड गाइड गंगा बेसिन के चयनित सरीसृपों के घोंसलों के बचाव के लिए सर्वोत्तम तरीके | WII
4 | Books | बचाव और पुनर्वास में मिलने वाले मीठे पानी के चिह्नित सरीसृपों के लिए शारीरिक स्थिति स्कोर का आंकलना | WII
5 | Reports | Status and Trends in Ecological Condition of The Ganga River | WII
6 | Reports | Socio Ecological Status of Chambal River for Conservation Planning | WII
7 | Reports | Half Yearly Report Of Planning And Management For Aquatic Species Conservation And Maintenance Of Ecosystem Services In The Ganga River Basin For A Clean Ganga (July to December 2025) | WII
8 | Reports | Mainstreaming biodiversity conservation in village development planning insights from participatory consultations with gram panchayats in the Ganga River Basin | WII
9 | Reports | Nature Interpretation and education for Biodiversity Conservation of Eleven Ganga River Basin States | WII
10 | Reports | Nature Interpretation and Education for Biodiversity Conservation of Five Ganga River States | WII
11 | Books | Ganga ki Pukar | WII
12 | Books | Bal Ganga Prahari Little Hands for Conservation | WII
13 | Reports | Bal Ganga Prahari Programme for five Ganga River states | WII
14 | Reports | Capacity Building of Forest Department and Other Stakeholders for Ganga River Basin | WII
15 | Books | Celebrating Ganga and its Tributaries | WII
16 | Reports | Bringing The Ecosystem Engineers Back Reintroduction Plan for Freshwater Turtles of The Ganga River Basin | WII
17 | Reports | Ganga River Volume III Towards Participatory River Governance Community-Based Conservation of the Ganga River | WII
18 | Reports | Ganga River Volume II Capacity Building of Forest Department and other Stakeholders for Five Ganga River States | WII
19 | Reports | Ganga River Volume I Ecological Assessment of the Ganga River for Conservation Planning | WII
20 | Reports | Status of Trace and Toxic Metals in Rivers of India (january-december 2025) | CWC
21 | Reports | Report on Water Quality Hot Spots in Rivers of India (january-december 2025) | CWC
22 | Miscellaneous | City Spotlight West Bengal | National Institute of Urban Affairs (NIUA)
23 | Water Quality Data | UK/UP/BH/JH/WB (FS) | Central Pollution Control Board (CPCB)
24 | Water Quality Data | UK/UP/BH/JH/WB (FC) | Central Pollution Control Board (CPCB)

## MPR 5.3-Prayag status
(April 2026 - March 2027)
For the month of May (As on 1st June 26)
MPR PRAYAG/ GeoPortal etc
A | OCEMS Status
1 | Installation and Data Status
a | No. of STPs with OCEMS Installed | 280
b | No. of STPs with Flow Data received | 200
c | No. of STPs with Influent Characteristic Data received | 176
d | No. of STPs with Effluent Characteristic Data received | 245
2 | Data Reliability Status
a | No. of STPs with Satisfactory Data received | 233
b | No. of STPs with Poor Data Quality (Annex A1) | 9
c | No. of STPs with No Data Received (Annex A2) | 28
B | OCEMS based results communicated to States till Month | Communicated till May 2026
C | Eflow reports updated till period | Updated till Oct-Dec 2025
D | GDPMS
| No. of Meetings held in May 2026 | 28
| No. of Meetings held in April 2026 | 92
E | PRAYAG_GEO Portal
| No. of Active GIS Layers (Annex B) | 29
| No. of Use Cases | 3
PRAYAG/ Geoportal-MPR May 2026 (Item 5.3, MPR)
No. of STPs with Poor Data Quality (Annex A1)
S. No | State | STP Name | Availability (%)
1 | Uttar Pradesh | 137 MLD STP Kasna Greater Noida | 2.08
2 | Uttar Pradesh | 2.76 MLD STP Goverdhan | 4.77
3 | Uttar Pradesh | 25 MLD STP sector 50 noida | 8.8
4 | Uttar Pradesh | 34 MLD STP sector 50 | 11.19
5 | Uttar Pradesh | 14 MLD STP Bandipur | 16.47
6 | West Bengal | 10 MLD STP at Kankinara | 28.6
7 | Uttar Pradesh | 16 MLD STP Laxmi Nagar UASB | 30.75
8 | Uttar Pradesh | 35 MLD STP Sector-123 | 35.45
9 | Uttar Pradesh | 30 MLD STP Pankha | 38.88
No. of STPs with No Data Received (Annex A2)
S. No | State | STP Name
1 | Delhi | 0.66 MGD Molar Band
2 | Jharkhand | 1.5 MLD STP Chutia
3 | Jharkhand | 1.5 MLD STP Harmu
4 | Jharkhand | 2.57 MLD STP Bokaro
5 | Uttar Pradesh | 1 MLD STP ANUPSHAHAR
6 | Uttar Pradesh | 1.5 MLD STP Anupshahar (UPJN)
7 | Uttar Pradesh | 10.445 MLD STP Etawah
8 | Uttar Pradesh | 100 MLD STP at Noida Sector 168
9 | Uttar Pradesh | 13.50 MLD STP Tixi Nala
10 | Uttar Pradesh | 14 MLD STP Baghpat
11 | Uttar Pradesh | 15 MLD STP Baniyapur UPJN
12 | Uttar Pradesh | 19 MLD STP CG City
13 | Uttar Pradesh | 20 MLD CETP Jajmau
14 | Uttar Pradesh | 21 MLD STP ETAWAH
15 | Uttar Pradesh | 21 MLD STP Pakka Bagh
16 | Uttar Pradesh | 30 MLD STP JAUNPUR
17 | Uttar Pradesh | 40 MLD STP Mapan
18 | Uttar Pradesh | 43 MLD STP Salori
19 | Uttar Pradesh | 7 MLD STP Mirzapur
20 | Uttarakhand | 50 KLD STP Srikot Pauri
21 | Uttarakhand | 75 KLD STP Srikot Pauri
22 | West Bengal | 18 MLD STP Kachanpara
23 | West Bengal | 26.5 MLD STP at Chinsurah
24 | West Bengal | 35 MLD STP Maheshtala Waste Water Management Pvt Ltd
25 | West Bengal | 40 MLD STP at Bally Howarh
26 | West Bengal | 6.5 MLD STP Naihati
27 | West Bengal | 60 MLD STP Baranagar
28 | West Bengal | 65 MLD STP Arupara Howrah
No. of Active GIS Layers (Annex B) as on 01.06.2026
S. No. | Type | GIS Layer
1 | BASIC | Ganga
2 |  | Ganga Centre line SoI
3 |  | Ganga River Basin
4 |  | Popular River
5 |  | Ganga State
6 |  | Ganga Basin Sub District Census
7 |  | Ganga Basin Town Census
8 |  | Census Sub District 2011
9 |  | Census Town 2011
10 | WATER RESOURCES | India River Network
11 |  | Major Aquifers
12 | ECOLOGY | Riverine Wetland (UP/Bihar/Jharkhand)
13 |  | Wetland PAN India (SAC)
14 | RIVER WATER QUALITY | Ganga Polluted Stretch, 2018
15 |  | Ganga Polluted Stretch, 2022
16 |  | Ganga Polluted Stretch, 2023
17 |  | Ganga Polluted Stretch, 2025
18 |  | Manual Water Quality Stations (Locations)
19 |  | RTQMS (Locations)
20 |  | Biomonitoring (Locations) (to be add)
21 | POLLUTION ASPECTS | Sewage Gap Analysis
22 |  | STP (Other than NMCG) (Locations)
23 |  | STP NMCG (Locations)
24 |  | GPIs (Locations)
25 |  | Solid Waste Dumps (IIRS data)
26 | MISC. | Ganga Centre line 1 km points SoI
27 |  | Ganga Final Survey SoI
28 |  | Point outfall 45N SoI
29 |  | Point outfall 44N SoI

## MPR 5.4-Jan Ganga Vertical_Comm
(April 2026 - March 2027)
For the Month of May 2026 (As on 1st June 2026)
MPR Communication
| Followers | Current Month (April 2026) | Current Month- May 2026
1 | Twitter | 123357 | 123899
| Facebook | 564038 | 592956
| Instagram | 122497 | 131368
2 | In Current Month
a) | Webposts (excluding B and C) | Number of Images | Videos (Minutes)
| Twitter | 190 | 31 | 50 Minutes
| Facebook | 190 | 31 | 50 Minutes
| Instagram | 152 | 44 | 66 Minutes
b) | Rebuttals on
| Social Media | 2
c) | Positive Stories | 30 Stories |  | Annex A
Social Media
3 | Youtube
4 | Print Media
a) | Rebutted | No
b) | Positive Stories | 13 |  | Annex A
5 | Publication through PIB
a) | Press Release ( Atleast One per month )
i) | Press Release-Event Based | Nil
ii) | Press Release- Success Story | Nil
b) | Backgrounder ( One per Quarter ) | Planned for June month
c) | Articles/Op-eds in Newspapers ( One article -Half Yearly) | Planned for July-August month
|  | Number of Events | Participation
6 | Events Organised by NMCG |  |  | Annex B
a) | Cleanliness Drives on Yamuna | 5 | Approx. 2500
7 | Events through Partner |  |  | Annex B
a) | DGC & SMCG | 84 | 13798
b) | NGO | 0 | 0
c) | Institutes
| Total | 84 | 13798
8 | Sponsorship | Yamuna Ki Pukar organised by SYA | 500
9 | Capacity Building Training /Workshop (Communication Unit ) | Nil
Annex B
| Annex A | S. No 2 C, 4 B | Coverage
S. No. | Title | Date | Twitter | Facebook | Instagram
1 | River sensitive urban planning | 26-05-2026 | https://x.com/cleanganganmcg/status/2059155849289822452?s=20 | https://www.facebook.com/share/p/18hGvbJYiY/ | https://www.instagram.com/p/DYyq9pEsVPu/?igsh=MWk2bGd2bnA0NjNi
2 | Lakes of Delhi | 26-05-2026 | https://x.com/cleanganganmcg/status/2059142160830898293?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid0c9XQHw4BKpbg33kjGR76rC72RjNWLVRxgLPjbQj5d84mqatw7aC9ur1xupxKmyjLl | https://www.instagram.com/p/DYykLkqDP49/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
3 | Waste water is the new fresh water | 25-05-2026 | https://x.com/cleanganganmcg/status/2058793726240293279?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid0nKG2saGGMpZ3bXvkvnvPK7raetGEgEv1v85PkDu8x39ua1d7szxrges7SLbrVVHtl | https://www.instagram.com/p/DYwHLMeMnzg/?utm_source=ig_web_copy_link&igsh=NTc4MTIwNjQ2YQ==
4 | Kolkata projects update | 21-05-2026 | https://x.com/cleanganganmcg/status/2057331875472191526?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid02UpUZmkXfUpXjVhrS6JGhx6rjB91ssLkNwDMJkt1aCYzsTx5F4NNqKAaLqi3EKbZGl | https://www.instagram.com/p/DYltZNQMLi_/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
5 | 75 MLD STP, Dhandbad | 20-05-2026 | https://x.com/cleanganganmcg/status/2057054425479549112?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid0CnShH476v9FUP5AFXYgfW9z552KzFthPRe3osGHocuG9ER1ZM1qeJrzaE4KdN1grl | https://www.instagram.com/p/DYjub-WM1Di/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
6 | East Kolkata wetlands | 20-05-2026 | https://x.com/cleanganganmcg/status/2057069040993186147?s=20 | https://www.facebook.com/share/p/1EDCi12ntP/ | https://www.instagram.com/reel/DYj4eQovdac/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
7 | Public review, Rishikesh | 20-05-2026 | https://x.com/cleanganganmcg/status/2057344461148225610?s=20 | https://facebook.com/reel/1271090685240475/ | https://www.instagram.com/reel/DYj9GzIkk-R/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
8 | 15 MLD STP, Sapera basti | 19-05-2026 | https://x.com/cleanganganmcg/status/2056695089511182677?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid02CTDpSANc6LQGzjCSD7ju9BvNq3TpRq3t5Cke4DaCcqqetiBHdCScoL9eTiA4GGJxl | https://www.instagram.com/p/DYhLXpgDDty/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
9 | Jojobera Thermal Power Plant, Jharkhand | 19-05-2026 | https://x.com/cleanganganmcg/status/2056624711518613607?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid0hZ4j9chdUe3pD3PyisWu7mtUYq5devwWn9TABzkTcZ7DgTQrJ64v13XwvVW3Zmivl | https://www.instagram.com/p/DYgsJ2qjAOo/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
10 | 22 MLD STP, Hazipur | 18-05-2026 | https://x.com/cleanganganmcg/status/2056306582867365991?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid0JqE5Qng6zytoWQbYYEv6roswdcp9MBsvZ3qZP3Zr9HKHfXnSDDGmRW8ypTASbizVl | https://www.instagram.com/p/DYebn6dDCjs/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
11 | Turtle was released at Kaziranga | 15-05-2026 | https://x.com/cleanganganmcg/status/2055203484631511521 | https://www.facebook.com/cleanganganmcg/posts/pfbid02ZBdD7Y1FSaBBQ9S9VicoXjs7TEDxFWxJ9kFXdY6y9XaVHEhJue769WFev2BopWqrl | https://www.instagram.com/p/DYWldnMj_Yk/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
12 | Polluted stretch update, Bihar | 15-05-2026 | https://x.com/cleanganganmcg/status/2055661466708238501?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid02QABTL9ZTmHMh47VxGzfH6PsWnZhEVEK2Q5aKEmpQjz1px349kqAsuiUkaqp7RMWyl | https://www.instagram.com/reel/DYZ4b67vNhL/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
13 | LiDAR survey | 15-05-2026 | https://x.com/cleanganganmcg/status/2055151152472416318?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid02FocfpuoSb9V9hwsahdYPnZX1viCAfXZ1Qa95z3TUaBAA3T2Lmh1vTffmARu85uK8l | https://www.instagram.com/reel/DYWNmrRv3Re/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
14 | Public review, Patna | 14-05-2026 | https://x.com/cleanganganmcg/status/2054928002992275843?s=20 | https://facebook.com/reel/1408272391063059/ | https://www.instagram.com/reel/DYUs1bkvKxr/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
15 | Project update | 14-05-2026 | https://x.com/cleanganganmcg/status/2054798960976675046?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid0ZfoTuozAZ1YmERTdwnG13U95sPRf5HDW2HHvV5tntsaRyhSxpdCWgVbgPHJcxZaSl | -----------------------------------
16 | One District One River | 14-05-2026 | https://x.com/cleanganganmcg/status/2054893688837558518?s=20 | ----------------- | -----------------------
17 | Polluted stretch update, Kannauj to varanasi | 14-05-2026 | https://x.com/cleanganganmcg/status/2054798960976675046?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid0ZfoTuozAZ1YmERTdwnG13U95sPRf5HDW2HHvV5tntsaRyhSxpdCWgVbgPHJcxZaSl | ----------------------------
18 | Project Update | 13-05-2026 | https://x.com/cleanganganmcg/status/2054534117568680195?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid0dz17MMiwHXh9zHfHcBSk59GuHydYMEtZG3BYhwCQCGSaGkBTEDhNYsrf7ayY9NA8l | ---------------------
19 | HAM, PRAYAG etc | 13-05-2026 | https://x.com/cleanganganmcg/status/2054455114203910465?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid021d9uvctj3BsF28k6nkW2SDPxx49e8wTMARvEjapL2r99R549tno7noZdBJcem9dVl | https://www.instagram.com/p/DYRQtnFDAp8/?utm_source=ig_web_copy_link&igsh=NTc4MTIwNjQ2YQ==
20 | Gangetic Dolphin, Bihar (Rebuttal) | 13-05-2026 | https://x.com/cleanganganmcg/status/2054437897953280203?s=20 | https://www.facebook.com/reel/1577295190720431 | https://www.instagram.com/reel/DYRImeyghgi/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
21 | CSIR-NGIR | 13-05-2026 | https://x.com/cleanganganmcg/status/2054406520549376240?s=20 | ------------------- | -----------------------------
22 | Project update, Uttarakhand | 2026-12-05 | https://x.com/cleanganganmcg/status/2054170655059513578?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid02YyHSrdiiY3ntDWA6WzUycMLcDPanW69TpxLJME4TRcTQvhHvqLeNA94hkEYtGgerl | ----------------------------------
23 | Public review, Kanpur | 2026-11-05 | https://x.com/cleanganganmcg/status/2053796732027457675?s=20 | https://facebook.com/reel/1045651031121339/ | https://www.instagram.com/reel/DYMk8W2scVv/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
24 | Assi Nala | 2026-11-05 | https://x.com/cleanganganmcg/status/2053681548885647478?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid0DH4Fa9r49grmgEAJgz3ALd9ra9ZQ7Kx9cjZiAZuvMKfUeTNYkJnpz6ypCQLXD6Qal
25 | Ganga Barrage | 08-05-2026 | https://x.com/cleanganganmcg/status/2052761945233830322?s=20 | https://facebook.com/reel/2151094338987986/ | https://www.instagram.com/reel/DYFOtvRP6pu/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
26 | Dolphin rescue | 07-05-2026 | https://x.com/cleanganganmcg/status/2052364332483350755?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid0j6j6S1LbfcrHsocES7ejSbkzP3EujePrSLg4hLsz5CtXXyMGEWB6WcmxgthZhGT4l | https://www.instagram.com/p/DYCbYjMjylG/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
27 | 7.5 MLD STP, Munni ki reti | 07-05-2026 | https://x.com/cleanganganmcg/status/2052252967953432617?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid02gD62vTHHMBHwYop2WbZg2idmLocSWQdycDiHTB7JYdBvEHZRbnCzggrCRogUGp7bl | https://www.instagram.com/reel/DYBntH6McMn/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
28 | CPCB report | 06-05-2026 | https://x.com/cleanganganmcg/status/2051893888768671878?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid0dG4nMXuUnteLDTJejRVvBm1n6TAy9D8pZ6F2jmcDL8xnukuqWqdwPBVzYYC6N7erl | https://www.instagram.com/reel/DX_EQpEMYlC/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
29 | CPCB state by state report | 04-05-2026 | --------------------------- | https://www.facebook.com/cleanganganmcg/posts/pfbid0Az3DKJaZPyJbyFdfckUz8mFxupGFqEtKBYoTFBdqk9N1Sc2S5LfTN8Swkh3LYjNol | https://www.instagram.com/reel/DX61PWjPx5M/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
30 | Swacchta drive, Kanpur | 03-05-2026 | https://x.com/cleanganganmcg/status/2050875945041686832?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid02E1krnB3mi8petwCNVGRM11Fd23qZkDGpRAABwg9p6b41LrURBNP3uSmmjYy6962El | ----------------------
31 | Project Update | 02-05-2026 | https://x.com/cleanganganmcg/status/2050438704251228230?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid0AsAACY2kugkFCVB1nrK5SxJjM5P8tkZZVwEb6KNnj7tYNr6MwF2tmZhoALEDezKal | --------------------------
32 | 3.5 MLD STP Tapovan (Rebuttal) | 02-05-2026 | https://x.com/cleanganganmcg/status/2050453696937672999?s=20 | https://www.facebook.com/cleanganganmcg/posts/pfbid0CuKkPpeuQPJwXETtzEc7ZHrn4uEz7UuCavdB4dRYRjvAMbjSKR1RQogYdHcfAQvjl | https://www.instagram.com/p/DX03OwKD0WN/?utm_source=ig_web_copy_link&igsh=MzRlODBiNWFlZA==
33 | Namami Gange Ignites Cleanliness Drive | 2nd May
34 | No polluted stretch of Ganga main stem in Uttarakhand: Shri CR Paatil | 6th May
35 | Namami Gnage 60 MLD STP construction to start in May end | 10th May
36 | Namami Gange Mission to Accelerate the Revamp of Chhoti Gandak River | 10th May
37 | Centre Pledges Full Support for Aviral and Nirmal Ganga: C.R. Paatil | 12th May
38 | Sewage treatment capacity across Ganga basin up 10-fold in seven years | 14th May
39 | Uttar Pradesh Emerges as the Anchor State of Namami Gange’s River Rejuvenation Mission | 16th May
40 | UP Gets ₹16K Crore as Namami Gange Boosts River Water Quality | 16th May
41 | NMCG launches aerial 3D mapping of Ganga corridor from Ballia to Farakka | 16th May
42 | Jharkhand maintains zero-polluted Ganga stretches | 20th May
43 | Major Stretch of Ganga in Bengal Declared Fit for Bathing | 22th May
44 | NMCG pushes circular water model to reuse wastewater | 26th May
45 | NMCG Initiative: Wastewater Being Treated and Used for Industrial Purposes | 26th May
| Annex B | S. No 5,6,7
S. No. | Event Name (Activity Type) | Agency | Date | Venue | Participants
1 | Cleanliness Drives on Yamuna | NMCG with NGOs (Delhi) | Every Sunday | Kalindi Kunj, Geeta Colony, Pushta 1, ITO Chhath Ghat and Teesra Pul, Yamuna Khadar, Usmanpur | NGOs- Saksham Bhoomi Foundation, Yuva Parivartan Foundation, Friends of Yamuna Swachh Yamuna Abhiyaan; Schools, Colleges, Youth Groups, NGOs and Yamuna Task Force etc.
2 | Yamuna Ki Pukar | Swachh Yamuna Abhiyan | 31.05.2026 | 3rd Pushta , Yamuna Khadar , Usmanpur | School/ College students, Youth Groups, Volunteers, NGOs,YTF, Local Community
UTTARAKHAND
3 | Swachhta Abhiyaan, Cleanliness and awareness drive tll Gangotri | DGC Uttarkashi | 22.05.2026 | Gangotri Uttarkashi | Students, Youth Groups, Volunteers & Local Communities
4 | Special Sanitation & awareness campaign at Ganga Ghats | Govt. PG College, Ramnagar, GGIC Jawalapur, Haridwar | 25.06.2026 | Ganga Ghats. Jawalapur, Haridwar | Students, Youth Groups, Volunteers & Local Communities
5 | Namami Gange Wall Painting Campaign | Govt. PG College, Uttarkashi | 16.05.2026 | Govt. PG College- Uttarkashi | College Students, Teachers & Volunteers
6 | Special Sanitation & awareness campaign at Ganga Ghats | Govt. PG Collge, Ramnagar, GGIC Jawalapur, Hraidwar | 25.05.2026 | Ganga Ghats. Jawalapur, Haridwar | College Students, Teachers, Youth Groups, Volunteers & Local Communities
UTTAR PRADESH
7 | Run for Ganga and awareness rally- Chandauli | DGC & Forest Department | 20.05.2026 | Avdhoot Bhagwan Ram Ghat, Chandauli | Forest Dept., School/College Students & Volunteers
8 | International Day for Biological Diversity | DGC-Bulandshahr, Auraiya, Lakhimpur Kheeri, Lalitpur, Chandauli, Jhansi, Maharajganj, Hathras, Ghazipur, Ayodhya, Forest Departments, Schools/Colleges & NGOs | 22.05.2026 | Pandit Deen Dayal Upadhyay Park, Ambition Inter College (Chandauli), Nagar Van (Jhansi, Hathras) | Forest Departments, School/College Students, Teachers, Youth Groups, Volunteers & Local Communities
9 | Ganga Chaupal | DGC- Ghazipur, Mathura, Gram Panchayats of Ganga Gram | 12.05.2026 | Collector Ghat (Ghazipur), Devraha Baba Ghat (Mathura) | Youth, Volunteers & Local Communities
10 | Gomti Sharmdaan Campaign | DGC- Lakhimpur Kheeri, Save Gomti Group under Gomti Sharmdaan Movement | 05.05.2026 | Amri and Imalia Ghat at Gomti River | Youth, Volunteers, NGO representatives & local communities
11 | 1 Hour Shramdaan on Ghats | DGC-Rampur, NGOs and Schools/Colleges | Every Sunday | Rampur (Nahal Barraj, Ramganag Ghat and Kosi Ghat) | School/College Students, Youth, Volunteers, NGO representatives & local communities
12 | Cleanliness & Awareness Drives, Swachhta Shapth, Painting & other Competitions | DGC-Rampur, Lalitpur, Ayodhya and School/Colleges | different dates throughout the month | Mansarovar Talab (Lalitpur), Guptar Ghat (Ayodhya), Gulabwati Inter College; UPS Ghatampur; UPS City, Bakar Inter College, Agarpur, Balghar Higher Sec. School, Ram Ganga Ghat(Rampur) | School/ College Students, Youth Groups, Volunteers, NGOs & Local Communities
13 | Maha Ganga Aarti, yamuna Aarti & Cultural Program (Ganga Dussehra) | DGC- Muzaffarpur, Mathura, Prayagraj | 23 & 25.05.2026 | Shukrtal Ghat (Muzzaffarpur), Devraha Baba Ghat (Vrindavan), Sangam (Prayagraj) | Volunteers & Local Communities
BIHAR
14 | Awareness Campaigns and Educational Outreach Campaign, Swachhta Abhiyaan, Swachhta Rally, Pad Yatra, Nukkad Natak | DGCs-Vaishali, Hajipur,Kaimur, Sheohar, Siwan, Katihar, Kishanganj, Saran, Jahanabad, Sonepur, Nagar Parishad, District Education Office, Education, Aganwadis, DFO, Women Groups, and various schools & colleges | different dates throughout the month | Konhara Ghat (Hajipur), Karhagola Ghat (Katihar), Kalighat, Gai Ghat (Siwan), Dev Ghat (Kishanganj), Ghats and other locations | School & College Students, Teachers, Youth Groups, Volunteers, NGOs & Local Communities
15 | Plantation and Swachhta Shapath | DGC- Saran, Samastipur, Darbhanga, Jahanbad, Forest Department, DFO, Schools/ Colleges and NGOs | 25.04.26 to 24.05.26 | Parmanandpur (Sonepur), GMRD College, Mohanpur (Samastipur), MK College (Darbhanga) | Forest Department, DGC, School & College Students, Youth Groups, Volunteers, NGOs & Local Communities
16 | Ganga Aarti, Competitions , Seminars and Cultural Programs | DGC- Aurangabad, Vaishali, Bhojpur, Kaimur, Bhojpur, Madhubani | 14-16 & 23-26.05.2026 | Ramgarh & Adhura Block (Kaimur), Mahauli Ganga Ghat (Bhojpur), Watson School (Madhubani), GT Road, Anugrah Middle School (Aurangabad) | School & College Students, Teachers, Youth Groups, Religious Groups, Volunteers, NGOs & Local Communities
JHARKHAND
17 | Awareness Sessions, Nukkad Natak and Educational Outreach | DGC- Dhanbad & Sahibganj, CSIR-CIMFR Dhanbad, Nagar Parishad, Education Department, Self Help Groups, Schools/Colleges | different dates throughout the month | Mukteshwar Dham Ghat (Sahibganj), Namami Gange Ghat, Rajrappa (Ramgarh)
18 | Cleanliness Drives, Yoga, Sport Activities and Competitions | DGC- Sahibganj, Nagar Parishad, Youth Groups, NGOs and school/colleges | different dates | various schools/colleges, community & market areas and key locations | School & College Students, Teachers, Youth Groups, Volunteers, NGOs & Local Communities
19 | Ganga Dussehra, Ganga Aarti | DGC- Sahibganj & Ramgarh | 23 to 26.05.2026 | Mukteshwar Dham Ghat, Namami Gange Ghat (Ramgarh) | School Students, Teachers, Religious Groups, Sports & Youth groups, Volunteers & NGOs

## MPR 5.5 RCA
(April 2026 - March 2027)
For the month of MAY
Organisation: River Cities Alliance
Sl. No. | Activity | Till Mar 2026 | 2026-05-26 | Total
1 | Web posts | 82 | 9 | 91
2 | Workshops (excluding 5b /URMP Workshops) | 19 | 0 | 19
3 | Seminar/ Webinar/Meetings | 40 | 2 | 42
4 | Exposure Visits | 2 | 0 | 2
5 | URMP Related (Non Ganga Basin)
| a) Meetings in States | 7 | 0 | 7
| b) Workshops in States | 2 | 0 | 2
6 | Publications
| a) Newsletter | 5 | 0 | 5
| b) Others | 21 | 2 | 23
7 | Concept Notes | 9 | 0 | 9
8 | Demands Received
| a) Cities | 14 | 0 | 14
| b) Academia | 7 | 0 | 7
Annexures
List (Type 2,3,4,5) March
Sl. No. | Event Topic | Type | Venue | Date/Days /Duration | Number of Participants
1 | Webinar on 'AI For Water Management' | 3 | Online | 15.05.2026 | 125
2 | Meeting with State of Manipur - EOI for joining RCA + Exploring potential synergies under RCA | 3 | Online | 29.05.2026 | 5
List (Type 1,6) March
Sl. No. | Subject | Type | Date
1 | Inspirational Monday Series on "Orange County Ground Water Replenishment System in California " | 1 | 04.05.2026
2 | Quiz series 12: Rivers, Cities, and Answers | 1 | 06.05.2026
3 | Inspirational Monday Series on "Community led Naganadi River rejuvenation initiative in Tamil Nadu " | 1 | 11.05.2026
4 | Quiz series 13: Rivers, Cities, and Answers | 1 | 06.05.2026
5 | Quiz series 14: Rivers, Cities, and Answers | 1 | 13.05.2026
6 | Inspirational Monday Series on "Alkaff Lake as Urban Flood Management measure in Singapore" | 1 | 16.05.2026
7 | Quiz series 15: Rivers, Cities, and Answers | 1 | 20.05.2026
8 | Inspirational Monday Series on "Tsomgo Lake Restoration Initative in Sikkim" | 1 | 25.05.2026
9 | Quiz series 16: Rivers, Cities, and Answers | 1 | 27.05.2026
10 | Perception Report for Jhansi | 6b | 12.05.2026
11 | Perception Report for Pilibhit | 6b | 20.05.2026
List (Type 7) March
Sl. No. | Subject | Type | Date
Demands for RCA (Type 8) March
Sl. No. | Subject | Type | Date

## COE-IT BHU
(April 2026 - March 2027)
For the month of May
Smart Laboratory on Clean Rivers (MPR 5.6a)
Sl. No. | Activity | Till Apr-26 | 2026-05-01 | Total
1 | Workshops / Conference - Organised | 5 | 0 | 5
2 | Capacity Building Workshops - Organised | 5 | 0 | 5
3 | Publications | 0 | 0 | 0
4 | STP Performance Evaluation (Number of STPs) | 7 | 3 | 10
5 | DSS Project (Physical progress %) | 62% | 5% | 67%
5a | No. Draft Modules Finalized | 10 | 0 | 10
6 | Characterisation of Emerging Pollutants (Physical progress %) | 63% | 1% | 64%
6a | No. of Draft SOPs Finalized | 5 | 0 | 5
7 | Hydrogeological Model of Varuna Basin for MAR sites (Physical progress %) | 61% | 4% | 65%
7a | No. of Sites implemented | 0 | 0 | 0
Annexure
List (Type 1, 2)
Sl. No. | Event Topic | Type | Venue | Date/Days/ Duration | Number of Participants
List (Type 3)
Sl. No. | Name of Publication | Date | Submitted
List (Type 4)
Sl. No. | Name of STP | Date visited | Report submitted
1 | ChandanNagar, West Bengal STP | 25.05.26 | -
2 | Bhatpara, West Bengal STP | 26.05.26 | -
3 | Kalyani, West Bengal STP | 26.05.26 | -
List (Type 5, 6, 7,)
Sl. No. | Project Details | Type | Activities
1 | DSS Project | Type 5 | The STP modules are being enhanced through the integration of a costing estimation engine and a customized area-based STP site selection and validation mechanism, with a strong emphasis on user-centric site validation. Additionally, work is underway to incorporate integrated project management capabilities within the DSS framework, aimed at improving overall system usability, functionality, and decision-making efficiency.
2 | Characterisation of Emerging Pollutants | Type 6 | Drafting of SOPs for Carbamazepine, Trimethoprim and Celecoxib is ongoing similar to the previously submitted SOPs for 5 emerging pollutants. A sewage sludge-based remediation material is being augmented. Varuna Basin samples are in process of data acquisition.
3 | Hydrogeological Model of Varuna Basin for MAR sites | Type 7 | FloaTEM Data acquisition and TEM data analysis for identification of potential zones for Managed Aquifer Recharge (MAR) to enhance river- 90 new TEM points has been surveyed.
List (Type 5a, 6a, 7a)
Sl. No. | Draft Finalized | Type | Comments
1 | SOPs for Carbamazepine, Trimethoprim and Celecoxib | Type 6a | Under Process
2 | Two sites for MAR structures at Rameshwar & Isharwar | Type 7a | Re-Tendering done on 01.06.26 due to less no. of bids received as on 29.05.26

## COE-IIT Delhi
(April 2025 - May 2026)
For the month of May
India-Netherlands Centre of Excellence on Water (MPR 5.6b)
Sl. No. | Activity | Till April-26 | 2026-05-01 | Total
1 | Workshops / Conference Organised | 9 | 0 | 9
2 | Capacity Building Workshops | 0 | 0 | 0
3 | Publications | 2 | 0 | 2
4 | STP Performance Evaluation (No of STPs) | 0 | 1 | 1
5 | Digital Twin project | 0 | 0 | 0
6 | Web Posts | 77 | 14 | 91
Annexure
List (Type 2,3)
Sl. No. | Event Topic | Type | Venue | Date/Days/Duration | Number of Participants
1
2
3
List (Type 4)
Sl. No. | Name of STP | Date visited | Report submitted
1 | Field Visit to 68 MLD Capacity Sewage Treatment Plant (STP) in Dehradun | 19-05-2026 | Planned for June